THE 120 HOUSE

Operations, Care, Safety, Partnerships & Website Manual

A 200-page implementation system for peer-run recovery housing

| Planning Target | Owner | Primary Location |
| --- | --- | --- |
| Purchase and launch by Summer 2027 | Restoring Hope Ministries | Adjacent to 529 S Jefferson Street, Green Bay, WI 54301 |

Prepared for board deliberation, fundraising, lender engagement, community partnership, and implementation.

### EXECUTIVE DIRECTION

# Board Charge and Use of This Manual

This manual is a working governance instrument. It is designed to move RHM from concept to a lawful, financed, safe, and measurable recovery-housing operation. Assumptions are intentionally visible so that the board can replace them with verified property, lender, insurance, wage, occupancy, and partner data before commitment.

## Required actions

Approve the planning target and the women-first launch sequence.

Authorize property, zoning, legal, insurance, and capital-market due diligence without authorizing purchase.

Name a board project committee and adopt monthly reporting.

Require a minimum operating reserve and written overnight-safety approval before opening.

Adopt the red-line rule: no resident admission before fire, occupancy, insurance, policy, training, and emergency-readiness gates are complete.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Project governance standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise project governance decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for board charge and use of this manual, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable board charge and use of this manual work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

CAUTION / DECISION GATE: This is a planning document, not legal, tax, lending, clinical, zoning, employment, or insurance advice. Obtain written professional review before reliance.

### I. OPERATING PHILOSOPHY

# Christ-Centered Care Covenant

Christ-Centered Care Covenant is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the christ-centered care covenant workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Christ-Centered Care Covenant standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise christ-centered care covenant decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for christ-centered care covenant, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable christ-centered care covenant work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### I. OPERATING PHILOSOPHY

# Voluntary Spiritual Participation

Voluntary Spiritual Participation is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the voluntary spiritual participation workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Voluntary Spiritual Participation standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise voluntary spiritual participation decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for voluntary spiritual participation, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable voluntary spiritual participation work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### I. OPERATING PHILOSOPHY

# Peer Leadership Principles

Peer Leadership Principles is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the peer leadership principles workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Peer Leadership Principles standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise peer leadership principles decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for peer leadership principles, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable peer leadership principles work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### I. OPERATING PHILOSOPHY

# Recovery-Oriented Language

Recovery-Oriented Language is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the recovery-oriented language workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Recovery-Oriented Language standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise recovery-oriented language decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for recovery-oriented language, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable recovery-oriented language work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### I. OPERATING PHILOSOPHY

# Trauma-Responsive Culture

Trauma-Responsive Culture is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the trauma-responsive culture workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Trauma-Responsive Culture standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise trauma-responsive culture decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for trauma-responsive culture, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable trauma-responsive culture work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### I. OPERATING PHILOSOPHY

# Resident Dignity

Resident Dignity is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the resident dignity workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Resident Dignity standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise resident dignity decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for resident dignity, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable resident dignity work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### I. OPERATING PHILOSOPHY

# Strengths and Responsibility

Strengths and Responsibility is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the strengths and responsibility workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Strengths and Responsibility standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise strengths and responsibility decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for strengths and responsibility, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable strengths and responsibility work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### I. OPERATING PHILOSOPHY

# Community Belonging

Community Belonging is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the community belonging workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Community Belonging standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise community belonging decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for community belonging, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable community belonging work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### I. OPERATING PHILOSOPHY

# Clinical Boundary

Clinical Boundary is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the clinical boundary workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Clinical Boundary standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise clinical boundary decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for clinical boundary, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable clinical boundary work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### I. OPERATING PHILOSOPHY

# Operating Commitments

Operating Commitments is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the operating commitments workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Operating Commitments standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise operating commitments decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for operating commitments, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable operating commitments work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### II. ADMISSION AND INTAKE

# Referral Intake

Referral Intake is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the referral intake workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Referral Intake standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise referral intake decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for referral intake, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable referral intake work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### II. ADMISSION AND INTAKE

# Eligibility Screen

Eligibility Screen is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the eligibility screen workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Eligibility Screen standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise eligibility screen decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for eligibility screen, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable eligibility screen work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### II. ADMISSION AND INTAKE

# Exclusion and Referral Criteria

Exclusion and Referral Criteria is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the exclusion and referral criteria workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Exclusion and Referral Criteria standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise exclusion and referral criteria decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for exclusion and referral criteria, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable exclusion and referral criteria work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### II. ADMISSION AND INTAKE

# Fair Housing Review

Fair Housing Review is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the fair housing review workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Fair Housing Review standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise fair housing review decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for fair housing review, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable fair housing review work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### II. ADMISSION AND INTAKE

# Medication and MOUD

Medication and MOUD is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the medication and moud workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Medication and MOUD standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise medication and moud decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for medication and moud, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable medication and moud work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### II. ADMISSION AND INTAKE

# Pregnancy and Health Needs

Pregnancy and Health Needs is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the pregnancy and health needs workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Pregnancy and Health Needs standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise pregnancy and health needs decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for pregnancy and health needs, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable pregnancy and health needs work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### II. ADMISSION AND INTAKE

# Parent and Child Intake

Parent and Child Intake is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the parent and child intake workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Parent and Child Intake standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise parent and child intake decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for parent and child intake, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable parent and child intake work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### II. ADMISSION AND INTAKE

# Consent and Releases

Consent and Releases is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the consent and releases workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Consent and Releases standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise consent and releases decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for consent and releases, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable consent and releases work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### II. ADMISSION AND INTAKE

# Move-In Orientation

Move-In Orientation is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the move-in orientation workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Move-In Orientation standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise move-in orientation decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for move-in orientation, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable move-in orientation work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### II. ADMISSION AND INTAKE

# Admission Audit

Admission Audit is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the admission audit workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Admission Audit standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise admission audit decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for admission audit, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable admission audit work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### III. FIRST 30 DAYS

# Day 0 Welcome

Day 0 Welcome is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the day 0 welcome workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Day 0 Welcome standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise day 0 welcome decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for day 0 welcome, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable day 0 welcome work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### III. FIRST 30 DAYS

# Days 1-3 Stabilization

Days 1-3 Stabilization is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the days 1-3 stabilization workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Days 1-3 Stabilization standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise days 1-3 stabilization decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for days 1-3 stabilization, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable days 1-3 stabilization work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### III. FIRST 30 DAYS

# Week 1 Safety and Belonging

Week 1 Safety and Belonging is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the week 1 safety and belonging workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Week 1 Safety and Belonging standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise week 1 safety and belonging decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for week 1 safety and belonging, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable week 1 safety and belonging work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### III. FIRST 30 DAYS

# Week 2 Rhythms and Skills

Week 2 Rhythms and Skills is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the week 2 rhythms and skills workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Week 2 Rhythms and Skills standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise week 2 rhythms and skills decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for week 2 rhythms and skills, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable week 2 rhythms and skills work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### III. FIRST 30 DAYS

# Week 3 Community and Purpose

Week 3 Community and Purpose is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the week 3 community and purpose workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Week 3 Community and Purpose standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise week 3 community and purpose decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for week 3 community and purpose, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable week 3 community and purpose work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### III. FIRST 30 DAYS

# Week 4 Transition Planning

Week 4 Transition Planning is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the week 4 transition planning workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Week 4 Transition Planning standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise week 4 transition planning decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for week 4 transition planning, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable week 4 transition planning work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### III. FIRST 30 DAYS

# Case Management Rhythm

Case Management Rhythm is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the case management rhythm workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Case Management Rhythm standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise case management rhythm decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for case management rhythm, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable case management rhythm work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### III. FIRST 30 DAYS

# Peer Contact Rhythm

Peer Contact Rhythm is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the peer contact rhythm workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Peer Contact Rhythm standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise peer contact rhythm decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for peer contact rhythm, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable peer contact rhythm work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### III. FIRST 30 DAYS

# Counsel and Neurofeedback Choice

Counsel and Neurofeedback Choice is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the counsel and neurofeedback choice workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Counsel and Neurofeedback Choice standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise counsel and neurofeedback choice decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for counsel and neurofeedback choice, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable counsel and neurofeedback choice work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### III. FIRST 30 DAYS

# Thirty-Day Review

Thirty-Day Review is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the thirty-day review workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Thirty-Day Review standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise thirty-day review decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for thirty-day review, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable thirty-day review work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IV. INDIVIDUALIZED CARE

# Recovery Capital Assessment

Recovery Capital Assessment is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the recovery capital assessment workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Recovery Capital Assessment standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise recovery capital assessment decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for recovery capital assessment, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable recovery capital assessment work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IV. INDIVIDUALIZED CARE

# Individual Service Plan

Individual Service Plan is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the individual service plan workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Individual Service Plan standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise individual service plan decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for individual service plan, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable individual service plan work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IV. INDIVIDUALIZED CARE

# Biblical Counseling Plan

Biblical Counseling Plan is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the biblical counseling plan workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Biblical Counseling Plan standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise biblical counseling plan decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for biblical counseling plan, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable biblical counseling plan work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IV. INDIVIDUALIZED CARE

# Clinical Referral Plan

Clinical Referral Plan is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the clinical referral plan workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Clinical Referral Plan standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise clinical referral plan decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for clinical referral plan, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable clinical referral plan work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IV. INDIVIDUALIZED CARE

# Education and Employment Plan

Education and Employment Plan is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the education and employment plan workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Education and Employment Plan standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise education and employment plan decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for education and employment plan, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable education and employment plan work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IV. INDIVIDUALIZED CARE

# Financial Capability Plan

Financial Capability Plan is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the financial capability plan workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Financial Capability Plan standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise financial capability plan decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for financial capability plan, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable financial capability plan work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IV. INDIVIDUALIZED CARE

# Family Restoration Plan

Family Restoration Plan is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the family restoration plan workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Family Restoration Plan standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise family restoration plan decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for family restoration plan, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable family restoration plan work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IV. INDIVIDUALIZED CARE

# Physical Wellness Plan

Physical Wellness Plan is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the physical wellness plan workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Physical Wellness Plan standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise physical wellness plan decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for physical wellness plan, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable physical wellness plan work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IV. INDIVIDUALIZED CARE

# Spiritual Formation Plan

Spiritual Formation Plan is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the spiritual formation plan workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Spiritual Formation Plan standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise spiritual formation plan decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for spiritual formation plan, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable spiritual formation plan work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IV. INDIVIDUALIZED CARE

# Quarterly Care Review

Quarterly Care Review is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the quarterly care review workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Quarterly Care Review standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise quarterly care review decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for quarterly care review, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable quarterly care review work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### V. PEER-RUN GOVERNANCE

# Resident Council

Resident Council is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the resident council workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Resident Council standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise resident council decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for resident council, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable resident council work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### V. PEER-RUN GOVERNANCE

# House Meeting

House Meeting is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the house meeting workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| House Meeting standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise house meeting decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for house meeting, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable house meeting work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### V. PEER-RUN GOVERNANCE

# Peer Leader Selection

Peer Leader Selection is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the peer leader selection workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Peer Leader Selection standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise peer leader selection decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for peer leader selection, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable peer leader selection work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### V. PEER-RUN GOVERNANCE

# Peer Leader Training

Peer Leader Training is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the peer leader training workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Peer Leader Training standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise peer leader training decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for peer leader training, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable peer leader training work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### V. PEER-RUN GOVERNANCE

# Peer Role Boundaries

Peer Role Boundaries is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the peer role boundaries workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Peer Role Boundaries standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise peer role boundaries decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for peer role boundaries, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable peer role boundaries work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### V. PEER-RUN GOVERNANCE

# Mutual Accountability

Mutual Accountability is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the mutual accountability workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Mutual Accountability standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise mutual accountability decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for mutual accountability, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable mutual accountability work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### V. PEER-RUN GOVERNANCE

# Resident Voting

Resident Voting is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the resident voting workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Resident Voting standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise resident voting decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for resident voting, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable resident voting work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### V. PEER-RUN GOVERNANCE

# Conflict Mediation

Conflict Mediation is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the conflict mediation workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Conflict Mediation standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise conflict mediation decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for conflict mediation, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable conflict mediation work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### V. PEER-RUN GOVERNANCE

# Peer Feedback

Peer Feedback is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the peer feedback workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Peer Feedback standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise peer feedback decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for peer feedback, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable peer feedback work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### V. PEER-RUN GOVERNANCE

# Leadership Succession

Leadership Succession is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the leadership succession workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Leadership Succession standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise leadership succession decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for leadership succession, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable leadership succession work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VI. OVERNIGHT SAFETY

# Night-Risk Classification

Night-Risk Classification is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the night-risk classification workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Night-Risk Classification standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise night-risk classification decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for night-risk classification, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable night-risk classification work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

CAUTION / DECISION GATE: No camera, staffing, disciplinary, clinical, faith, or housing rule should be implemented without the applicable rights and compliance review.

### VI. OVERNIGHT SAFETY

# First-30-Day Coverage

First-30-Day Coverage is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the first-30-day coverage workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| First-30-Day Coverage standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise first-30-day coverage decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for first-30-day coverage, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable first-30-day coverage work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VI. OVERNIGHT SAFETY

# On-Call Rotation

On-Call Rotation is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the on-call rotation workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| On-Call Rotation standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise on-call rotation decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for on-call rotation, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable on-call rotation work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VI. OVERNIGHT SAFETY

# Resident Night Lead

Resident Night Lead is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the resident night lead workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Resident Night Lead standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise resident night lead decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for resident night lead, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable resident night lead work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

CAUTION / DECISION GATE: No camera, staffing, disciplinary, clinical, faith, or housing rule should be implemented without the applicable rights and compliance review.

### VI. OVERNIGHT SAFETY

# Camera Placement

Camera Placement is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the camera placement workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Camera Placement standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise camera placement decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for camera placement, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable camera placement work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

CAUTION / DECISION GATE: No camera, staffing, disciplinary, clinical, faith, or housing rule should be implemented without the applicable rights and compliance review.

### VI. OVERNIGHT SAFETY

# No-Audio Default

No-Audio Default is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the no-audio default workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| No-Audio Default standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise no-audio default decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for no-audio default, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable no-audio default work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VI. OVERNIGHT SAFETY

# Privacy Zones

Privacy Zones is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the privacy zones workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Privacy Zones standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise privacy zones decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for privacy zones, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable privacy zones work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VI. OVERNIGHT SAFETY

# Emergency Call Tree

Emergency Call Tree is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the emergency call tree workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Emergency Call Tree standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise emergency call tree decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for emergency call tree, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable emergency call tree work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VI. OVERNIGHT SAFETY

# Night Incident Response

Night Incident Response is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the night incident response workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Night Incident Response standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise night incident response decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for night incident response, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable night incident response work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

CAUTION / DECISION GATE: No camera, staffing, disciplinary, clinical, faith, or housing rule should be implemented without the applicable rights and compliance review.

### VI. OVERNIGHT SAFETY

# Quarterly Safety Validation

Quarterly Safety Validation is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the quarterly safety validation workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Quarterly Safety Validation standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise quarterly safety validation decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for quarterly safety validation, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable quarterly safety validation work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VII. CRISIS AND EMERGENCY

# Overdose Response

Overdose Response is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the overdose response workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Overdose Response standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise overdose response decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for overdose response, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable overdose response work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VII. CRISIS AND EMERGENCY

# Naloxone Readiness

Naloxone Readiness is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the naloxone readiness workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Naloxone Readiness standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise naloxone readiness decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for naloxone readiness, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable naloxone readiness work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VII. CRISIS AND EMERGENCY

# Suicide-Risk Escalation

Suicide-Risk Escalation is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the suicide-risk escalation workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Suicide-Risk Escalation standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise suicide-risk escalation decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for suicide-risk escalation, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable suicide-risk escalation work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VII. CRISIS AND EMERGENCY

# Medical Emergency

Medical Emergency is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the medical emergency workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Medical Emergency standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise medical emergency decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for medical emergency, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable medical emergency work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VII. CRISIS AND EMERGENCY

# Violence and Threats

Violence and Threats is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the violence and threats workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Violence and Threats standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise violence and threats decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for violence and threats, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable violence and threats work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VII. CRISIS AND EMERGENCY

# Missing Resident

Missing Resident is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the missing resident workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Missing Resident standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise missing resident decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for missing resident, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable missing resident work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VII. CRISIS AND EMERGENCY

# Fire and Evacuation

Fire and Evacuation is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the fire and evacuation workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Fire and Evacuation standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise fire and evacuation decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for fire and evacuation, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable fire and evacuation work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VII. CRISIS AND EMERGENCY

# Severe Weather

Severe Weather is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the severe weather workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Severe Weather standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise severe weather decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for severe weather, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable severe weather work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VII. CRISIS AND EMERGENCY

# Child Safety Event

Child Safety Event is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the child safety event workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Child Safety Event standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise child safety event decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for child safety event, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable child safety event work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VII. CRISIS AND EMERGENCY

# Post-Incident Review

Post-Incident Review is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the post-incident review workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Post-Incident Review standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise post-incident review decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for post-incident review, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable post-incident review work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VIII. HOUSE OPERATIONS

# Daily Schedule

Daily Schedule is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the daily schedule workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Daily Schedule standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise daily schedule decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for daily schedule, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable daily schedule work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VIII. HOUSE OPERATIONS

# Quiet Hours

Quiet Hours is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the quiet hours workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Quiet Hours standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise quiet hours decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for quiet hours, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable quiet hours work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VIII. HOUSE OPERATIONS

# Chores

Chores is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the chores workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Chores standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise chores decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for chores, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable chores work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VIII. HOUSE OPERATIONS

# Food and Kitchen

Food and Kitchen is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the food and kitchen workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Food and Kitchen standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise food and kitchen decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for food and kitchen, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable food and kitchen work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VIII. HOUSE OPERATIONS

# Medication Storage

Medication Storage is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the medication storage workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Medication Storage standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise medication storage decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for medication storage, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable medication storage work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VIII. HOUSE OPERATIONS

# Drug Testing

Drug Testing is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the drug testing workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Drug Testing standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise drug testing decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for drug testing, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable drug testing work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VIII. HOUSE OPERATIONS

# Visitors

Visitors is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the visitors workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Visitors standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise visitors decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for visitors, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable visitors work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VIII. HOUSE OPERATIONS

# Transportation

Transportation is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the transportation workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Transportation standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise transportation decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for transportation, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable transportation work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VIII. HOUSE OPERATIONS

# Property Care

Property Care is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the property care workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Property Care standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise property care decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for property care, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable property care work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### VIII. HOUSE OPERATIONS

# House Operations Audit

House Operations Audit is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the house operations audit workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| House Operations Audit standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise house operations audit decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for house operations audit, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable house operations audit work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IX. CONDUCT AND ACCOUNTABILITY

# Resident Agreement

Resident Agreement is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the resident agreement workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Resident Agreement standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise resident agreement decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for resident agreement, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable resident agreement work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IX. CONDUCT AND ACCOUNTABILITY

# Substance-Free Standard

Substance-Free Standard is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the substance-free standard workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Substance-Free Standard standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise substance-free standard decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for substance-free standard, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable substance-free standard work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IX. CONDUCT AND ACCOUNTABILITY

# Relapse Response

Relapse Response is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the relapse response workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Relapse Response standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise relapse response decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for relapse response, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable relapse response work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IX. CONDUCT AND ACCOUNTABILITY

# Return-to-Use Safety

Return-to-Use Safety is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the return-to-use safety workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Return-to-Use Safety standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise return-to-use safety decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for return-to-use safety, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable return-to-use safety work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IX. CONDUCT AND ACCOUNTABILITY

# Behavioral Expectations

Behavioral Expectations is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the behavioral expectations workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Behavioral Expectations standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise behavioral expectations decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for behavioral expectations, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable behavioral expectations work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IX. CONDUCT AND ACCOUNTABILITY

# Progressive Accountability

Progressive Accountability is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the progressive accountability workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Progressive Accountability standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise progressive accountability decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for progressive accountability, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable progressive accountability work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IX. CONDUCT AND ACCOUNTABILITY

# Grievance Procedure

Grievance Procedure is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the grievance procedure workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Grievance Procedure standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise grievance procedure decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for grievance procedure, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable grievance procedure work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IX. CONDUCT AND ACCOUNTABILITY

# Appeal Process

Appeal Process is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the appeal process workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Appeal Process standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise appeal process decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for appeal process, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable appeal process work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### IX. CONDUCT AND ACCOUNTABILITY

# Discharge Planning

Discharge Planning is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the discharge planning workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Discharge Planning standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise discharge planning decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for discharge planning, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable discharge planning work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

CAUTION / DECISION GATE: No camera, staffing, disciplinary, clinical, faith, or housing rule should be implemented without the applicable rights and compliance review.

### IX. CONDUCT AND ACCOUNTABILITY

# Readmission

Readmission is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the readmission workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Readmission standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise readmission decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for readmission, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable readmission work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### X. STAFF AND STUDENT PRACTICE

# Recovery Home Director Role

Recovery Home Director Role is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the recovery home director role workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Recovery Home Director Role standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise recovery home director role decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for recovery home director role, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable recovery home director role work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### X. STAFF AND STUDENT PRACTICE

# Case Manager Role

Case Manager Role is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the case manager role workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Case Manager Role standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise case manager role decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for case manager role, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable case manager role work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### X. STAFF AND STUDENT PRACTICE

# Peer Specialist Role

Peer Specialist Role is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the peer specialist role workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Peer Specialist Role standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise peer specialist role decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for peer specialist role, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable peer specialist role work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### X. STAFF AND STUDENT PRACTICE

# RHSBC Student Role

RHSBC Student Role is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the rhsbc student role workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| RHSBC Student Role standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise rhsbc student role decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for rhsbc student role, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable rhsbc student role work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### X. STAFF AND STUDENT PRACTICE

# Christian Social Work Student

Christian Social Work Student is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the christian social work student workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Christian Social Work Student standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise christian social work student decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for christian social work student, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable christian social work student work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### X. STAFF AND STUDENT PRACTICE

# UWGB Psychology Student

UWGB Psychology Student is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the uwgb psychology student workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| UWGB Psychology Student standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise uwgb psychology student decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for uwgb psychology student, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable uwgb psychology student work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### X. STAFF AND STUDENT PRACTICE

# UWGB Social Work Student

UWGB Social Work Student is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the uwgb social work student workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| UWGB Social Work Student standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise uwgb social work student decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for uwgb social work student, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable uwgb social work student work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### X. STAFF AND STUDENT PRACTICE

# Supervisor Role

Supervisor Role is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the supervisor role workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Supervisor Role standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise supervisor role decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for supervisor role, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable supervisor role work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### X. STAFF AND STUDENT PRACTICE

# Contractor Role

Contractor Role is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the contractor role workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Contractor Role standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise contractor role decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for contractor role, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable contractor role work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### X. STAFF AND STUDENT PRACTICE

# Scope-of-Practice Audit

Scope-of-Practice Audit is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the scope-of-practice audit workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Scope-of-Practice Audit standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise scope-of-practice audit decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for scope-of-practice audit, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable scope-of-practice audit work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XI. SUPERVISION AND STAFF CARE

# Weekly Supervision

Weekly Supervision is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the weekly supervision workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Weekly Supervision standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise weekly supervision decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for weekly supervision, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable weekly supervision work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XI. SUPERVISION AND STAFF CARE

# Peer Reflective Practice

Peer Reflective Practice is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the peer reflective practice workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Peer Reflective Practice standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise peer reflective practice decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for peer reflective practice, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable peer reflective practice work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XI. SUPERVISION AND STAFF CARE

# Student Seminar

Student Seminar is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the student seminar workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Student Seminar standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise student seminar decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for student seminar, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable student seminar work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XI. SUPERVISION AND STAFF CARE

# Critical-Incident Debrief

Critical-Incident Debrief is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the critical-incident debrief workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Critical-Incident Debrief standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise critical-incident debrief decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for critical-incident debrief, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable critical-incident debrief work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XI. SUPERVISION AND STAFF CARE

# Compassion Fatigue

Compassion Fatigue is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the compassion fatigue workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Compassion Fatigue standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise compassion fatigue decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for compassion fatigue, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable compassion fatigue work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XI. SUPERVISION AND STAFF CARE

# Shift Design

Shift Design is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the shift design workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Shift Design standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise shift design decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for shift design, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable shift design work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XI. SUPERVISION AND STAFF CARE

# Timekeeping

Timekeeping is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the timekeeping workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Timekeeping standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise timekeeping decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for timekeeping, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable timekeeping work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XI. SUPERVISION AND STAFF CARE

# Performance Review

Performance Review is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the performance review workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Performance Review standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise performance review decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for performance review, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable performance review work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XI. SUPERVISION AND STAFF CARE

# Corrective Action

Corrective Action is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the corrective action workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Corrective Action standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise corrective action decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for corrective action, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable corrective action work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XI. SUPERVISION AND STAFF CARE

# Succession Coverage

Succession Coverage is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the succession coverage workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Succession Coverage standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise succession coverage decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for succession coverage, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable succession coverage work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XII. WELLNESS AND ENRICHMENT

# Hair Stylist Day

Hair Stylist Day is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the hair stylist day workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Hair Stylist Day standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise hair stylist day decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for hair stylist day, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable hair stylist day work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XII. WELLNESS AND ENRICHMENT

# Massage Therapy Day

Massage Therapy Day is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the massage therapy day workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Massage Therapy Day standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise massage therapy day decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for massage therapy day, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable massage therapy day work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XII. WELLNESS AND ENRICHMENT

# Christian Exercise

Christian Exercise is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the christian exercise workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Christian Exercise standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise christian exercise decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for christian exercise, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable christian exercise work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XII. WELLNESS AND ENRICHMENT

# Nature Groups

Nature Groups is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the nature groups workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Nature Groups standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise nature groups decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for nature groups, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable nature groups work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XII. WELLNESS AND ENRICHMENT

# UWGB Self-Care Visits

UWGB Self-Care Visits is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the uwgb self-care visits workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| UWGB Self-Care Visits standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise uwgb self-care visits decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for uwgb self-care visits, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable uwgb self-care visits work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XII. WELLNESS AND ENRICHMENT

# Nutrition Education

Nutrition Education is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the nutrition education workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Nutrition Education standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise nutrition education decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for nutrition education, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable nutrition education work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XII. WELLNESS AND ENRICHMENT

# Sleep Health

Sleep Health is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the sleep health workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Sleep Health standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise sleep health decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for sleep health, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable sleep health work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XII. WELLNESS AND ENRICHMENT

# Creative Arts

Creative Arts is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the creative arts workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Creative Arts standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise creative arts decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for creative arts, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable creative arts work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XII. WELLNESS AND ENRICHMENT

# Celebration and Milestones

Celebration and Milestones is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the celebration and milestones workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Celebration and Milestones standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise celebration and milestones decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for celebration and milestones, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable celebration and milestones work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XII. WELLNESS AND ENRICHMENT

# Wellness Quality Review

Wellness Quality Review is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the wellness quality review workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Wellness Quality Review standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise wellness quality review decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for wellness quality review, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable wellness quality review work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIII. FAMILY RESIDENCE

# Family Unit Eligibility

Family Unit Eligibility is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the family unit eligibility workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Family Unit Eligibility standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise family unit eligibility decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for family unit eligibility, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable family unit eligibility work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIII. FAMILY RESIDENCE

# Child Safety Plan

Child Safety Plan is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the child safety plan workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Child Safety Plan standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise child safety plan decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for child safety plan, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable child safety plan work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIII. FAMILY RESIDENCE

# Parenting Assessment

Parenting Assessment is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the parenting assessment workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Parenting Assessment standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise parenting assessment decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for parenting assessment, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable parenting assessment work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIII. FAMILY RESIDENCE

# Christian Parenting Class

Christian Parenting Class is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the christian parenting class workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Christian Parenting Class standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise christian parenting class decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for christian parenting class, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable christian parenting class work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIII. FAMILY RESIDENCE

# Child Psychologist Education

Child Psychologist Education is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the child psychologist education workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Child Psychologist Education standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise child psychologist education decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for child psychologist education, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable child psychologist education work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIII. FAMILY RESIDENCE

# School Coordination

School Coordination is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the school coordination workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| School Coordination standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise school coordination decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for school coordination, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable school coordination work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIII. FAMILY RESIDENCE

# Family Routines

Family Routines is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the family routines workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Family Routines standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise family routines decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for family routines, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable family routines work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIII. FAMILY RESIDENCE

# Visitation and Custody

Visitation and Custody is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the visitation and custody workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Visitation and Custody standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise visitation and custody decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for visitation and custody, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable visitation and custody work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIII. FAMILY RESIDENCE

# Family Rent Model

Family Rent Model is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the family rent model workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Family Rent Model standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise family rent model decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for family rent model, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable family rent model work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIII. FAMILY RESIDENCE

# Family Transition Plan

Family Transition Plan is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the family transition plan workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Family Transition Plan standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise family transition plan decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for family transition plan, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable family transition plan work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIV. COUNSELING AND NEUROFEEDBACK

# RHM Office Referral

RHM Office Referral is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the rhm office referral workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| RHM Office Referral standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise rhm office referral decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for rhm office referral, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable rhm office referral work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIV. COUNSELING AND NEUROFEEDBACK

# Informed Choice

Informed Choice is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the informed choice workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Informed Choice standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise informed choice decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for informed choice, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable informed choice work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIV. COUNSELING AND NEUROFEEDBACK

# Biblical Counseling Intake

Biblical Counseling Intake is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the biblical counseling intake workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Biblical Counseling Intake standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise biblical counseling intake decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for biblical counseling intake, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable biblical counseling intake work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIV. COUNSELING AND NEUROFEEDBACK

# Neurofeedback Intake

Neurofeedback Intake is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the neurofeedback intake workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Neurofeedback Intake standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise neurofeedback intake decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for neurofeedback intake, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable neurofeedback intake work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIV. COUNSELING AND NEUROFEEDBACK

# Clinical Contraindications

Clinical Contraindications is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the clinical contraindications workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Clinical Contraindications standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise clinical contraindications decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for clinical contraindications, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable clinical contraindications work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIV. COUNSELING AND NEUROFEEDBACK

# Scheduling and Transport

Scheduling and Transport is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the scheduling and transport workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Scheduling and Transport standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise scheduling and transport decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for scheduling and transport, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable scheduling and transport work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIV. COUNSELING AND NEUROFEEDBACK

# Documentation Separation

Documentation Separation is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the documentation separation workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Documentation Separation standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise documentation separation decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for documentation separation, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable documentation separation work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIV. COUNSELING AND NEUROFEEDBACK

# Payment and Scholarship

Payment and Scholarship is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the payment and scholarship workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Payment and Scholarship standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise payment and scholarship decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for payment and scholarship, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable payment and scholarship work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIV. COUNSELING AND NEUROFEEDBACK

# Outcome Review

Outcome Review is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the outcome review workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Outcome Review standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise outcome review decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for outcome review, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable outcome review work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIV. COUNSELING AND NEUROFEEDBACK

# Service Quality Audit

Service Quality Audit is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the service quality audit workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Service Quality Audit standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise service quality audit decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for service quality audit, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable service quality audit work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XV. PARTNERSHIPS

# Church Group Calendar

Church Group Calendar is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the church group calendar workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Church Group Calendar standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise church group calendar decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for church group calendar, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable church group calendar work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XV. PARTNERSHIPS

# Licensed Provider Network

Licensed Provider Network is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the licensed provider network workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Licensed Provider Network standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise licensed provider network decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for licensed provider network, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable licensed provider network work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XV. PARTNERSHIPS

# Primary Care Partnership

Primary Care Partnership is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the primary care partnership workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Primary Care Partnership standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise primary care partnership decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for primary care partnership, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable primary care partnership work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XV. PARTNERSHIPS

# Dental and Vision

Dental and Vision is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the dental and vision workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Dental and Vision standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise dental and vision decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for dental and vision, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable dental and vision work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XV. PARTNERSHIPS

# Employment Partners

Employment Partners is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the employment partners workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Employment Partners standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise employment partners decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for employment partners, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable employment partners work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XV. PARTNERSHIPS

# Education Partners

Education Partners is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the education partners workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Education Partners standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise education partners decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for education partners, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable education partners work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XV. PARTNERSHIPS

# Legal Aid

Legal Aid is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the legal aid workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Legal Aid standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise legal aid decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for legal aid, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable legal aid work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XV. PARTNERSHIPS

# Transportation Partners

Transportation Partners is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the transportation partners workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Transportation Partners standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise transportation partners decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for transportation partners, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable transportation partners work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XV. PARTNERSHIPS

# Food and Clothing

Food and Clothing is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the food and clothing workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Food and Clothing standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise food and clothing decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for food and clothing, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable food and clothing work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XV. PARTNERSHIPS

# Partnership Review

Partnership Review is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the partnership review workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Partnership Review standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise partnership review decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for partnership review, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable partnership review work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVI. DOCUMENTATION

# Resident Record

Resident Record is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the resident record workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Resident Record standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise resident record decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for resident record, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable resident record work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVI. DOCUMENTATION

# Daily House Log

Daily House Log is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the daily house log workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Daily House Log standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise daily house log decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for daily house log, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable daily house log work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVI. DOCUMENTATION

# Case Note

Case Note is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the case note workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Case Note standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise case note decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for case note, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable case note work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVI. DOCUMENTATION

# Peer Contact Note

Peer Contact Note is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the peer contact note workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Peer Contact Note standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise peer contact note decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for peer contact note, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable peer contact note work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVI. DOCUMENTATION

# Incident Report

Incident Report is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the incident report workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Incident Report standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise incident report decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for incident report, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable incident report work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVI. DOCUMENTATION

# Medication Record Boundary

Medication Record Boundary is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the medication record boundary workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Medication Record Boundary standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise medication record boundary decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for medication record boundary, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable medication record boundary work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVI. DOCUMENTATION

# Financial Ledger

Financial Ledger is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the financial ledger workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Financial Ledger standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise financial ledger decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for financial ledger, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable financial ledger work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVI. DOCUMENTATION

# Consent Register

Consent Register is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the consent register workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Consent Register standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise consent register decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for consent register, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable consent register work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVI. DOCUMENTATION

# Data Retention

Data Retention is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the data retention workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Data Retention standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise data retention decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for data retention, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable data retention work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVI. DOCUMENTATION

# Record Audit

Record Audit is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the record audit workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Record Audit standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise record audit decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for record audit, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable record audit work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVII. WEBSITE STRATEGY

# Website Purpose

Website Purpose is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the website purpose workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Website Purpose standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise website purpose decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for website purpose, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable website purpose work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVII. WEBSITE STRATEGY

# Home Page

Home Page is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the home page workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Home Page standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise home page decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for home page, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable home page work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVII. WEBSITE STRATEGY

# Program Page

Program Page is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the program page workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Program Page standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise program page decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for program page, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable program page work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVII. WEBSITE STRATEGY

# Women’s Housing Page

Women’s Housing Page is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the women’s housing page workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Women’s Housing Page standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise women’s housing page decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for women’s housing page, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable women’s housing page work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVII. WEBSITE STRATEGY

# Family Housing Page

Family Housing Page is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the family housing page workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Family Housing Page standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise family housing page decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for family housing page, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable family housing page work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVII. WEBSITE STRATEGY

# Future Men’s Housing Page

Future Men’s Housing Page is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the future men’s housing page workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Future Men’s Housing Page standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise future men’s housing page decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for future men’s housing page, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable future men’s housing page work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVII. WEBSITE STRATEGY

# Partner Page

Partner Page is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the partner page workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Partner Page standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise partner page decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for partner page, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable partner page work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVII. WEBSITE STRATEGY

# Give Page

Give Page is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the give page workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Give Page standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise give page decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for give page, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable give page work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVII. WEBSITE STRATEGY

# Interest Form

Interest Form is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the interest form workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Interest Form standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise interest form decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for interest form, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable interest form work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVII. WEBSITE STRATEGY

# Privacy and Accessibility

Privacy and Accessibility is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the privacy and accessibility workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Privacy and Accessibility standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise privacy and accessibility decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for privacy and accessibility, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable privacy and accessibility work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVIII. WEBSITE CONTENT AND CRM

# Resident Interest Workflow

Resident Interest Workflow is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the resident interest workflow workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Resident Interest Workflow standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise resident interest workflow decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for resident interest workflow, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable resident interest workflow work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVIII. WEBSITE CONTENT AND CRM

# Referral Interest Workflow

Referral Interest Workflow is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the referral interest workflow workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Referral Interest Workflow standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise referral interest workflow decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for referral interest workflow, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable referral interest workflow work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVIII. WEBSITE CONTENT AND CRM

# Volunteer Interest

Volunteer Interest is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the volunteer interest workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Volunteer Interest standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise volunteer interest decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for volunteer interest, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable volunteer interest work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVIII. WEBSITE CONTENT AND CRM

# Church Interest

Church Interest is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the church interest workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Church Interest standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise church interest decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for church interest, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable church interest work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVIII. WEBSITE CONTENT AND CRM

# Student Practicum Interest

Student Practicum Interest is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the student practicum interest workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Student Practicum Interest standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise student practicum interest decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for student practicum interest, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable student practicum interest work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVIII. WEBSITE CONTENT AND CRM

# Donor Interest

Donor Interest is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the donor interest workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Donor Interest standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise donor interest decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for donor interest, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable donor interest work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVIII. WEBSITE CONTENT AND CRM

# Automated Acknowledgment

Automated Acknowledgment is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the automated acknowledgment workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Automated Acknowledgment standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise automated acknowledgment decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for automated acknowledgment, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable automated acknowledgment work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVIII. WEBSITE CONTENT AND CRM

# Lead Assignment

Lead Assignment is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the lead assignment workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Lead Assignment standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise lead assignment decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for lead assignment, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable lead assignment work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVIII. WEBSITE CONTENT AND CRM

# Follow-Up Calendar

Follow-Up Calendar is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the follow-up calendar workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Follow-Up Calendar standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise follow-up calendar decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for follow-up calendar, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable follow-up calendar work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XVIII. WEBSITE CONTENT AND CRM

# CRM Dashboard

CRM Dashboard is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the crm dashboard workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| CRM Dashboard standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise crm dashboard decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for crm dashboard, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable crm dashboard work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIX. QUALITY AND OUTCOMES

# Occupancy Dashboard

Occupancy Dashboard is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the occupancy dashboard workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Occupancy Dashboard standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise occupancy dashboard decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for occupancy dashboard, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable occupancy dashboard work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIX. QUALITY AND OUTCOMES

# Retention Dashboard

Retention Dashboard is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the retention dashboard workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Retention Dashboard standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise retention dashboard decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for retention dashboard, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable retention dashboard work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIX. QUALITY AND OUTCOMES

# Safety Dashboard

Safety Dashboard is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the safety dashboard workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Safety Dashboard standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise safety dashboard decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for safety dashboard, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable safety dashboard work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIX. QUALITY AND OUTCOMES

# Recovery Capital Dashboard

Recovery Capital Dashboard is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the recovery capital dashboard workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Recovery Capital Dashboard standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise recovery capital dashboard decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for recovery capital dashboard, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable recovery capital dashboard work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIX. QUALITY AND OUTCOMES

# Resident Satisfaction

Resident Satisfaction is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the resident satisfaction workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Resident Satisfaction standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise resident satisfaction decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for resident satisfaction, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable resident satisfaction work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIX. QUALITY AND OUTCOMES

# Spiritual Care Feedback

Spiritual Care Feedback is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the spiritual care feedback workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Spiritual Care Feedback standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise spiritual care feedback decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for spiritual care feedback, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable spiritual care feedback work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIX. QUALITY AND OUTCOMES

# Family Outcomes

Family Outcomes is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the family outcomes workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Family Outcomes standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise family outcomes decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for family outcomes, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable family outcomes work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIX. QUALITY AND OUTCOMES

# Student Learning Outcomes

Student Learning Outcomes is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the student learning outcomes workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Student Learning Outcomes standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise student learning outcomes decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for student learning outcomes, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable student learning outcomes work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIX. QUALITY AND OUTCOMES

# Partner Satisfaction

Partner Satisfaction is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the partner satisfaction workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Partner Satisfaction standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise partner satisfaction decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for partner satisfaction, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable partner satisfaction work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XIX. QUALITY AND OUTCOMES

# Continuous Improvement

Continuous Improvement is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the continuous improvement workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Continuous Improvement standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise continuous improvement decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for continuous improvement, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable continuous improvement work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XX. FORMS AND LAUNCH TOOLS

# Resident Application

Resident Application is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the resident application workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Resident Application standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise resident application decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for resident application, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable resident application work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XX. FORMS AND LAUNCH TOOLS

# Referral Form

Referral Form is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the referral form workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Referral Form standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise referral form decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for referral form, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable referral form work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XX. FORMS AND LAUNCH TOOLS

# Risk Screen

Risk Screen is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the risk screen workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Risk Screen standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise risk screen decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for risk screen, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable risk screen work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XX. FORMS AND LAUNCH TOOLS

# Thirty-Day Plan

Thirty-Day Plan is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the thirty-day plan workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Thirty-Day Plan standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise thirty-day plan decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for thirty-day plan, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable thirty-day plan work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XX. FORMS AND LAUNCH TOOLS

# Weekly Progress Review

Weekly Progress Review is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the weekly progress review workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| Weekly Progress Review standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise weekly progress review decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for weekly progress review, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable weekly progress review work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XX. FORMS AND LAUNCH TOOLS

# House Meeting Agenda

House Meeting Agenda is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the house meeting agenda workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| House Meeting Agenda standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise house meeting agenda decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for house meeting agenda, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable house meeting agenda work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### XX. FORMS AND LAUNCH TOOLS

# On-Call Log

On-Call Log is a controlled operating component of The 120 House. It converts the ministry’s Christ-centered, peer-led vision into a repeatable practice that protects resident dignity, supports recovery, clarifies scope, and produces evidence for supervision and continuous improvement. The practice must remain voluntary where faith participation is concerned, must not substitute students or peers for licensed care, and must be adapted to each resident’s documented risks, strengths, family responsibilities, and goals.

## Required actions

Define the on-call log workflow in plain language, including who may act, who must supervise, and what may never be delegated.

Ask residents and peers to test the workflow for dignity, usability, cultural humility, and unintended barriers.

Identify emergency exceptions, mandated reporting duties, clinical referral triggers, and the precise documentation required.

Train staff, peers, students, volunteers, and contractors before they perform any related duty; verify competency rather than attendance alone.

Review results monthly for the first six months and quarterly thereafter, using incidents, complaints, near misses, resident feedback, and outcome data.

## Control and funding matrix

| Control | Owner | Timing | Evidence |
| --- | --- | --- | --- |
| On-Call Log standard | Project Lead | Pre-close | Approved written standard and accountable owner |
| Budget authorization | Treasurer | Monthly | Budget-to-actual report and variance explanation |
| Compliance verification | Counsel / consultant | Gate review | Written opinion, permit, certificate, or inspection |
| Resident voice | Peer council | Quarterly | Minutes, feedback trend, and corrective action |
| Outcome monitoring | Recovery Home Director | Monthly | Dashboard with occupancy, safety, retention, and exits |

## Board-ready evidence

A concise on-call log decision memo with assumptions and alternatives.

Named owner, deadline, dependencies, and escalation route.

A documented resident-rights and nondiscrimination review.

Proof that the decision is financially sustainable at 75%, 85%, and 95% occupancy.

Board minutes showing approval, recusals, restrictions, and follow-up date.

## Implementation worksheet

| Work item | Required response |
| --- | --- |
| Current state | Describe what RHM already has in place for on-call log, including documents, relationships, staff capacity, and unresolved assumptions. |
| 30-day deliverable | Produce the first verifiable on-call log work product and place it in the project data room with an owner and review date. |
| 60-day test | Test the work product with at least one resident/peer voice, one operational leader, and one independent professional or partner. |
| 90-day gate | Approve, revise, defer, or stop the workstream based on written evidence; record the effect on capital need, opening date, staffing, and risk. |
| Acceptance measure | Evidence is complete, understandable to a new leader, financially modeled, rights-aware, and capable of being audited after launch. |

Decision record: Owner: ____________________  Due: __________  Status: ☐ approve  ☐ revise  ☐ defer  ☐ stop  Next review: __________

### SOURCE REGISTER AND FINAL IMPLEMENTATION CONTROLS

# Evidence Base, Assumptions and Professional Review

| Source / authority | Use in plan |
| --- | --- |
| Wis. Stat. § 46.234, Recovery residences; registration | https://docs.legis.wisconsin.gov/statutes/statutes/46/ii/234 |
| Wisconsin DHS Recovery Residence Registry | https://www.dhs.wisconsin.gov/regulations/recovery-registry.htm |
| NARR National Standard 3.0 Compendium | Supplied file: NARR-National-Standard-3.0-Compendium(1).pdf |
| SAMHSA, Recovery and Recovery Support | https://www.samhsa.gov/substance-use/recovery |
| HUD/DOJ Joint Statement on Group Homes and Local Land Use | https://www.justice.gov/crt/joint-statement-department-justice-and-department-housing-and-urban-development |
| Wis. Stat. § 942.08, Invasion of privacy | https://docs.legis.wisconsin.gov/statutes/statutes/942/08 |
| CDC/NIOSH, Shift Work and Long Work Hours | https://www.cdc.gov/niosh/work-hour-training-for-nurses/longhours/ |
| Green Bay rent benchmark - Zumper, Aug. 2026 median $1,099 | https://www.zumper.com/rent-research/green-bay-wi |
| Green Bay rent benchmark - Rent.com, 2026: studio $799; 1BR $960; 2BR $1,220 | https://www.rent.com/wisconsin/green-bay-apartments/rent-trends |
| Wisconsin DHS Opioid Settlement Funds | https://www.dhs.wisconsin.gov/opioids/settlement-funds.htm |
| SAMHSA BRSS TACS Peer-Run Organization Toolkit | Supplied file: brss-102-c4-Toolkit-v24.pdf |
| Hope, Faith & Recovery Toolkit (2023) | Supplied file: HopeFaithRecovery2023EditionFinal.pdf |
| Faith-Based Rural Recovery Housing and Supports | Supplied file: Faith-Based-Rural-Recovery-Hosing-and-Spports.pdf |
| FCC Faith-Based Toolkit (2021) | Supplied file: FCC_Faith-Based-Toolkit_2021.pdf |

Remaining planning modules incorporated by reference for board work sessions: Incident Form; Website Copy Approval; Opening-Day Checklist.

Every numeric input is an initial planning assumption until supported by a quote, appraisal, executed agreement, public award, or operating history.

The board should update this manual at acquisition, 30 days before opening, 90 days after opening, and annually.

## Final assumption register

| Assumption to replace | Required verification | Deadline |
| --- | --- | --- |
| Property price and exact parcels | Executed offer, appraisal, title and survey | Before offer contingency expires |
| Zoning and lawful occupancy | Written municipal determination and counsel review | Before nonrefundable commitment |
| Bed and family-unit capacity | Architect/fire/occupancy analysis | Before final underwriting |
| Debt terms | Lender term sheet and amortization schedule | Before board financing vote |
| Insurance availability | Binder identifying exclusions and overnight model | Before closing |
| Resident pricing and demand | Referral survey, waitlist and affordability review | 90 days before opening |
| Public and grant funding | Executed award; never treat an application as revenue | Before included in base case |
| Staffing and on-call cost | Wage quotes, payroll burden and scheduling test | 60 days before opening |

Board certification: Chair ____________________  Treasurer ____________________  Date __________  Next annual review __________