## Live Risk Register
TRC Live Risk Register | TRC Live Risk Register | TRC Live Risk Register | TRC Live Risk Register | TRC Live Risk Register | TRC Live Risk Register | TRC Live Risk Register | TRC Live Risk Register | TRC Live Risk Register | TRC Live Risk Register | TRC Live Risk Register | TRC Live Risk Register | TRC Live Risk Register | TRC Live Risk Register
Risk ID | Risk Statement | Category | Early Warning Signs / Triggers | Likely Effect on Performance | Current Rating | Existing / Planned Mitigation | Risk Owner | Monitoring Indicator | Review Frequency | Immediate Next Step | Status | Last Updated | Escalation Level
R1 | Low locomotive availability and reliability continue to constrain freight and passenger operations. | Operations / Rolling Stock | Average available locomotives remains far below plan; repeated mechanical breakdowns; maintenance backlog persists. | Reduced freight haulage, reduced passenger service reliability, lower revenue, delayed trains, and reputational damage. | High | Complete locomotive maintenance outsourcing, secure spare parts, and closely track locomotive delivery and rehabilitation. | DRS / Operations / PMU | Average locomotives available per day; number of breakdowns; service cancellations or delays. | Monthly / Weekly operations review | Agree a weekly locomotive recovery tracker and report it to management. | Open |  | Red
R2 | Frequent accidents and incidents continue to expose the Corporation to safety, service, and reputation risk. | Safety | Rise in major accidents, repeated incident trends, and weak compliance with inspection and maintenance requirements. | Line closures, service interruption, casualties or damage, public concern, and high recovery cost. | High | Strengthen track inspection, complete priority rehabilitation works, enforce safety briefs and refresher training, and track root causes. | Safety Unit / DCEI / Operations | Number of major accidents; number of minor incidents; causes by section. | Monthly | Create a standing safety escalation note for all high-risk sections. | Open |  | Red
R3 | Poor track condition and speed restrictions continue to weaken operational efficiency. | Infrastructure | Severe speed restrictions remain on critical sections; track defects recur; rehabilitation progress lags. | Longer journey times, poor punctuality, lower customer confidence, higher accident exposure, and reduced freight throughput. | High | Prioritize routine and urgent maintenance, accelerate rehabilitation on the worst sections, and monitor reduction in restriction length. | DCEI / Engineering | Km under speed restriction; turnaround time; punctuality; maintenance completion status. | Monthly | Identify the top five priority sections and monitor them separately. | Open |  | Red
R4 | Wagon turnaround time remains above target and is affecting cargo flow. | Operations / Logistics | Turnaround exceeds planned days; congestion and slow recovery in wagon circulation continue. | Reduced freight capacity, delayed customer service, lower asset utilization, and weaker revenue performance. | Medium-High | Tighten dispatch planning, improve line reliability, reduce avoidable stoppages, and monitor terminal and section bottlenecks. | Operations / Commercial | Average wagon turnaround days; freight backlog; train cycle performance. | Monthly | Assign accountability for turnaround improvement and report weekly. | Open |  | Amber
R5 | Incomplete port links and terminal readiness are limiting SGR freight uptake. | Project Delivery / Commercial | Cargo handling interface remains incomplete; customer access to loading points is weak; double handling persists. | SGR freight volumes remain below target, creating lost commercial opportunities and weaker return on infrastructure investment. | High | Finalize port link and terminal works, improve customer interface arrangements, and coordinate with relevant stakeholders. | DCEI / Commercial / Project Teams | SGR freight tonnage; readiness of port interface works; customer uptake. | Monthly / Project review | Prepare a short port-link delivery status note for management. | Open |  | Red
R6 | Service disruption from protests, washaways, and extreme weather remains a live operational risk. | External / Service Continuity | Public disturbances, flood events, washaways, and unexpected closures recur with short notice. | Suspended services, loss of freight and passenger revenue, reputational damage, and emergency operating cost. | High | Maintain emergency response protocols, strengthen climate-risk monitoring, pre-position recovery planning, and update disruption log. | Operations / Engineering / Safety | Number of service suspensions; days lost; estimated revenue impact; restoration time. | Monthly / Event-based | Add disruption log and restoration time to monthly reporting. | Open |  | Red
R7 | Revenue performance may remain below target if operating constraints are not addressed. | Finance / Commercial | Freight and passenger volumes remain weak; service interruptions persist; commercial utilization underperforms. | Cash pressure, constrained maintenance, slower project support, and a wider performance gap against plan. | High | Link financial review more directly to service performance, protect key revenue streams, and monitor recovery actions monthly. | Finance / Commercial / Management | Revenue collected versus target; traffic volumes; service availability. | Monthly | Present revenue recovery actions together with operational performance in one management review. | Open |  | Red
R8 | Delayed development fund disbursement may slow implementation of planned projects. | Development Finance | Funds received remain below plan; project sequencing slips; payment timing becomes uncertain. | Delayed project delivery, rescheduled works, contractor claims or penalties, and weak budget absorption. | Medium-High | Strengthen follow-up with the Ministry, improve cash forecasting, and prioritize works based on confirmed funding. | DCPI / Finance | Funds received vs planned; delayed activities; commitments versus cash availability. | Monthly | Maintain a monthly disbursement variance note for all major projects. | Open |  | Amber
R9 | Low implementation of the Annual Procurement Plan is affecting delivery of goods, works, and services. | Procurement / Delivery | High gap between planned tenders, initiated tenders, and signed contracts; prolonged processing times. | Delayed maintenance, delayed project execution, weakened service reliability, and underutilized budget. | High | Start procurement planning earlier, improve coordination with user departments, and strengthen procurement monitoring and capacity. | DPMU | APP implementation rate; number initiated; number signed; average procurement cycle time. | Monthly | Escalate all high-value delayed procurements in monthly management meetings. | Open |  | Red
R10 | Data quality and reporting completeness may weaken management confidence in the M&E system. | Institutional M&E | Missing actuals, inconsistent baselines, unclear sources, narrative and table mismatch, and late submissions. | Weak decision-making, disputed figures, poor comparability over time, and reduced credibility of reports. | Medium-High | Apply validation rules before report issuance, assign data owners, disclose not-reported KPIs, and maintain one official workbook. | M&E Unit / All Directorates | Reporting completeness; number of data gaps; number of corrected submissions. | Monthly | Introduce a pre-issuance validation checklist for every reporting cycle. | Open |  | Amber
R11 | Too many KPIs at the same reporting level may dilute management attention. | Performance Management | Dashboard and reports carry too many indicators without prioritization; key issues get buried. | Management focus drifts, critical problems are not escalated quickly enough, and reporting becomes heavy but less useful. | Medium | Use KPI tiers consistently: Critical, Core Operational, Supporting. Keep dashboard focus on headline issues only. | M&E Unit | Number of critical KPIs on dashboard; number of supporting KPIs pushed to annexes. | Quarterly | Review KPI tiers quarterly and retire weak or duplicate indicators. | Open |  | Amber
R12 | Remaining M&E framework and strategy work may stall if not aligned quickly to the next strategic plan cycle. | Institutional Planning | Core M&E documents remain incomplete; strategic plan transition delays final alignment. | M&E institutionalization slows down, the reporting system stays fragmented, and learning and evaluation remain weak. | Medium | Finalize the framework and strategy immediately after strategic plan confirmation and maintain interim discipline meanwhile. | M&E Unit / Management | Completion status of core M&E documents; adoption status. | Monthly / Quarterly | Prepare a finalization timetable with named responsibilities. | Open |  | Amber

## Risk Summary
Risk Summary | Risk Summary | Risk Summary | Risk Summary | Risk Summary | Risk Summary
Management snapshot of the live risk register for monthly review and escalation. | Management snapshot of the live risk register for monthly review and escalation. | Management snapshot of the live risk register for monthly review and escalation. | Management snapshot of the live risk register for monthly review and escalation. | Management snapshot of the live risk register for monthly review and escalation. | Management snapshot of the live risk register for monthly review and escalation.
Rating / Level | Meaning | Count | Default Use | Suggested Review | Comment
High | Immediate management attention required | 7 | Escalate in monthly management review | Monthly / urgent | Keep on red list until controls take effect.
Medium-High | Serious risk with active mitigation needed | 3 | Track closely in management meetings | Monthly | Should not be left without named next steps.
Medium | Important risk but not yet critical | 2 | Monitor and follow up | Monthly / quarterly | Review trend and avoid drift into red status.
Immediate Advice
1 | Update this register at least once every month, and after any major incident.
2 | Record evidence when a risk is downgraded from High to Medium-High or Medium.
3 | Use the register together with the dashboard, monthly report, and management action tracker.
4 | Escalate red risks without waiting for the next mid-year or annual report.
5 | Carry unresolved risks forward into the next monthly review meeting.

## How to Use
How to Use the Live Risk Register | How to Use the Live Risk Register | How to Use the Live Risk Register | How to Use the Live Risk Register | How to Use the Live Risk Register | How to Use the Live Risk Register
This sheet explains how the risk register should be maintained and used in the TRC M&E system. | This sheet explains how the risk register should be maintained and used in the TRC M&E system. | This sheet explains how the risk register should be maintained and used in the TRC M&E system. | This sheet explains how the risk register should be maintained and used in the TRC M&E system. | This sheet explains how the risk register should be maintained and used in the TRC M&E system. | This sheet explains how the risk register should be maintained and used in the TRC M&E system.
1 | Use the register as a live document, not as a year-end narrative attachment.
2 | Update Status, Last Updated, Current Rating, and Immediate Next Step during each reporting cycle.
3 | Link each high or medium-high risk to the monthly report and management action tracker.
4 | Use Monitoring Indicator to confirm whether mitigation is working over time.
5 | Where the same risk stays high for more than one cycle, request a more direct action plan.
6 | Keep one official version of this register and avoid parallel unmanaged copies.
7 | Review this register alongside the monitoring workbook and dashboard every month.