## 00 Instructions
TRC FY2025/26 Monitoring, Evaluation and Reporting Workbook | TRC FY2025/26 Monitoring, Evaluation and Reporting Workbook | TRC FY2025/26 Monitoring, Evaluation and Reporting Workbook | TRC FY2025/26 Monitoring, Evaluation and Reporting Workbook | TRC FY2025/26 Monitoring, Evaluation and Reporting Workbook | TRC FY2025/26 Monitoring, Evaluation and Reporting Workbook
Final presentation version prepared to support monthly monitoring, KPI oversight, management review, and evaluation planning. | Final presentation version prepared to support monthly monitoring, KPI oversight, management review, and evaluation planning. | Final presentation version prepared to support monthly monitoring, KPI oversight, management review, and evaluation planning. | Final presentation version prepared to support monthly monitoring, KPI oversight, management review, and evaluation planning. | Final presentation version prepared to support monthly monitoring, KPI oversight, management review, and evaluation planning. | Final presentation version prepared to support monthly monitoring, KPI oversight, management review, and evaluation planning.
1 | Use 01 Dashboard for executive review, monthly status summary, and management attention areas. |  |  | Workbook purpose | Provide one controlled workbook for FY2025/26 monitoring, reporting, and management follow-up.
2 | Update monthly actual values only in 02 Corporate M&E Matrix and allow formulas to update the summary view. |  |  | Primary users | TRC Management, M&E Unit, Directorate Heads, and reporting focal persons.
3 | Change the reporting month from 01 Dashboard cell B4 only; the workbook is designed to mirror that selection. |  |  | Main data-entry sheet | 02 Corporate M&E Matrix
4 | Use the KPI Tier fields to distinguish Critical, Core Operational, and Supporting indicators for reporting. |  |  | Executive summary sheet | 01 Dashboard
5 | Use 03 Activity Input Register and 04 Evaluation Workplan for operational follow-up and evaluation tracking. |  |  | Headline KPI logic | Critical KPIs for dashboard use; Core Operational KPIs for the main report; Supporting KPIs for annexes.
6 | Use 07 Jan2026 Import Log as a supporting audit trail for January data already loaded into the workbook. |  |  | Presentation note | This workbook is structured for management presentation and routine monthly updating.

## 01 Dashboard
FY2025/26 TRC Monitoring Dashboard | FY2025/26 TRC Monitoring Dashboard | FY2025/26 TRC Monitoring Dashboard | FY2025/26 TRC Monitoring Dashboard | FY2025/26 TRC Monitoring Dashboard | FY2025/26 TRC Monitoring Dashboard | FY2025/26 TRC Monitoring Dashboard | FY2025/26 TRC Monitoring Dashboard | FY2025/26 TRC Monitoring Dashboard | FY2025/26 TRC Monitoring Dashboard
Presentation-ready management summary showing KPI status, reporting completeness, and high-risk attention areas. | Presentation-ready management summary showing KPI status, reporting completeness, and high-risk attention areas. | Presentation-ready management summary showing KPI status, reporting completeness, and high-risk attention areas. | Presentation-ready management summary showing KPI status, reporting completeness, and high-risk attention areas. | Presentation-ready management summary showing KPI status, reporting completeness, and high-risk attention areas. | Presentation-ready management summary showing KPI status, reporting completeness, and high-risk attention areas. | Presentation-ready management summary showing KPI status, reporting completeness, and high-risk attention areas. | Presentation-ready management summary showing KPI status, reporting completeness, and high-risk attention areas. | Presentation-ready management summary showing KPI status, reporting completeness, and high-risk attention areas. | Presentation-ready management summary showing KPI status, reporting completeness, and high-risk attention areas.
MASTER Report Month # | 7 |  | Selected Month Name | Jan | Change B4 only. The dashboard and matrix report month mirror this master selector. | Change B4 only. The dashboard and matrix report month mirror this master selector. | Change B4 only. The dashboard and matrix report month mirror this master selector. | Change B4 only. The dashboard and matrix report month mirror this master selector. | Change B4 only. The dashboard and matrix report month mirror this master selector.
Compact Management Summary
🔴 On Track |  |  | 🔴 Off Track |  |  | 🔴 Not Reported |  |  | 🔴 High Risk
56 |  |  | 35 |  |  | 0 |  |  | 8
Indicators meeting or exceeding target |  |  | Indicators below plan and needing action |  |  | Indicators without actual data for selected month |  |  | Indicators flagged as high risk
Traffic Light Summary
● | On Track | ● | Not Reported | ● | Off Track | ● | High Risk
| 56 |  | 0 |  | 35 |  | 8
Management Area | Summary | Current Count / Signal | Interpretation
Reporting coverage | Indicators with actual data reported this month | 91 | Higher value means stronger reporting discipline
Performance concern | Indicators currently below target | 35 | Priority list for management follow-up
Data gap | Indicators not yet reported | 0 | Requires immediate data follow-up from responsible units
Risk exposure | Indicators marked high risk | 8 | Should be reviewed in management meeting
Priority Management Attention
Priority Type | Suggested Focus | Why It Matters | Immediate Action
Off Track | Review indicators below target and confirm root causes | Supports quick corrective action by management | Discuss in monthly review and assign action owners
Not Reported | Follow up directorates with missing January actuals | Improves completeness of the monitoring system | Set reporting deadline and data owner
High Risk | Escalate indicators flagged as high risk | Prevents unmanaged slippage or compliance issues | Update risk register and mitigation action
Qualitative Updates | Review narrative indicators for clearer status coding | Avoids under-reporting of completed process milestones | Standardize comments and proof of completion
Dashboard Use Notes
• This dashboard derives month-based counts directly from the selected month in cell B4.
• Only indicators with actual values entered in the corresponding 'Actual' month column are counted as reported.
• If data exists only for January, selecting other months will show high 'Not Reported' counts until those months are updated.
• High-risk counts come from the Risk Level column in the Corporate M&E Matrix.
KPI Rationalization
Critical KPIs should drive the executive dashboard; Core Operational KPIs should appear in the main monthly report body; Supporting KPIs should remain in annexes or departmental trackers for follow-up.
Official KPI Reference | Official KPI Reference | Official KPI Reference | Official KPI Reference | Official KPI Reference | Official KPI Reference | Official KPI Reference | Official KPI Reference | Official KPI Reference | Official KPI Reference
Use sheet 09 Master KPI Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting.
Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting. | Use sheet 09_Master_KPI_Register as the official cleaned KPI reference for the monitoring plan, dashboard prioritization, and monthly reporting.
[10 empty] | Critical KPI Status | Count
[10 empty] | On Track | 4
[10 empty] | Off Track | 8
[10 empty] | Not Reported | 0
[10 empty] | High Risk | 0
[10 empty] | Helper | Value
[10 empty] | Total Indicators | 91
[10 empty] | On Track | 56
[10 empty] | Off Track | 35
[10 empty] | Not Reported | 0
[10 empty] | Complete/Manual | 10
[10 empty] | High Risk | 8
[10 empty] | Medium Risk | 17
[10 empty] | Low Risk | 1

## 02 Corporate M&E Matrix
Corporate Monitoring & Evaluation Matrix
Appendix 1 converted to the main corporate M&E matrix with full indicator metadata and monthly target/actual tracking
[14 empty] | Selected Month # (mirror of Dashboard B4) | 7 | Report Month column is controlled centrally from Dashboard B4 |  |  |  |  | To change month, go to Dashboard tab and edit cell B4
Objective | Target Description | Output / Lower-Level Result | Indicator | Indicator Type | Baseline Year | Baseline Value | FY Target | Unit / Measure | Data Source | Means of Verification | Responsible Unit | Data Owner | Reporting Frequency | Report Month | Plan Jul | Plan Aug | Plan Sep | Plan Oct | Plan Nov | Plan Dec | Plan Jan | Plan Feb | Plan Mar | Plan Apr | Plan May | Plan Jun | Actual Jul | Actual Aug | Actual Sep | Actual Oct | Actual Nov | Actual Dec | Actual Jan | Actual Feb | Actual Mar | Actual Apr | Actual May | Actual Jun | YTD Plan | YTD Actual | Variance | Status | Risk Level | Assumptions / Comments | KPI ID | KPI Tier | Dashboard Inclusion | Reporting Placement | Tier Rationale
RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | Speed restrictions reduced from 63 km to 10km ( DSM-DOM, DOM-TBR, RUVU JNCT-TANGA PORT) by June, 2026 | Increase operation efficiency | No. of km speed restriction reduced | Output | 2024/2025 | 0 | 15 | Km | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | 10km |  |  | 15km | 15 |  | 15km |  |  | 13km | 151 | 151 | 151 | 151 | 151 | 151 | 15.5 | 151 | 151 | 151 | 151 | 151 | 15 | 15.5 | 0.5 | On Track | Medium | Source note: Speed restriction was reduced within 15.5km ¦ Deviation in source: 5.5km | KPI-001 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 50% of speed along MGR alignment upgraded by June, 2026 | Increase operation efficiency | % of curves/gradient realigned/relocated | Outcome / Efficiency | 2024/2025 | 0 | 0.1 | Percent | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | 0.1 |  |  | 0.2 | 10 |  | 0.1 |  |  | 0.1 | 151 | 151 | 151 | 151 | 151 | 151 | 0.6 | 151 | 151 | 151 | 151 | 151 | 10.3 | 0.6 | -9.7 | Off Track | Low | Source note: 0.5km was realigned/relocated ¦ Deviation in source: -0.94 | KPI-002 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 50% of speed along MGR alignment upgraded by June, 2026 | Increase operation efficiency | No. of rail km joined | Output | 2024/2025 | 0 |  | Km | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [6 empty] | 10 | [5 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 1.6 | 151 | 151 | 151 | 151 | 151 | 10 | 1.6 | -8.4 | Off Track | 151 | Source note: 1.6 km joined ¦ Deviation in source: -8.4 | KPI-003 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 50% of speed along MGR alignment upgraded by June, 2026 | Increase operation efficiency | No of km relayed | Output | 2024/2025 | 0 |  | Km | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [6 empty] | 10 | [5 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 1.7 | 151 | 151 | 151 | 151 | 151 | 10 | 1.7 | -8.3 | Off Track | 151 | Source note: 1.7 km relayed ¦ Deviation in source: -8.3 | KPI-004 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 80 km of railway line ballasted ( Kidomole-Tanga port, Godegode section, Gulwe diversion) by June, 2026 | Increase operation efficiency | No. of km ballasted | Output | 2024/2025 | 0 | 24 | Km | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | 6km | 10km | 10km |  | 10 |  |  | 15km | 15km | 24km | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 151 | 151 | 151 | 151 | 151 | 10 | 0 | -10 | Off Track | 151 | Source note: 0 | KPI-005 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | Establishment of llala-SGR siding by June, 2026 | Increase operation efficiency | No. of sidings established | Output | 2024/2025 | 0 | Ilala siding completed | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  |  | Ilala siding completed | [8 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | Complete | 151 | Jan actual narrative: The work completed ¦ Source note: The work completed | KPI-006 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 100 km of railway line (Kaliua-Mpanda , Godegode section & Tanga port) rehabilitated by June, 2026 | Increase operation efficiency | No. of Km of railway line rehabilitated | Output | 2024/2025 | 0 | 10 | Km | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | 10km | 10km | 10km | 10km | 10km | 10km | 10km | 10km | 10km | 10km | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | On Track | 151 | Source note: None ¦ Deviation in source: -10 | KPI-007 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 100% of 25 operational buildings rehabilitated by June, 2026 | Increase operation efficiency | % of works completed | Outcome / Efficiency | 2024/2025 | 0 | 1 | Percent | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | 0.1 |  |  | 0.4 | 0.23 |  | 0.7 |  |  | 1 | 151 | 151 | 151 | 151 | 151 | 151 | 0.1 | 151 | 151 | 151 | 151 | 151 | 0.73 | 0.1 | -0.63 | Off Track | 151 | Source note: 0.1 ¦ Deviation in source: =F12-E12 | KPI-008 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 722km of SGR railway line maintained by June, 2026 | Increase operation efficiency | No. of km of speed restriction | Output | 2024/2025 | 0 | 722 | Km | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 722km | 722km | 722km | 722km | 722km | 722km | 722km | 722km | 722km | 722km | 722km | 722km | 151 | 151 | 151 | 151 | 151 | 151 | 98 | 151 | 151 | 151 | 151 | 151 | 0 | 98 | 98 | On Track | 151 | Source note: 98.0km of SGR were maintained ¦ Deviation in source: (624.0km) | KPI-009 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 80% of 45 locomotives available by June, 2026 | Increase operation efficiency | No. of Locomotives available for operations | Output | 2024/2025 | 18 | 36 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 151 | 151 | 151 | 151 | 151 | 151 | 18 | 151 | 151 | 151 | 151 | 151 | 252 | 18 | -234 | Off Track | 151 | Source note: A total of 18 locomotives were available equals to 50% of target ¦ Deviation in source: -18 | KPI-010 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 95% of locomotive realibility ensured by June, 2026 | Increase operation efficiency | Mean Kilometers Before Failure | To confirm | 2024/2025 | 8000 | 19000 | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 8000 | 10000 | 10000 | 12000 | 14000 | 15000 | 17000 | 18000 | 18000 | 19000 | 19000 | 19000 | 151 | 151 | 151 | 151 | 151 | 151 | 6960 | 151 | 151 | 151 | 151 | 151 | 86000 | 6960 | -79040 | Off Track | 151 | Source note: Locomotives were travelled 6,960 km before failure compared to the target of 17,000km/failure (40.94%) ¦ Deviation in source: -5040 | KPI-011 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 80% of 83 MGR coaches available by June, 2026 | Increase operation efficiency | No. of coaches available | Output | 2024/2025 | 64 | 83 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 66 | 66 | 69 | 69 | 72 | 72 | 75 | 75 | 77 | 80 | 80 | 83 | 151 | 151 | 151 | 151 | 151 | 151 | 97 | 151 | 151 | 151 | 151 | 151 | 489 | 97 | -392 | Off Track | 151 | Source note: A total of 97 coaches were available agaist a target of 87 coaches.The target was attained by 111.49 percent ¦ Deviation in source: 10 | KPI-012 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 80% of 883 MGR wagons available by June, 2026 | Increase operation efficiency | % of wagons available | Outcome / Efficiency | 2024/2025 | 640 | 1046 | Percent | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 706 | 726 | 746 | 766 | 786 | 826 | 846 | 886 | 926 | 966 | 1006 | 1046 | 151 | 151 | 151 | 151 | 151 | 151 | 870 | 151 | 151 | 151 | 151 | 151 | 5402 | 870 | -4532 | Off Track | 151 | Source note: A total of 870 wagons wa available against a target of 846 coaches.The target was attained by 102.83 percent ¦ Deviation in source: 46 | KPI-013 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 180 MGR wagons rehabilitated and roll out for operation by June, 2026 | Increase operation efficiency | No. of wagons roll out for operation | Output | 2024/2025 | 15 | 20 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 151 | 151 | 151 | 151 | 151 | 80 | 0 | -80 | Off Track | 151 | Source note: wagons were not rehabilited ¦ Deviation in source: 0 | KPI-014 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 50 MGR wagons to be delivered by June, 2026 | Increase operation efficiency | No. of wagons delivered | Output | 2024/2025 | 50 | 50 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 151 | 151 | 151 | 151 | 151 | 50 | 151 | 151 | 151 | 151 | 151 | 50 | 50 | 0 | On Track | 151 | Source note: MGR wagons delivered, now under operations ¦ Deviation in source: 0 | KPI-015 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 8 new MGR locomotives to be delivered by June, 2026 | Increase operation efficiency | No. of Locomotive | Output | 2024/2025 | 0 | 4 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 0 | 0 | 0 | 2 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 151 | 151 | 151 | 151 | 151 | 2 | 151 | 151 | 151 | 151 | 151 | 8 | 2 | -6 | Off Track | 151 | Source note: MGR locomotives have been delivered and are under Operations. ¦ Deviation in source: 0 | KPI-016 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | 2024/25 Corporation unqualified opinion secured by June, 2026 | Increase operation efficiency | Unqualified opinion | To confirm | 2024/2025 | Unqualified opinion | Report | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [8 empty] | Report |  |  |  | 151 | 151 | 151 | 151 | 151 | 151 | 2024 | 151 | 151 | 151 | 151 | 151 | 0 | 2024 | 2024 | On Track | Medium | Source note: The audit for the finacial year 2024/25 completed and report submitted to the office of controller and Auditor General for review. | KPI-017 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | 2024/25 Corporation unqualified opinion secured by June, 2026 | Increase operation efficiency | Advisory Audit consultant in place | To confirm | 2024/2025 | Unqualified opinion |  | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [12 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | Complete | 151 | Jan actual narrative: Tax Audit consultant is in place ¦ Source note: Tax Audit consultant is in place | KPI-018 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | Quarterly financial management report prepared by June, 2026 | Increase cost management efficiency | Financial Management Report | To confirm | 2024/2025 | Unqualified opinion | 1 | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 2 | 0 | -2 | Complete | Medium | Jan actual narrative: Second quarter finanacial management report were prepared ¦ Source note: Preparation of second quarter finanacial management report is ongoing | KPI-019 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | Audited Financial report prepared and published annually by June, 2026 | Increase cost management efficiency | Financial Management Report | To confirm | 2024/2025 | NA |  | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [12 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 2024 | 151 | 151 | 151 | 151 | 151 | 0 | 2024 | 2024 | On Track | 151 | Source note: Financial statement for the Financial year 2024/25 prepared and submitted to the office of Controller and Auditor General | KPI-020 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | 70% of Tshs.8,455,960,658.12 debt collected by June, 2026 | Increase revenue collection | Tshs. Collected | Financial | 2024/2025 | NA | 493264371.72 | TZS | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 493264371.72 | 493264371.72 | 493264371.72 | 493264371.72 | 493264371.72 | 493264371.72 | 493264371.72 | 493264371.72 | 493264371.72 | 493264371.72 | 493264371.72 | 493264371.72 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 151 | 151 | 151 | 151 | 151 | 3452850602.04 | 0 | -3452850602.04 | Off Track | 151 | 151 | KPI-021 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | 50% of Tshs.19,414,385,689 service provider outstanding debt settled by June, 2026 | Increase operation efficiency | Tshs. Settled | Financial | 2024/2025 | NA | 808932737.04 | TZS | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 808932737.04 | 808932737.04 | 808932737.04 | 808932737.04 | 808932737.04 | 808932737.04 | 808932737.04 | 808932737.04 | 808932737.04 | 808932737.04 | 808932737.04 | 808932737.04 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 5662529159.28 | 0 | -5662529159.28 | Off Track | 151 | 151 | KPI-022 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | Tshs. 265,372,951,248 of internal revenue collected by June, 2026 | 304601604627.7 | Tshs. Collected | Financial | 2024/2025 | 145515892703.76 | 24068445412.9703 | TZS | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 22277061299.8144 | 22325932904.7845 | 21794540024.4247 | 21252900080.2036 | 22608309187.7453 | 24068445412.9703 | 23273013346.7027 | 20735153600.0625 | 20155968752.5573 | 22364150570.6636 | 21376023516.1322 | 23141452551.939 | 151 | 151 | 151 | 151 | 151 | 151 | 11131111301.09 | 151 | 151 | 151 | 151 | 151 | 157600202256.6454 | 11131111301.09 | -146469090955.5554 | Off Track | 151 | Source note: A total of 11,131,111,301.09 was collected equals to 47.83 percent of the target. | KPI-023 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | Monthly Corporation audited report prepared by June, 2026 | Increase operation efficiency | Report | To confirm | 2024/2025 | NA | IT Systems Audit (MGR & SGR) | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | Follow-up on Implementation of Auditors' Findings and Recommendations | Expenditure Management Audit – SGR Operation | Safety and Risk Management Audit (MGR & SGR) | Procurement Process and Contract Management Audit | Real Estate Management Audit (MGR & SGR) | Follow-up on Implementation of Auditors' Recommendations | Procurement Process and Contract Management Audit, | Fuel and Lubricants Audit (MGR & SGR) | Follow-up on Implementation of Auditors' Recommendations | Procurement Process and Contract Management | Follow-up on Implementation of Auditors' Recommendations | IT Systems Audit (MGR & SGR) | 151 | 151 | 151 | 151 | 151 | 151 | 100 | 151 | 151 | 151 | 151 | 151 | 0 | 100 | 100 | On Track | Medium | Source note: The Draft Audit Report has been prepared and submitted to auditee for Management Response | KPI-024 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 810,000 metric tons (MGR) to be transported by June, 2026 | 810,000 metric tons transported | No. Metric tons transported | Output | 2024/2025 | 246824 | 79766.9671 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 65651.2353 | 69788.1797 | 61140.6578 | 69397.537 | 75514.5615 | 72826.3297 | 79766.9671 | 47957.0016 | 52173.9578 | 77615.6794 | 70690.0573 | 67477.836 | 151 | 151 | 151 | 151 | 151 | 151 | 15451 | 151 | 151 | 151 | 151 | 151 | 494085.4679 | 15451 | -478634.4679 | Off Track | 151 | Source note: 15,451 tonnes for MGR were hauled equals to 19.37 percent of the planned target ¦ Deviation in source: =F33-E33 | KPI-025 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 710,889,286 ton-km (MGR) to be covered by June, 2026 | Increase operational efficiency | Ton-km | Output | 2024/2025 | 265101245 | 76499308.5802 | Km | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 56888300.248 | 61344764.7874 | 53351231.914 | 62657969.7326 | 71909003.2487 | 69983455.0859 | 76499308.5802 | 42058895.6293 | 40809363.1214 | 63388911.3719 | 55714212.68 | 56283870.0542 | 151 | 151 | 151 | 151 | 151 | 151 | 2517291 | 151 | 151 | 151 | 151 | 151 | 452634033.5969 | 2517291 | -450116742.5969 | Off Track | 151 | Source note: 2,517,291 ton per km was attained ¦ Deviation in source: =F34-E34 | KPI-026 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 500,000 metric tons (SGR) to be transported by June, 2026 | 500,000 metrics tons transported | No. Metric tons transported | Output | 2024/2025 | 0 | 41666.6667 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 151 | 151 | 151 | 151 | 151 | 151 | 8625 | 151 | 151 | 151 | 151 | 151 | 291666.6667 | 8625 | -283041.6667 | Off Track | 151 | Source note: 8,625 tonnes for SGR were hauled equals to 20.70 percent of the planned target ¦ Deviation in source: =F35-E35 | KPI-027 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 224,500,000 ton-km (SGR) to be covered by June, 2026 | Increase operational efficiency | Ton-km | Output | 2024/2025 | 0 | 224500000 | Km | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 18708333.3333 | 18708333.3333 | 18708333.3333 | 18708333.3333 | 18708333.3333 | 18708333.3333 | 18708333.3333 | 18708333.3333 | 18708333.3333 | 18708333.3333 | 18708333.3333 | 18708333.3333 | 151 | 151 | 151 | 151 | 151 | 151 | 991875 | 151 | 151 | 151 | 151 | 151 | 130958333.3333 | 991875 | -129966458.3333 | Off Track | 151 | Source note: 991,875 ton per km was attained ¦ Deviation in source: =F36-E36 | KPI-028 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 552,038 Mainline Passengers (MGR) to be transported by June, 2026. | 552,038 mainline passengers transported | No. of passengers transported | Output | 2024/2025 | 504634 | 63473.7068 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 51078.8195 | 63473.7068 | 55445.8333 | 52109.3854 | 43346.2122 | 45002.8397 | 38829.4724 | 32787.9726 | 37665.0841 | 34943.7972 | 42599.6254 | 54755.3288 | 151 | 151 | 151 | 151 | 151 | 151 | 18341 | 151 | 151 | 151 | 151 | 151 | 349286.2693 | 18341 | -330945.2693 | Off Track | 151 | Source note: 18,341 Mainline Passengers for MGR were transported equals to 47.23 percent of the planned target. ¦ Deviation in source: =F37-E37 | KPI-029 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 406,873,140 pax-km (MGR) to be covered by June, 20226 | Increase operational efficiency | Pax-km | Output | 2024/2025 | 372688787 | 45856211.1756 | Km | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 37418334.8796 | 45856211.1756 | 40820554.7978 | 37839483.8109 | 31770667.8212 | 32566083.2204 | 27411464.0066 | 24545657.8997 | 28344633.531 | 26125692.2003 | 31918368.3437 | 42255988.732 | 151 | 151 | 151 | 151 | 151 | 151 | 8542160 | 151 | 151 | 151 | 151 | 151 | 253682799.7121 | 8542160 | -245140639.7121 | Off Track | 151 | Source note: 8,542,160 passenger per km were attained ¦ Deviation in source: =F38-E38 | KPI-030 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 3,046,320 Mainline Passengers (SGR) to be transported by June, 2026. | 3,046,320 SGR passengers transported | No. of passengers transported | Output | 2024/2025 | 2997792 | 281559.7776 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 249999.86 | 247563.3997 | 251347.5322 | 245804.4798 | 246261.3449 | 276740.0482 | 241780.404 | 235277.2668 | 250180.7958 | 260759.4768 | 259045.4058 | 281559.7776 | 151 | 151 | 151 | 151 | 151 | 151 | 271642 | 151 | 151 | 151 | 151 | 151 | 1759497.0688 | 271642 | -1487855.0688 | Off Track | 151 | Source note: 271,642 Mainline Passengers for SGR were transported equals to 112.35 percent of the planned target. ¦ Deviation in source: =F39-E39 | KPI-031 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 940,380,365 pax-km (SGR) to be covered by June, 20226 | Increase operational efficiency | Pax-km | Output | 2024/2025 | 2997792 | 87518313.9797 | Km | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 75181658.3713 | 76910506.7187 | 78003442.2116 | 76099686.9969 | 76218645.9142 | 85834614.144 | 74554077.5276 | 72380101.3903 | 77068094.6256 | 80669953.577 | 79941269.6263 | 87518313.9797 | 151 | 151 | 151 | 151 | 151 | 151 | 82935299 | 151 | 151 | 151 | 151 | 151 | 542802631.8844 | 82935299 | -459867332.8844 | Off Track | 151 | Source note: 82,935,299 passenger per km were attained ¦ Deviation in source: =F40-E40 | KPI-032 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 3,067,200 commuter passengers to be transported by June, 2026. | 3,067,200 commuter passengers transported | No. of passengers transported | Output | 2024/2025 | 2494659 | 306684.1031 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 283955.135 | 215807.969 | 301960.5469 | 276528.0516 | 270075.8805 | 186078.4416 | 274402.0539 | 287130.2231 | 306684.1031 | 208644.4828 | 261190.4025 | 194742.71 | 151 | 151 | 151 | 151 | 151 | 151 | 110759 | 151 | 151 | 151 | 151 | 151 | 1808808.0786 | 110759 | -1698049.0786 | Off Track | 151 | Source note: 110,759 Commuter Passengers were transported equals to 40.36 percent of the planned target. ¦ Deviation in source: =F41-E41 | KPI-033 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 58 Surveyed plots demarcated by June, 2026 | Increase operational efficiency | No. of plots demarcated | Output | 2024/2025 | 0 | 16 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | 12 |  |  | 14 |  |  | 16 |  |  | 16 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 26 | 0 | -26 | Off Track | Medium | Jan actual narrative: Demarcation was not done ¦ Source note: Demarcation was not done | KPI-034 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Tshs. 3,607,911,882 revenue to be collected from leased tenants by June, 2026 | Increase revenue collection | Tshs. Collected | Financial | 2024/2025 | 2833908850.73 | 386.34 | TZS | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 386.34mil | 291.34mil | 316.34mil | 276.34mil | 311.34mil | 281.34mil | 266.13mil | 285.34mil | 288.34mil | 296.34mil | 292.34mil | 316.34mil | 151 | 151 | 151 | 151 | 151 | 151 | 288822345 | 151 | 151 | 151 | 151 | 151 | 0 | 288822345 | 288822345 | On Track | 151 | Source note: A total of 288,822,345 were collected from leased tenants ¦ Deviation in source: 22.69 mil | KPI-035 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 95% commercial area to be leased for SGR stations by June, 2026 | Increase revenue collection | % commercial space leased at DSM station | Outcome / Efficiency | 2024/2025 | 0.79 | 0.89 | Percent | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | 0.81 |  |  | 0.84 | 0.84 |  | 0.86 |  |  | 0.89 | 151 | 151 | 151 | 151 | 151 | 151 | 0.84 | 151 | 151 | 151 | 151 | 151 | 2.49 | 0.84 | -1.65 | Off Track | 151 | Source note: 84 percent of commercial space leased at DSM station ¦ Deviation in source: 0 | KPI-036 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 95% commercial area to be leased for SGR stations by June, 2026 | Increase revenue collection | % commercial space leased at Morogoro station | Outcome / Efficiency | 2024/2025 | 0.66 | 0.9 | Percent | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | 0.82 |  |  | 0.87 | 0.87 |  | 0.9 |  |  | 0.9 | 151 | 151 | 151 | 151 | 151 | 151 | 0.95 | 151 | 151 | 151 | 151 | 151 | 2.56 | 0.95 | -1.61 | Off Track | 151 | Source note: 95 percent of commercial space leased at Morogoro station ¦ Deviation in source: 0.07999999999999996 | KPI-037 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 95% commercial area to be leased for SGR stations by June, 2026 | Increase revenue collection | % commercial space leased at Kilosa station | Outcome / Efficiency | 2024/2025 | 0.31 | 0.63 | Percent | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | 0.63 |  |  | 0.63 | 0.63 |  | 0.63 |  |  | 0.63 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 151 | 151 | 151 | 151 | 151 | 1.89 | 0 | -1.89 | Off Track | Medium | Source note: The commercial space at at Kilosa station was not leased during the period under review ¦ Deviation in source: -0.63 | KPI-038 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 95% commercial area to be leased for SGR stations by June, 2026 | Increase revenue collection | % commercial space leased at Dodoma station | Outcome / Efficiency | 2024/2025 | 0.67 | 0.87 | Percent | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | 0.77 |  |  | 0.81 | 0.81 |  | 0.84 |  |  | 0.87 | 151 | 151 | 151 | 151 | 151 | 151 | 0.67 | 151 | 151 | 151 | 151 | 151 | 2.39 | 0.67 | -1.72 | Off Track | 151 | Source note: 67 percent of commercial space leased at Dodoma station ¦ Deviation in source: -0.14 | KPI-039 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 4 feasibility studies for Real Estate investment opportunities conducted and evaluate their potential risks and returns by June 2026. | Increase revenue collection | No. of feasibility studies conducted | Output | 2024/2025 | 0 | 4 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [11 empty] | 4 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | Off Track | Medium | Jan actual narrative: Procurement of a consultant to carry out feasibility study for six land parcel/plots is ongoing ¦ Source note: Procurement of a consultant to carry out feasibility study for six land parcel/plots is ongoing | KPI-040 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | To collect 1,898,000,000 parking revenue from parking fee by June, 2026 | Parking fee collected | Amount paid | To confirm | 2024/2025 | - | 158166667 | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 158166667 | 158166667 | 158166667 | 158166667 | 158166667 | 158166667 | 158166667 | 158166667 | 158166667 | 158166667 | 158166667 | 158166667 | 151 | 151 | 151 | 151 | 151 | 151 | 182435000 | 151 | 151 | 151 | 151 | 151 | 1107166669 | 182435000 | -924731669 | Off Track | 151 | Source note: A total of 182,435,000 were collected from parking equivalent to 115.34 percent of the target. ¦ Deviation in source: =F49-E49 | KPI-041 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Availability of Electrification, signaling and telecommunication services ensured by June, 2026 | Increase operational efficiency | No. of incidence/ faults recorded | Output | 2024/2025 | - | 0 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 151 | 151 | 151 | 151 | 151 | 12 | 151 | 151 | 151 | 151 | 151 | 0 | 12 | 12 | On Track | 151 | Source note: A total of 12 Signal failures, 3 point-machine failures and 1 derailer were detected with zero false occupation and wheel detector | KPI-042 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Availability of Electrification, signaling and telecommunication services ensured by June, 2026 | Increase operational efficiency | Incidence Recovery time | To confirm | 2024/2025 | - | 2 | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | ≤ 2hrs | ≤ 2hrs | ≤ 2hrs | ≤ 2hrs | ≤ 2hrs | ≤ 2hrs | ≤ 2hrs | ≤ 2hrs | ≤ 2hrs | ≤ 2hrs | ≤ 2hrs | ≤ 2hrs | 151 | 151 | 151 | 151 | 151 | 151 | 1 | 151 | 151 | 151 | 151 | 151 | 0 | 1 | 1 | On Track | 151 | Source note: The average failure time were 1: 49 | KPI-043 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Safety and security of railway infrastructure and operation ensured by June, 2026 | Increase operational efficiency | No. of incidence recorded (MGR) | Output | 2024/2025 | 0 | 0 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 151 | 151 | 151 | 151 | 151 | 12 | 151 | 151 | 151 | 151 | 151 | 0 | 12 | 12 | On Track | 151 | Source note: A total of (12) locomotive failure were recorded, against a planned target of zero (0). ¦ Deviation in source: 12 | KPI-044 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Safety and security of railway infrastructure and operation ensured by June, 2026 | Increase operational efficiency | No. of accident recorded(MGR) | Output | 2024/2025 | 0 | 0 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 151 | 151 | 151 | 151 | 151 | 4 | 151 | 151 | 151 | 151 | 151 | 0 | 4 | 4 | On Track | High | Source note: A total number of four (4) accidents (Derailments and capsizement) were recorded against zero (0) planned target ¦ Deviation in source: 4 | KPI-045 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Safety and security of railway infrastructure and operation ensured by June, 2026 | Increase operational efficiency | No. of trainings provided (MGR) | Output | 2024/2025 | 5 | 1 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 151 | 151 | 151 | 151 | 151 | 7 | 0 | -7 | Off Track | 151 | Source note: No training conducted against 1 planned target ¦ Deviation in source: 1 | KPI-046 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Safety and security of railway infrastructure and operation ensured by June, 2026 | Increase operational efficiency | No. of incidence recorded(SGR) | Output | 2024/2025 | 0 | 0 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 151 | 151 | 151 | 151 | 151 | 16 | 151 | 151 | 151 | 151 | 151 | 0 | 16 | 16 | On Track | 151 | Source note: A total number of 16 incidents were recorded which are ,false occupation,Coach deffective, power outage, dynamic instability of train and points machine failure. ¦ Deviation in source: 16 | KPI-047 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Safety and security of railway infrastructure and operation ensured by June, 2026 | Increase operational efficiency | No. of accident recorded (SGR) | Output | 2024/2025 | 0 | 0 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 151 | 151 | 151 | 151 | 151 | 4 | 151 | 151 | 151 | 151 | 151 | 0 | 4 | 4 | On Track | High | Source note: A total number 4 accidents were recorded which are washaway,pantograph broken, dead body (suspected knocked by train and train trailed the points ¦ Deviation in source: 4 | KPI-048 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Safety and security of railway infrastructure and operation ensured by June, 2026 | Increase operational efficiency | No. of trainings provided (SGR) | Output | 2024/2025 | 5 | 1 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 151 | 151 | 151 | 151 | 151 | 151 | 1 | 151 | 151 | 151 | 151 | 151 | 7 | 1 | -6 | Off Track | 151 | Source note: One (1) training sessions was conducted against a planned target of one (1) ¦ Deviation in source: 0 | KPI-049 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Punctuality on trains operation ensured by June, 2026 | Increase operational efficiency | Working timetable | To confirm | 2024/2025 | Adhered | Adhered | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | Adhered | Adhered | Adhered | Adhered | Adhered | Adhered | Adhered | Adhered | Adhered | Adhered | Adhered | Adhered | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | On Track | 151 | Jan actual narrative: Working timetable was nof fully adhered ¦ Source note: Working timetable was nof fully adhered | KPI-050 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Punctuality on trains operation ensured by June, 2026 | Increase operational efficiency | Wagon turnround time | To confirm | 2024/2025 | 19 | 14 | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 151 | 151 | 151 | 151 | 151 | 98 | 0 | -98 | Off Track | 151 | Source note: zero ¦ Deviation in source: 0 | KPI-051 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Transportation of 810,000 metric tons (MGR) ensured by June, 2026 | Revenue realized and increase operational efficiency | No. of block trains run | Output | 2024/2025 | 308.53 | 79766.9671 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 82.064 | 87.2352 | 76.4258 | 86.7469 | 94.3932 | 91.0329 | 99.7087 | 59.9463 | 65.2174 | 97.0196 | 88.3626 | 84.3473 | 151 | 151 | 151 | 151 | 151 | 151 | 7 | 151 | 151 | 151 | 151 | 151 | 617.6068 | 7 | -610.6068 | Off Track | 151 | Source note: 7 block trains for MGR were run ¦ Deviation in source: =F60-E60 | KPI-052 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Transportation of 500,000 metric tons (SGR) ensured by June, 2026 | Revenue realized and increase operational efficiency | No. of block trains run | Output | 2024/2025 | NA | 41666.6667 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 27.7778 | 27.7778 | 27.7778 | 27.7778 | 27.7778 | 27.7778 | 27.7778 | 27.7778 | 27.7778 | 27.7778 | 27.7778 | 27.7778 | 151 | 151 | 151 | 151 | 151 | 151 | 14 | 151 | 151 | 151 | 151 | 151 | 194.4444 | 14 | -180.4444 | Off Track | 151 | Source note: 14 block train for SGR were run ¦ Deviation in source: =F61-E61 | KPI-053 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 16 cases finalized by June, 2026 | Increase operational efficiency | No. of cases finalized | Output | 2024/2025 | 16 | 4 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 151 | 151 | 151 | 151 | 151 | 8 | 0 | -8 | Off Track | 151 | Source note: None | KPI-054 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Contract worth above TZS One Billion to be vetted within 21 days | Increase operational efficiency | No. of days | Output | 2024/2025 | 21 | 21 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 151 | 151 | 151 | 151 | 151 | 151 | 21 | 151 | 151 | 151 | 151 | 151 | 147 | 21 | -126 | Off Track | 151 | Source note: The contracts above TZS one billion were vetted within 21 days | KPI-055 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Agreements and/or Contract worth below TZS One Billion to be vetted within 7 days | Increase operational efficiency | No. of days | Output | 2024/2025 | 7 | 7 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 151 | 151 | 151 | 151 | 151 | 151 | 7 | 151 | 151 | 151 | 151 | 151 | 49 | 7 | -42 | Off Track | 151 | Source note: The contracts below TZS one billion were vetted within 21 days | KPI-056 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Agreements, Contract and MoU reviewed monthly by June, 2026 | Increase operational efficiency | No. of agreements/ Contracts/MoU reviewed | Output | 2024/2025 | 20 | 7 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 151 | 151 | 151 | 151 | 151 | 151 | 136 | 151 | 151 | 151 | 151 | 151 | 49 | 136 | 87 | On Track | 151 | Source note: 136 - employment contracts; 5 - MoUs vetted. | KPI-057 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | To coordinate quarterly Board Meeting by June, 2026 | Increase operational efficiency | No of meetings | Output | 2024/2025 | 4 | 4 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 151 | 151 | 151 | 151 | 151 | 8 | 0 | -8 | Off Track | Medium | Source note: Preparation for board meeting is ongoing | KPI-058 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Tshs. 1.857,082,670,000 mobilized for development projects by June 2026 | Increase operational efficiency | Tsh. collected | To confirm | 2024/2025 | 4 | 180.7 | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 170.9 bil | 180.7bil | 148.9bil | 157.7bil | 174.2bil | 143.7bil | 177.2bil | 152.9bil | 139.8bil | 139.9bil | 139.5bil | 137.6bil | 151 | 151 | 151 | 151 | 151 | 151 | 153.34 | 151 | 151 | 151 | 151 | 151 | 0 | 153.34 | 153.34 | On Track | 151 | Source note: A total of TZS 153.34 billion was received to support development projects against a planned target of TZS 177.2 billion, resulting in a shortfall of 13.47%. ¦ Deviation in source: 24 bil | KPI-059 | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | To brand corporation image by June, 2026 | Increase operational efficiency | Report | To confirm | 2024/2025 | NA | Brand visibility and identinty, brand communication, brand experience and activation and Internal branding | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | Brand visibility and identinty, brand communication, brand experience and activation and Internal branding | Brand visibility and identinty, brand communication, brand experience and activation and Internal branding | Brand visibility and identinty, brand communication, brand experience and activation and Internal branding | Brand visibility and identinty, brand communication, brand experience and activation and Internal branding | Brand visibility and identinty, brand communication, brand experience and activation and Internal branding | Brand visibility and identinty, brand communication, brand experience and activation and Internal branding | Brand visibility and identinty, brand communication, brand experience and activation and Internal branding | Brand visibility and identinty, brand communication, brand experience and activation and Internal branding | Brand visibility and identinty, brand communication, brand experience and activation and Internal branding | Brand visibility and identinty, brand communication, brand experience and activation and Internal branding | Brand visibility and identinty, brand communication, brand experience and activation and Internal branding | Brand visibility and identinty, brand communication, brand experience and activation and Internal branding | 151 | 151 | 151 | 151 | 151 | 151 | 30 | 151 | 151 | 151 | 151 | 151 | 0 | 30 | 30 | On Track | 151 | Source note: One media coverage were conducted and 30 social media contents were prepared | KPI-060 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 700 students enrolled by June, 2026 | Increase TIRTEC efficiency | No. of student enrolled | Output | 2024/2025 | 559 | 700 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  |  | 700 | [8 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 689 | 151 | 151 | 151 | 151 | 151 | 700 | 689 | -11 | Off Track | 151 | Source note: A total number of 689 students were enrolled eqauls to 98.43 percent of the target | KPI-061 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Refreshers course training provided to staff by June, 2026 | Increase staff efficiency | No of trainings | Output | 2024/2025 | 0 | 50 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  | Mechanical Department (50) | Civil Department (50) | Signaling, Telecom & Electrification (50) | Railway Traffic (50) |  |  | Business Department (50) |  |  |  | Human Resource and Administration Department (50) | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | On Track | Medium | Source note: The training was not conducted. | KPI-062 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 2 PPP feasibility study prepared by June, 2026 | Increase operational efficiency | No. of PPP F.S prepared | Output | 2024/2025 | NA | Mtwara and DSM commuter investor secured | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [11 empty] | Mtwara and DSM commuter investor secured | 151 | 151 | 151 | 151 | 151 | 151 | 1 | 151 | 151 | 151 | 151 | 151 | 0 | 1 | 1 | On Track | Medium | Source note: 1. Review of the feasibility study for Dar es salaam Commutter Railway through PPP is underway 2. Feasibility Study for Railway line linking the SGR with Airports is underway | KPI-063 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Two policies (Investment plan and Policy) reviewed by June, 2026 | Increase operational efficiency | No. of document reviewed | Output | 2024/2025 | NA | Review of policies (Investment Plan and policies) completed | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [5 empty] | Review of policies (Investment Plan and policies) completed | [6 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | Off Track | Medium | Jan actual narrative: Terms of Reference for engagement of the consultant to prepare the policies were reviewed. ¦ Source note: Terms of Reference for engagement of the consultant to prepare the policies were reviewed. | KPI-064 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Corporate Strategic Plan prepared by June, 2026 | Increase operational efficiency | Strategic plan Document | To confirm | 2024/2025 | NA | Strategic plan Document in place | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  | ToRs prepared |  | Consultant in place | [7 empty] | Strategic plan Document in place | 151 | 151 | 151 | 151 | 151 | 151 | 27 | 151 | 151 | 151 | 151 | 151 | 0 | 27 | 27 | On Track | Medium | Source note: The tender to procure consultant for preparation of Corporate Strategic Plan was opened on 27th November, 2026. The evaluation is ongoing | KPI-065 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Railway master plan prepared by June, 2026 | Increase operational efficiency | Railway master plan Document | To confirm | 2024/2025 | NA | Ongoing | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | ToRs prepared |  |  | Procurement completed | Procurement completed |  |  |  |  | Ongoing | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | On Track | 151 | Jan actual narrative: The preparation of the Terms of Reference (ToR) was finalised and it is in the final stages of tendering. ¦ Source note: The preparation of the Terms of Reference (ToR) was finalised and it is in the final stages of tendering. | KPI-066 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Business transformation strategy prepared and approved by June, 2026 | Increase operational efficiency | Business transformation strategy Document | To confirm | 2024/2025 | NA | Business Transformation Report in Place | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  |  | Business Transformation Report in Place | [8 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | Complete | Medium | Jan actual narrative: Review of draft business transformation strategy report completed, the inputs were incorporated and submitted to the Consultant.Currently awaiting for consultant presentation of the report. ¦ Source note: Management were received and discuss the draft business transformation strategy, the inputs were incorporated and submitted to the Consultant.Currently awaiting for consultant presentation of the report. | KPI-067 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 279 staffs recruited by June, 2026 | Increase staff capacity and efficiency | No. of staff recruited | Output | 2024/2025 | NA | 279 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279 | 0 | 0 | 0 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | Off Track | 151 | Jan actual narrative: Recruitment approval has been sought from the Permanent Secretary (Establishment ), Follow-ups are being made, however the recruitment permit has not been granted. ¦ Source note: Recruitment approval has been sought from the Permanent Secretary (Establishment ), Follow-ups are being made, however the recruitment permit has not been granted. | KPI-068 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 279 staff oriented and 432 staff vetted by June, 2026 | Increase staff efficiency | No. of staff oriented | Output | 2024/2025 | NA | 279 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279 | 0 | 0 | 0 | 151 | 151 | 151 | 151 | 151 | 151 | 65 | 151 | 151 | 151 | 151 | 151 | 0 | 65 | 65 | On Track | 151 | Source note: Orientation was conducted to 65 cabin crew | KPI-069 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 279 staff oriented and 432 staff vetted by June, 2026 | Increase staff efficiency | No. of staff vetted | Output | 2024/2025 | NA | 432 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432 | 0 | 0 | 0 | 151 | 151 | 151 | 151 | 151 | 151 | 65 | 151 | 151 | 151 | 151 | 151 | 0 | 65 | 65 | On Track | 151 | Source note: Vetting was conducted to 65 Cabin Crew | KPI-070 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 1,000 Staff trained by June, 2026 | Increase operational efficiency | 5 Documents prepared (TNA, Training program, Training Policy, Training Evaluation & Training Reports) | To confirm | 2024/2025 | NA | 2 | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 2 | 0 | -2 | Complete | Medium | Jan actual narrative: Draft Training Policy has been prepared and submitted to the management for their input.and Procurement of Consultant for Training need assesmnet is ongoing under World Bank procedures. ¦ Source note: Draft Training Policy has been prepared and submitted to the management for their input.and Procurement of Consultant for Training need assesmnet is ongoing under World Bank procedures. | KPI-071 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 1,000 Staff trained by June, 2026 | Increase operational efficiency | No. of staff trained | Output | 2024/2025 | NA | 250 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 0 | 0 | 250 | 0 | 0 | 250 | 0 | 0 | 250 | 0 | 0 | 250 | 151 | 151 | 151 | 151 | 151 | 151 | 45 | 151 | 151 | 151 | 151 | 151 | 500 | 45 | -455 | Off Track | 151 | Source note: Training on Environmental, Social and Good Governamce ESG for 45 staffs were coducted. | KPI-072 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 5 HR policies (Staff Regulations, Incentive scheme, Salary Structure,schemes of services & Training Policy) prepared by June, 2026 | Increase operational efficiency | No. of policy document prepared | Output | 2024/2025 | NA | 2 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 2 | 0 | -2 | Off Track | 151 | Jan actual narrative: During the period, draft of staff training policy and internship guidelines was presented to Management meeting for approval before submission to the Board. ¦ Source note: During the period, draft of staff training policy and internship guidelines was presented to Management meeting for approval before submission to the Board. | KPI-073 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 10 Running rooms furnished by June, 2026 | Increase operational efficiency | No. of running rooms furnished | Output | 2024/2025 | NA | 10 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | On Track | 151 | Jan actual narrative: Running staff are now staying at the leased Hotel/Lodge. ¦ Source note: Running staff are now staying at the leased Hotel/Lodge. | KPI-074 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Four(4) existing systems enhanced and upgraded by June, 2026 | Increase operational efficiency | Cargo system | To confirm | 2024/2025 | NA | e-ticketing- Reporting implemented | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [5 empty] | Cargo system enhanced and upgraded | Standalone and Customized ERMS |  | LPMS enhanced and upgraded |  | e-ticketing- Reporting implemented |  | 151 | 151 | 151 | 151 | 151 | 151 | 80 | 151 | 151 | 151 | 151 | 151 | 0 | 80 | 80 | On Track | Medium | Source note: Upgrade of the system is ongoing and has reached 80%. The work is expected to be completed at the end of February, 2026 | KPI-075 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Four(4) existing systems enhanced and upgraded by June, 2026 | Increase operational efficiency | e-ticketing- Reporting | To confirm | 2024/2025 | NA |  | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [12 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | Off Track | 151 | Jan actual narrative: User requirement have been collected, The implementation is planned to starts from February ¦ Source note: User requirement have been collected, The implementation is planned to starts from February ¦ Deviation in source: Resource from eGA were not available | KPI-076 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Four(4) existing systems enhanced and upgraded by June, 2026 | Increase operational efficiency | Upgrade ERP system | To confirm | 2024/2025 | NA |  | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [12 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | Complete | 151 | Jan actual narrative: Terms of reference for engaging consultant was prepared. ¦ Source note: Terms of reference for engaging consultant was prepared. | KPI-077 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Four(4) existing systems enhanced and upgraded by June, 2026 | Increase operational efficiency | Land and Property Management System | To confirm | 2024/2025 | NA |  | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [12 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | Off Track | Medium | Jan actual narrative: The system requirements were reviewed and preparation of the first draft Software Requirements Specification (SRS) were done ¦ Source note: The system requirements were reviewed and preparation of the first draft Software Requirements Specification (SRS) were done | KPI-078 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Three (3) new systems developed by June, 2026 | Increase operational efficiency | Maintainance system | To confirm | 2024/2025 | NA | System in place(Maintainance and overtime) | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | Help desk system in place | [5 empty] | Overtime management system in place |  |  | System in place(Maintainance and overtime) | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | Off Track | 151 | Jan actual narrative: Maintenance System has been planned to be moduled in ERP ¦ Source note: Maintenance System has been planned to be module in ERP so it will be in the upgrading ERP | KPI-079 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Three (3) new systems developed by June, 2026 | Increase operational efficiency | Help desk system | To confirm | 2024/2025 | NA |  | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [12 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | Complete | 151 | Jan actual narrative: Completed | KPI-080 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Three (3) new systems developed by June, 2026 | Increase operational efficiency | Overtime system | To confirm | 2024/2025 | NA |  | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [12 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | Complete | 151 | Jan actual narrative: Gathering of system requirement completed and submitted to Ega for incorporation in the ERMS ¦ Source note: Gathering of system requirement completed. | KPI-081 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Satisfactory procurement audit opinion attained by June, 2026 | Increase operational efficiency | Report | To confirm | 2024/2025 | Satisfactory opinion |  | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [12 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | Off Track | Medium | Jan actual narrative: Implementation of procurement Plan is ongoing ¦ Source note: Implementation of procurement Plan is ongoing | KPI-082 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Annual procurement plan implemented by June, 2026 | Increase operational efficiency | No. of contract awarded | Output | 2024/2025 | Satisfactory opinion | 20 | Count | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | 20 |  |  | 20 | 20 |  | 20 |  |  | 20 | 151 | 151 | 151 | 151 | 151 | 151 | 5 | 151 | 151 | 151 | 151 | 151 | 60 | 5 | -55 | Off Track | 151 | Source note: Five(5) procurement contracts were signed | KPI-083 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Ensure Procurement process is completed as per timeframe standard by June, 2026 | Increase operational efficiency | 120 days International competitive tendering | To confirm | 2024/2025 | Adhered | Adhered | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | Adhered | [5 empty] | Adhered | [5 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | On Track | High | Jan actual narrative: Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time ¦ Source note: Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time | KPI-084 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Ensure Procurement process is completed as per timeframe standard by June, 2026 | Increase operational efficiency | 90 days national competitive tendering | To confirm | 2024/2025 | Adhered |  | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [12 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | On Track | High | Jan actual narrative: Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time ¦ Source note: Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time | KPI-085 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Ensure Procurement process is completed as per timeframe standard by June, 2026 | Increase operational efficiency | 90 days Restricted national competitive tendering | To confirm | 2024/2025 | Adhered |  | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [12 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | On Track | High | Jan actual narrative: Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time ¦ Source note: Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time | KPI-086 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Ensure Procurement process is completed as per timeframe standard by June, 2026 | Increase operational efficiency | 60 days international shopping | To confirm | 2024/2025 | Adhered |  | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [12 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | On Track | High | Jan actual narrative: Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time ¦ Source note: Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time | KPI-087 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Ensure Procurement process is completed as per timeframe standard by June, 2026 | Increase operational efficiency | 45 days national shopping | To confirm | 2024/2025 | Adhered |  | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [12 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | On Track | High | Jan actual narrative: Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time ¦ Source note: Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time | KPI-088 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Ensure Procurement process is completed as per timeframe standard by June, 2026 | Increase operational efficiency | 45 days minor value procurement | To confirm | 2024/2025 | Adhered |  | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [12 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | On Track | High | Jan actual narrative: Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time ¦ Source note: Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time | KPI-089 | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Capacity and staff competence ensured by June, 2026 | Increase operational efficiency | User departments (US) and Tender Board members | To confirm | 2024/2025 | Adhered | 1 | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan | [5 empty] | 1 | [6 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 1 | 0 | -1 | Complete | 151 | Jan actual narrative: No training conducted ¦ Source note: No training conducted | KPI-090 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Capacity and staff competence ensured by June, 2026 | Increase operational efficiency | PMU staff | To confirm | 2024/2025 | Adhered | 1 | Units / To confirm | Source report / department return | Report / inspection / MIS | To be assigned | To be assigned | Monthly | Jan |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 2 | 0 | -2 | Complete | 151 | Jan actual narrative: No training conducted ¦ Source note: No training conducted | KPI-091 | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.

## 03 Activity Input Register
Activity / Input Register
Appendix 2 retained as the supporting activity-input sheet and completed with outcome / KPI logic where missing
Objective | Target Code | Activity Code | Activity / Intervention | Output | Indicator | Outcome | Outcome KPI | Development Objective | Responsible Unit | Source / Evidence | Status | Comments | Link to Corporate Indicator
HIV/AIDS Infections and Non-Communicable Diseases Reduced and supportive services Improved | A01S01 | 1 | To conduct 6 awareness campagns/programs on the spread of HIV/AIDS and Hepatisis B by June 2026 | 6 awareness campagns conducted | No. of awareness campagns/programs conducted | HIV/AIDS Infections and Non-Communicable Diseases Reduced and supportive services Improved | No. of awareness campagns/programs conducted | HIV/AIDS Infections and Non-Communicable Diseases Reduced and supportive services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
HIV/AIDS Infections and Non-Communicable Diseases Reduced and supportive services Improved | A01S02 | 2 | To provide care and support services to staff living with HIV/AIDS including attendence in HIV/AIDS conferences by June 2026 | 30 staff provided with support | No. of staff provided with support | HIV/AIDS Infections and Non-Communicable Diseases Reduced and supportive services Improved | No. of staff provided with support | HIV/AIDS Infections and Non-Communicable Diseases Reduced and supportive services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
HIV/AIDS Infections and Non-Communicable Diseases Reduced and supportive services Improved |  |  |  | xxx staff provided with care | No. of staff provided with care | HIV/AIDS Infections and Non-Communicable Diseases Reduced and supportive services Improved | No. of staff provided with care | HIV/AIDS Infections and Non-Communicable Diseases Reduced and supportive services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
HIV/AIDS Infections and Non-Communicable Diseases Reduced and supportive services Improved | A02S01 | 1 | To facilitate quarterly implementation NCD guidelines and manuals by June, 2026 | 4 NCD awereness seminars conducted | No. of awereness seminars conducted | HIV/AIDS Infections and Non-Communicable Diseases Reduced and supportive services Improved | No. of awereness seminars conducted | HIV/AIDS Infections and Non-Communicable Diseases Reduced and supportive services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
HIV/AIDS Infections and Non-Communicable Diseases Reduced and supportive services Improved | A02S02 | 2 | To conduct quarterly sensitization seminars/workshop to staffs about NCD by June, 2026 | 4 sensitization seminars/workshop conducted | No. of sensitization seminars/workshop conducted | HIV/AIDS Infections and Non-Communicable Diseases Reduced and supportive services Improved | No. of sensitization seminars/workshop conducted | HIV/AIDS Infections and Non-Communicable Diseases Reduced and supportive services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Effective Implementation of the National Anti-Corruption Strategy enhanced and sustained | B01S01 | 1 | To conduct quarterly awareness campaign on the National Anti Corruption by June, 2026 | 4 awareness campaign on the National Anti Corruption conducted | No. of awareness campaign on the National Anti Corruption conducted | Effective Implementation of the National Anti-Corruption Strategy enhanced and sustained | No. of awareness campaign on the National Anti Corruption conducted | Effective Implementation of the National Anti-Corruption Strategy enhanced and sustained | To be assigned | Admin records / reports | 151 | 151 | 151
Effective Implementation of the National Anti-Corruption Strategy enhanced and sustained | B01S02 | 2 | To conduct quarterly ethical committee meetings by June, 2026 | 4 ethical committee meetings conducted | No. of ethical committee meetings conducted | Effective Implementation of the National Anti-Corruption Strategy enhanced and sustained | No. of ethical committee meetings conducted | Effective Implementation of the National Anti-Corruption Strategy enhanced and sustained | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F01C01 | 1 | To facilitate staff recruitment and promotion by June, 2026. | 272 staff recruited | No. of staff recruited | Corporation Operational Efficiency Enhanced | No. of staff recruited | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | xxx staff promoted | No. of staff promoted | Corporation Operational Efficiency Enhanced | No. of staff promoted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F01C02 | 2 | To facilitate Orientantion of new recruits and Vetting by June 2026 | 272 staff Oriented | No. of staff Oriented | Corporation Operational Efficiency Enhanced | No. of staff Oriented | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | 272 staff Vetted | No. of staff Vetted | Corporation Operational Efficiency Enhanced | No. of staff Vetted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F01C03 | 3 | To facilitate preparation of annual Personal Emolunments budget by June 2026. | Annual Personal Emolunments budget prepared | Personal Emolunments budget document in place | Corporation Operational Efficiency Enhanced | Personal Emolunments budget document in place | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F01C04 | 4 | To facilitate transfer of 120 staff quaterly by June 2026. | 120 staff transfered | No. of staff transfered | Corporation Operational Efficiency Enhanced | No. of staff transfered | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F01C05 | 5 | To facilitate reallocation of 41 staff to Dodoma HQ by June 2026. | 41 staff reallocated to Dodoma | No. of staff reallocated | Corporation Operational Efficiency Enhanced | No. of staff reallocated | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F02S01 | 1 | To facilitate training of 1,000 staff by June, 2026 | 1,000 staff trained | No. of staff trained | Corporation Operational Efficiency Enhanced | No. of staff trained | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F02S02 | 2 | To facilitate staff compensation and benefits by June 2026 | 4005 staff provided with compensation and benefits | No. of staff provided with benefit and compensation | Corporation Operational Efficiency Enhanced | No. of staff provided with benefit and compensation | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F02C03 | 3 | To facilitate and coordinate management of staff discipline by June 2026 | 4 discipline committee meetings conducted | No. of discpline committee meetings conducted | Corporation Operational Efficiency Enhanced | No. of discpline committee meetings conducted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F02S04 | 4 | To facilitate participation in proffessional association & attending local & international training meetings by June, 2026. | xxx staff participated in proffessional association training meetings | No. of staff participated in proffessional training meetings | Corporation Operational Efficiency Enhanced | No. of staff participated in proffessional training meetings | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | xxx staff participated in local training meetings | No. of staff participated in local training meetings | Corporation Operational Efficiency Enhanced | No. of staff participated in local training meetings | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | xxx staff participated in international training meetings | No. of staff participated in international training meetings | Corporation Operational Efficiency Enhanced | No. of staff participated in international training meetings | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F02S05 | 5 | To facilitate availability and updates of HR&Admin policy documents by June 2026 | xxx of HR&Admin policy documents prepared | No.of HR&Admin policy documents inplace | Corporation Operational Efficiency Enhanced | No.of HR&Admin policy documents inplace | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F02S06 | 6 | To provide awareness to employees on the updated HR&Admin policies by June 2026 | xxx awareness of HR&Admin policies conducted | No. of awareness on HR&Admin policies conducted | Corporation Operational Efficiency Enhanced | No. of awareness on HR&Admin policies conducted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F05C01 | 1 | To facilitate and furnishing 10 running rooms by June 2026 | 10 running rooms furnished | No. of running rooms furnished | Corporation Operational Efficiency Enhanced | No. of running rooms furnished | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F05C02 | 2 | To facilitate two Workers Council meetings, management- employees & Management - Union meetings, by June 2026 | 2 Workers Council meetings Conducted | No. of Workers Council meetings Conducted | Corporation Operational Efficiency Enhanced | No. of Workers Council meetings Conducted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | Management and employees meeting conducted | No. of Management and employees meeting conducted | Corporation Operational Efficiency Enhanced | No. of Management and employees meeting conducted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | Management and Union meeting conducted | No. of Management and Union meeting conducted | Corporation Operational Efficiency Enhanced | No. of Management and Union meeting conducted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F05C03 | 03 | To organise & facilitate Labour and Women day by June 2026 | Labour day organised | Labour day conducted | Corporation Operational Efficiency Enhanced | Labour day conducted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | Women day organised | Women day conducted | Corporation Operational Efficiency Enhanced | Women day conducted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F05C04 | 04 | To facilitate TRC sports bonanza by June 2026 | xxx TRC sports bonanza conducted | No. of TRC sports bonanza conducted | Corporation Operational Efficiency Enhanced | No. of TRC sports bonanza conducted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F05C05 | 05 | To facilitate and coordinate staff welfare by June 2026 | xxx staff provided with welfare and benefit | No. of staff provided with welfare and benefit | Corporation Operational Efficiency Enhanced | No. of staff provided with welfare and benefit | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S01 | 01 | To facilitate and cordinate operations of DGs office by June 2026 | Administrative support services provided to the DG's office | % of Administrative support services provided | Corporation Operational Efficiency Enhanced | % of Administrative support services provided | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S02 | 02 | To facilitate provision of utilities services to TRC buildings by June 2026 | xxx TRC buildings provided with utilities services | No. of TRC buildings provided with utilities services | Corporation Operational Efficiency Enhanced | No. of TRC buildings provided with utilities services | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S03 | 03 | To provide office supplies and equipments to staff by June 2026 | XXX staff provided with office supplies and equipments | No. of staff provided with office supplies and equipments | Corporation Operational Efficiency Enhanced | No. of staff provided with office supplies and equipments | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S04 | 04 | To provide monthly Maintenance of 60 existing motor vehicle and motor cycles by June, 2026 | 60 motor vehicle and motor cycles maintained | No. of motor vehicle and motor cycles maintained | Corporation Operational Efficiency Enhanced | No. of motor vehicle and motor cycles maintained | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S05 | 05 | To facilitate operations of Residual Services and Digitalisation of Records by June, 2026 | Residual Services and Records digitalized | No. of Residual Services and Records digitalized | Corporation Operational Efficiency Enhanced | No. of Residual Services and Records digitalized | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S06 | 06 | To facilitate operation of railway police (Investigation, Ambush, Dog ration) on TRC networks by June, 2026 | xxx Investigation of railway police conducted | No. of investigation conducted | Corporation Operational Efficiency Enhanced | No. of investigation conducted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | xxx Ambush of railway police facilitated | No. of Ambush conducted | Corporation Operational Efficiency Enhanced | No. of Ambush conducted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | xxx Kg of Dog ration provided | No. of Kg of dog ration provided | Corporation Operational Efficiency Enhanced | No. of Kg of dog ration provided | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F14S01 | 01 | To facilitate 9 Railway Dispensary to provide health service to staff and community by June, 2026 | 9 Railway Dispensaries facilitated with equipment and facilities | No. of Railway Dispensaries facilitated with equipment and facilities | Corporation Operational Efficiency Enhanced | No. of Railway Dispensaries facilitated with equipment and facilities | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F14S02 | 02 | To provide Primary School education to 208 employees children in remote areas and wayside stations by June, 2026 | 208 employees children facilitated with Primary school education | No. of employees children facilitated with Primary school education | Corporation Operational Efficiency Enhanced | No. of employees children facilitated with Primary school education | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F14S03 | 03 | To conduct two Board Meeting of Itigi primary school and Graduation ceremony by June, 2026 | 2 Board Meetings conducted | No. of Board Meetings a conducted | Corporation Operational Efficiency Enhanced | No. of Board Meetings a conducted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | Graduation ceremony conducted | No. of Graduation ceremony conducted | Corporation Operational Efficiency Enhanced | No. of Graduation ceremony conducted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F16S01 | 01 | To facilitate and supervise cleaning services by June, 2026 | TRC buildings facilitated with cleaning services | No. of cleaniless services contract signed | Corporation Operational Efficiency Enhanced | No. of cleaniless services contract signed | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | TRC buildings services supervised | No. of TRC buildings with cleaning services supervised | Corporation Operational Efficiency Enhanced | No. of TRC buildings with cleaning services supervised | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F16S02 | 02 | To facilitate and supervise security services by June, 2026 | TRC buildings facilitated with Security services | No. of Security services contracts signed | Corporation Operational Efficiency Enhanced | No. of Security services contracts signed | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | TRC Security services supervised | No. of Security services supervised | Corporation Operational Efficiency Enhanced | No. of Security services supervised | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  | SUB-VOTE NAME: PROCUREMENT MANAGEMENT UNIT |  |  | Corporation Operational Efficiency Enhanced |  | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Corporation Operational Efficiency Enhanced | Indicator | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Financial management and marketing strengthened | D07S01 | 01 | To facilitate procurement of 130 of Service provider (Consultancy, Contractor and Suppliers) by June, 2026 | 130 Service providers procured | No. of Service providers procured | Financial management and marketing strengthened | No. of Service providers procured | Financial management and marketing strengthened | To be assigned | Admin records / reports | 151 | 151 | 151
Financial management and marketing strengthened | D07S02 | 02 | To facilitate survey for disposal of goods by June, 2026 | Unused goods/assets disposed | No. of unused goods/assets disposed | Financial management and marketing strengthened | No. of unused goods/assets disposed | Financial management and marketing strengthened | To be assigned | Admin records / reports | 151 | 151 | 151
Financial management and marketing strengthened | D07S03 | 03 | To prepare and update TRC inventory and conduct Annual Stocktaking by June, 2026 | TRC inventory prepared and updated | Updated Inventory register in place | Financial management and marketing strengthened | Updated Inventory register in place | Financial management and marketing strengthened | To be assigned | Admin records / reports | 151 | 151 | 151
Financial management and marketing strengthened |  |  |  | Annual Stocktaking conducted | Annual Stocktaking in place | Financial management and marketing strengthened | Annual Stocktaking in place | Financial management and marketing strengthened | To be assigned | Admin records / reports | 151 | 151 | 151
Financial management and marketing strengthened | D07S04 | 04 | To prepare and develop comprehensive TRC Procurement and Action Plan by June, 2026 | Procurement Plan developed | Procurement Plan document in place | Financial management and marketing strengthened | Procurement Plan document in place | Financial management and marketing strengthened | To be assigned | Admin records / reports | 151 | 151 | 151
Financial management and marketing strengthened |  |  |  | Procurement Action Plan developed | Procurement Action Plan document in place | Financial management and marketing strengthened | Procurement Action Plan document in place | Financial management and marketing strengthened | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S01 | 01 | To provide office supplies and equipment to 35 staff by June 2026 | 35 staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S02 | 02 | To conduct seminar and training to staff and Board of Directors regarding regular changes on procurement Act and Regulations by June, 2026 | xxx Seminar and training conducted to Board of Directors | No. of seminars conducted to board of directors | Corporation Operational Efficiency Enhanced | No. of seminars conducted to board of directors | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | xxx Seminar and training conducted to staff | No. of seminars conducted to staff | Corporation Operational Efficiency Enhanced | No. of seminars conducted to staff | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S03 | 03 | To provide proffessional training to 10 procurement staff by June, 2026 | 10 staff provided with proffessional training | No. of staff trained | Corporation Operational Efficiency Enhanced | No. of staff trained | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S04 | 04 | To facilitate Clearance of Oversea consignments from 20 contracts by June 2026 | 20 oversea consignment contract cleared | No. of oversea consignment contract cleared | Corporation Operational Efficiency Enhanced | No. of oversea consignment contract cleared | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S05 | 05 | To facilitate logistics of supplies to three zones and Kwala SGR Workshop by June 2026 | 3 zones facilitated with supplies and equipment | No. of Zones facilitated | Corporation Operational Efficiency Enhanced | No. of Zones facilitated | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  | SUB-VOTE NAME: INTERNAL AUDIT UNIT |  |  | Corporation Operational Efficiency Enhanced |  | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Corporation Operational Efficiency Enhanced | Indicator | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Financial management and marketing strengthened. | D06S01 | 01 | To Audit Quarterly Development Project ( SGR (Lot 3,4 & 5), Kilosa Gulwe,TIRP by June, 2026 | 3 Development Projects audit conducted quarterly | No. of development project audited quarterly | Financial management and marketing strengthened. | No. of development project audited quarterly | Financial management and marketing strengthened. | To be assigned | Admin records / reports | 151 | 151 | 151
Financial management and marketing strengthened. | D06S02 | 02 | To Audit Monthly Corporation Activities - MGR and SGR by June, 2026 | 48 operational audited reports prepared | No. of audited reports prepared | Financial management and marketing strengthened. | No. of audited reports prepared | Financial management and marketing strengthened. | To be assigned | Admin records / reports | 151 | 151 | 151
Financial management and marketing strengthened. | D06S03 | 03 | To prepare Internal Audit Manual, strategic Audit Plan and Audit Charter by June, 2026 | 3 Audited documents (Audit Manual, strategic Audit Plan and Audit Charter) prepared | No. of documents prepared | Financial management and marketing strengthened. | No. of documents prepared | Financial management and marketing strengthened. | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced | F11S02 | 02 | To facilitate conducive working environment to 11 staff by june 2026 | 11 staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Capacity of the corporation to discharge its mandates enhanced | % of satisfaction of conducive working envoronment | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced | F11S03 | 03 | To Attend professional Seminars NBAA & IIA) and professional exams (CPA, CIA,CSPTB, CFE & CISA) | 11 staff attended professional Seminars and exams | No. of staff | Capacity of the corporation to discharge its mandates enhanced | No. of staff | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced |  |  | SUB-VOTE NAME: FINANCE AND ACCOUNTS UNIT |  |  | Capacity of the corporation to discharge its mandates enhanced |  | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Capacity of the corporation to discharge its mandates enhanced | Indicator | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Financial management and marketing strengthened | F11S01 | 01 | To facilitate preparation of annual financial statements by June, 2026 | Annual financial statement report prepared | No. of Annual financial statement prepared | Financial management and marketing strengthened | No. of Annual financial statement prepared | Financial management and marketing strengthened | To be assigned | Admin records / reports | 151 | 151 | 151
Financial management and marketing strengthened | F11S02 | 02 | To conduct quartely survey for updation of Fixed Asset register by June 2026 | Fixed Asset register updated | No. of Fixed asset register updated | Financial management and marketing strengthened | No. of Fixed asset register updated | Financial management and marketing strengthened | To be assigned | Admin records / reports | 151 | 151 | 151
Financial management and marketing strengthened | F11S03 | 03 | To facilitate annual Asset verification by June 2026 | Annual Asset verification report prepared | No. of Asset verification report | Financial management and marketing strengthened | No. of Asset verification report | Financial management and marketing strengthened | To be assigned | Admin records / reports | 151 | 151 | 151
Financial management and marketing strengthened | D01S01 | 01 | To facilitate revenue collections of 243.28 billion by June 2026 | 243.28 billion Collected | Amount of Revenue collected | Financial management and marketing strengthened | Amount of Revenue collected | Financial management and marketing strengthened | To be assigned | Admin records / reports | 151 | 151 | 151
Financial management and marketing strengthened | D01S02 | 02 | To facilitate routine TRC payments (staff and third parties) by June 2026 | Payment of staff and third parties facilitated | Amount of staff payment facilitated | Financial management and marketing strengthened | Amount of staff payment facilitated | Financial management and marketing strengthened | To be assigned | Admin records / reports | 151 | 151 | 151
Financial management and marketing strengthened |  |  |  |  | Amount of third parties payment facilitated | Financial management and marketing strengthened | Amount of third parties payment facilitated | Financial management and marketing strengthened | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F11S01 | 01 | To provide conducive working environment to 80 staffs by June,2026 | 80 staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F11S02 | 01 | To attend four workshops and seminars as per NBAA by law,PPRA and Tax by June,2026 | 80 staff attended workshops and seminars | No. of staff attended | Corporation Operational Efficiency Enhanced | No. of staff attended | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  | 01 | To facilitate collection of TRC debts by June,2026 | xxx of total debt collected | Amount of debt | Corporation Operational Efficiency Enhanced | Amount of debt | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  | SUB-VOTE NAME: CORPORATE PLANNING AND INVESTMENT UNIT |  |  | Corporation Operational Efficiency Enhanced |  | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Corporation Operational Efficiency Enhanced | Indicator | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F03S01 | 01 | To prepare Corporate Strategic Plan for the Financial Year 2026/2027 - 2030/2031 by June, 2026 | Corporate Strategic Plan document prepared | Corporate Strategic Plan in place | Corporation Operational Efficiency Enhanced | Corporate Strategic Plan in place | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F03S02 | 02 | To participate in preparations of policies and plans and coordinate review of departmental policies by June, 2026 | xxx policies prepared | No. of policies prepared | Corporation Operational Efficiency Enhanced | No. of policies prepared | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | xxx plans prepared | No. of Plans prepared | Corporation Operational Efficiency Enhanced | No. of Plans prepared | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | xxx guidelines prepered | No. of guideline prepared | Corporation Operational Efficiency Enhanced | No. of guideline prepared | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | xxx policies reviewed | No. of policies reviewed | Corporation Operational Efficiency Enhanced | No. of policies reviewed | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F07S03 | 03 | To coordinate preparations of annual Medium Term Expenditure Framework (MTEF) financial year 2026/2027 by June, 2026 | Corporate Annual Medium Term Expenditure Framework (MTEF) FY 2026/2027 prepared | Medium Term Expenditure Framework in place | Corporation Operational Efficiency Enhanced | Medium Term Expenditure Framework in place | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F03S04 | 04 | To coordinate preparations of Action Plan for financial year 2026/2027 by June, 2026 | Annual Action plan document prepared | Annual Action plan in place | Corporation Operational Efficiency Enhanced | Annual Action plan in place | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F03S05 | 05 | To coordinate budget implementation and control through quarterly budget committee meetings by June, 2026 | 4 budget committee meetings conducted | No. of committee conducted | Corporation Operational Efficiency Enhanced | No. of committee conducted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F03S06 | 06 | To prepare Tanzania Railway Master Plan by June, 2026 | Railway Master Plan developed | Railway Master Plan in place | Corporation Operational Efficiency Enhanced | Railway Master Plan in place | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F03S07 | 07 | To prepare quarterly, semi annual and annual progress reports as per budget guideline by June, 2026 | 4 Progress reports prepared and submitted | Report | Corporation Operational Efficiency Enhanced | Report | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F03S08 | 08 | To coordinate Regional, bilateral and International planning in relation to railway sub sector by June, 2026 | 7 Regional meetings attended | No. of Regional meetings | Corporation Operational Efficiency Enhanced | No. of Regional meetings | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | 5 International meetings attended | No. of International meetings | Corporation Operational Efficiency Enhanced | No. of International meetings | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | 2 bilateral meetings attended | No. of bilateral meetings | Corporation Operational Efficiency Enhanced | No. of bilateral meetings | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F03S09 | 09 | To coordinate Parliamentary standing Committees meetings and submit implementation of projects and Budget by June, 2026 | 3 Parliamentary standing Committees meetings attended | No. of meetings attended | Corporation Operational Efficiency Enhanced | No. of meetings attended | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F03S10 | 10 | To conduct seminar on railway projects and its implementation to new Members of Parliament by June, 2026 | 1 seminar conducted | No. of seminar | Corporation Operational Efficiency Enhanced | No. of seminar | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F03S11 | 11 | To coordinate preparation of Comprehensive Business Transformation Strategy by June, 2026 | Comprehensive Business Transformation Strategy in place | Report | Corporation Operational Efficiency Enhanced | Report | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F07S01 | 01 | To attend local and international business and investment forums/meetings for investment of railway projects by June, 2026 | 2 local business forum/meetings attended | No. of meetings | Corporation Operational Efficiency Enhanced | No. of meetings | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | 2 international business forum/meetings attended | No. of meetings | Corporation Operational Efficiency Enhanced | No. of meetings | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F07S02 | 02 | To prepare project documents (Concept Note and Pre-feasibility) for railway projects investment by June, 2026 | 1 Concept Note for railway projects prepared | No. of Concept Note prepared | Corporation Operational Efficiency Enhanced | No. of Concept Note prepared | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | 1 Pre-feasibility study for railway projects prepared | No. of Pre-feasibility study prepared | Corporation Operational Efficiency Enhanced | No. of Pre-feasibility study prepared | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F07S03 | 03 | To prepare project profile for PPP investement and coordinate implementation of PPP regulation by June, 2026 | 4 PPP project profiles document prepared | No. of PPP project profiles document prepared | Corporation Operational Efficiency Enhanced | No. of PPP project profiles document prepared | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | 1 PPP regulation coordinated | PPP regulation complied | Corporation Operational Efficiency Enhanced | PPP regulation complied | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S01 | 01 | To provide conducive working environment to 10 CPIU staff by June, 2026 | 10 staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S02 | 02 | To facilitate 10 CPIU staff to attend proffesional local and international trainings, workshops and seminars by June, 2026 | 10 staff facilitate to attend proffessional training | No. of staffs trained | Corporation Operational Efficiency Enhanced | No. of staffs trained | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  | SUB-VOTE NAME: MONITORING AND EVALUATION UNIT |  |  | Corporation Operational Efficiency Enhanced |  | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Corporation Operational Efficiency Enhanced | Indicator | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F03S01 | 01 | To coordinate preparation and implementation of Performance Contracts by June, 2026 | Performance Contracts prepared and implemented | No. of Performance Contracts prepared and implemented | Corporation Operational Efficiency Enhanced | No. of Performance Contracts prepared and implemented | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F03S02 | 02 | To conduct M&E Readiness Assessment and develop M&E documentations by June, 2026 | M&E Readiness assessment document prepared | M&E Readiness assessment report document in place | Corporation Operational Efficiency Enhanced | M&E Readiness assessment report document in place | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | M&E Plan prepared | M&E Plan document in place | Corporation Operational Efficiency Enhanced | M&E Plan document in place | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | M&E Operational Manual Prepared | M&E Operational Manual document in lace | Corporation Operational Efficiency Enhanced | M&E Operational Manual document in lace | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | M&E Framework prepared | M&E Framework document in place | Corporation Operational Efficiency Enhanced | M&E Framework document in place | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | M&E Strategy prepared | M&E Strategy document in place | Corporation Operational Efficiency Enhanced | M&E Strategy document in place | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F03S03 | 03 | To facilitate and participate in Annual Joint Transport Sector Review (JTSR) meeting by June, 2026. | Joint Transport Sector Review meeting attended | No of meetings attended | Corporation Operational Efficiency Enhanced | No of meetings attended | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F03S04 | 04 | To monitor and evaluate the implementation of institutional annual plans by June, 2026. | Institutional plan monitored and evaluated | % of activities monitored in a period | Corporation Operational Efficiency Enhanced | % of activities monitored in a period | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  |  | No. of evaluation studies conducted | Corporation Operational Efficiency Enhanced | No. of evaluation studies conducted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F03S05 | 05 | To coordinate development and operationalisation of integrated Monitoring and Evaluation system (M&E) by June, 2026 | Development of Integrated Monitoring and Evaluation system | % of integrated M&E System developed | Corporation Operational Efficiency Enhanced | % of integrated M&E System developed | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  | Operationalisation of Integrated Monitoring and Evaluation System | % of operationalisation of Integrated M&E system | Corporation Operational Efficiency Enhanced | % of operationalisation of Integrated M&E system | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S01 | 01 | To provide conducive working environment to M&E staff by June, 2026. | 11 staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S02 | 02 | To facilitate M&E staff to attend proffesional local and international trainings, workshops and seminars by June, 2026 | 11 staff attended professional Seminars, training and workshop | No. of staff attended seminars and training | Corporation Operational Efficiency Enhanced | No. of staff attended seminars and training | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  | SUB VOTE NAME:TANZANIA INSTITUTE OF RAIL TECHNOLOGY |  |  | Corporation Operational Efficiency Enhanced |  | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Corporation Operational Efficiency Enhanced | Indicator | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S01 | 01 | To provide conducive working environment to 52 TIRTEC staffs by June, 2026 | 52 staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S02 | 02 | To coordinate and supervise academics and administrative matters by June, 2025 | Academics and administrative matters coordinated and supervised | No. of academics and administrative matters coordinated | Corporation Operational Efficiency Enhanced | No. of academics and administrative matters coordinated | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  |  |  | No. of academics and administrative matters supervised | Corporation Operational Efficiency Enhanced | No. of academics and administrative matters supervised | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S03 | 03 | To facilitate availabiliy and supply of teaching and learning materials | Institute equiped with teaching and learning materials | % of teaching and learning materials supplied | Corporation Operational Efficiency Enhanced | % of teaching and learning materials supplied | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S04 | 04 | To organize and facilitate graduation ceremony by June 2026 | Graduation ceremony conducted | No. of Graduation ceremony conducted | Corporation Operational Efficiency Enhanced | No. of Graduation ceremony conducted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S05 | 05 | To conduct advisory board of governor meetings by June, 2026 | 6 Advisory board governor meeting conducted | No of meetings | Corporation Operational Efficiency Enhanced | No of meetings | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S06 | 06 | To facilitate 15 TIRTEC staffs to attend local poffessional boards trainings, meetings and workshops by june 2026 | 15 Staffs facilitated to attend local and international professional trainings, meetings and workshop | No. of staff trained | Corporation Operational Efficiency Enhanced | No. of staff trained | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F14S01 | 01 | To facilitate 20 instructors to supervise students in industrial training programmes June, 2026 | 20 instructors facilitated to supervise students in industrial training programmes | No of instructors engaged in supervision | Corporation Operational Efficiency Enhanced | No of instructors engaged in supervision | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F14S02 | 02 | To develop and operationalize students information system by June 2026 | Student information system developed and operationalized | System in place | Corporation Operational Efficiency Enhanced | System in place | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F14S03 | 03 | To develop 5 teaching curriculam by june 2026 | 5 Teaching Curriculum developed | No. of Curriculum developed | Corporation Operational Efficiency Enhanced | No. of Curriculum developed | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F14S04 | 04 | To carry out 1 research in railway industry by June, 2026 | 1 Railway industry reaserch conducted | Research report | Corporation Operational Efficiency Enhanced | Research report | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F14S05 | 05 | Capacity building to 52 TIRTEC staff by june 2026 | 52 staffs trained | No. of staffs trained | Corporation Operational Efficiency Enhanced | No. of staffs trained | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  | SUB-VOTE NAME: LEGAL SERVICE UNIT |  |  | Corporation Operational Efficiency Enhanced |  | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Corporation Operational Efficiency Enhanced | Indicator | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F11S01 | 01 | To represent the Corporation before the court of law and or quassi judicial bodies on monthly basis by June, 2026 | Corporation represented before the court | No. of cases finalized | Corporation Operational Efficiency Enhanced | No. of cases finalized | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F11S02 | 02 | To facilitate and coordinate review of cases/amendments of Railway Act, Cap. 170 and its regulations and related matters thereto by June, 2026 | Railway Act and regulations reviewed | Act and number of regulations reviewed | Corporation Operational Efficiency Enhanced | Act and number of regulations reviewed | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F11S03 | 03 | To review 50 employment contracts, vet 50 procurement & operational Contracts and submission of same to the AG, 50 lease agreements, 10 MoUs, and other Agreements of the Corporation by June, 2026 | 50 contracts reviewed and vetted | No of contracts | Corporation Operational Efficiency Enhanced | No of contracts | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F18S01 | 01 | To facilitate four (4) Ordinary & four (4) Extra ordinary Board Meetings by June, 2026 | 8 board meetings conducted | No of meetings | Corporation Operational Efficiency Enhanced | No of meetings | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F18S02 | 02 | To facilitate four (4) statutory Board Committes meetings by June, 2026 | 4 statutory board meetings conducted | No of meetings | Corporation Operational Efficiency Enhanced | No of meetings | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F18S03 | 03 | To facilitate 8 Board members in monitoring and evaluation of TRC projects by June, 2026 | 8 board members participated in Monitoring of projects | No of members | Corporation Operational Efficiency Enhanced | No of members | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S01 | 01 | To provide conducive environment to 13 departmental staff by June 2026 | 13 staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S02 | 02 | To facilitate 11 departmental staff to attend proffessional seminars and trainings by June, 2026 | 11 staff attended professional Seminars, training and workshop | No of staffs | Corporation Operational Efficiency Enhanced | No of staffs | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  | SUB-VOTE NAME: PUBLIC RELATIONS UNIT |  |  | Corporation Operational Efficiency Enhanced |  | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Corporation Operational Efficiency Enhanced | Indicator | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F12S01 | 01 | To prepare and disseminate corporation's performance information to the public throughout by June, 2026 | 100 % of Corporation Performance information reports to the public prepared and disseminated | Percentage (%) of public information prepared and disseminated | Corporation Operational Efficiency Enhanced | Percentage (%) of public information prepared and disseminated | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F12S02 | 02 | To implement three Corporate Social Responsibility (CSR) Policy by June 2026 | 3 corporate social responsibility undertaken | No of corporate social responsibility | Corporation Operational Efficiency Enhanced | No of corporate social responsibility | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F12S03 | 03 | To conduct quartly awareness to the Citizens along the railway corridor by June, 2026 | 4 awareness compaign conducted | No of awareness campign | Corporation Operational Efficiency Enhanced | No of awareness campign | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F12S04 | 04 | To coordinate and participate in National and International exhibition, TRC Week and other related events, by June, 2026 | 6 National and International exhibition, coordinated and attended. | No of exhibition attended | Corporation Operational Efficiency Enhanced | No of exhibition attended | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S01 | 01 | To provide conducive working environment to 14 departmental staff by June, 2026 | 14 staff provided with working conducive environment | No of staffs with conducive environment | Corporation Operational Efficiency Enhanced | No of staffs with conducive environment | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S02 | 02 | To facilitate 10 staff to attend workshops and annual meetings related to Public Relations Affair by June, 2026 | 10 staff attended professional Seminars, training and workshop | No of staffs trained/ attended seminar | Corporation Operational Efficiency Enhanced | No of staffs trained/ attended seminar | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  | SUB-VOTE NAME: INFORMATION COMMUNICATION TECHNOLOGY (ICT) |  |  | Corporation Operational Efficiency Enhanced |  | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Corporation Operational Efficiency Enhanced | Indicator | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F16S01 | 01 | Upgrade and Enhancement of existing systems (Eg.cargo system and LPMS) by 2026 | 2 ICT systems enhanced and upgraded | No. of internal systems upgraded | Corporation Operational Efficiency Enhanced | No. of internal systems upgraded | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F16S02 | 02 | To develop new systems by June. 2026 | 2 New system developed | No. of new systems | Corporation Operational Efficiency Enhanced | No. of new systems | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F16S03 | 03 | To conduct network vulnerability scan and Penetration for netwrok infrastructure and Security Operation and Incience Response by June, 2026 | One network vulnerability scan and Penetration for netwrok infrastucture and security operation conducted | No. of network infrastructure security enhanced | Corporation Operational Efficiency Enhanced | No. of network infrastructure security enhanced | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F05S01 | 01 | To maintain and service ICT equipment, software and accessories for both MGR and SGR by June 2026 | Enhance ICT network service availability | %of network availability | Corporation Operational Efficiency Enhanced | %of network availability | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F05S02 | 02 | To maintain monthly Internet connectivity and all application hosting by June, 2026 | Enhance internet connectivity and availability | % of internet avaliability | Corporation Operational Efficiency Enhanced | % of internet avaliability | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F05S04 | 04 | To conduct awareness of the ICT security policy to TRC staff throughout the network by June, 2026 | 4 Awareness of the ICT security policy to TRC staff conducted | No. of awareness | Corporation Operational Efficiency Enhanced | No. of awareness | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S01 | 01 | To provide conducive working environment to 47 staff by June, 2026 | 47 staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10c02 | 02 | To facilitate 40 ICT Staff to attend training by june 2026 | 40 staff attended training | No. of staffs trained | Corporation Operational Efficiency Enhanced | No. of staffs trained | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10C03 | 03 | To facilitate 21 ICT Staff to attend workshops and professional bodies by june 2026 | 21staff attended professional workshop and professional bodies | No. of staffs attended | Corporation Operational Efficiency Enhanced | No. of staffs attended | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  | SUB VOTE NAME:RAIL SAFETY AND SECURITY UNIT |  |  | Corporation Operational Efficiency Enhanced |  | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | Target code | MTEF Activity Code | MTEF Activity Code | Output (Lower level Result) | Indicator | Corporation Operational Efficiency Enhanced | Indicator | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Railway infrastructure, Rolling stock and Safety improved | C07S01 | 01 | To monitor instutional security services to MGR and SGR operation by June 2026 | enhance institutional security in operation activities | % of number of insecurity incidence occured | Railway infrastructure, Rolling stock and Safety improved | % of number of insecurity incidence occured | Railway infrastructure, Rolling stock and Safety improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway infrastructure, Rolling stock and Safety improved | C07S02 | 02 | To conduct quarterly Safety inspection of railway operation and maintenance by June 2026 | 4 safety inspection of railway operation conducted | No. of inspection conducted | Railway infrastructure, Rolling stock and Safety improved | No. of inspection conducted | Railway infrastructure, Rolling stock and Safety improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics services Improved | E05S01 | 1 | To Conduct 8 Safety Sensitization Programs and seminars by June 2026. | 8 safety sensitization programs and seminars conducted | No.of sensitization programs conducted | Railway Transport and Logistics services Improved | No.of sensitization programs conducted | Railway Transport and Logistics services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics services Improved | E05S02 | 2 | To conduct quarterly monitoring of Accident minimization strategy by June 2026 | Accident reduced | No. of accident | Railway Transport and Logistics services Improved | No. of accident | Railway Transport and Logistics services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics services Improved | E05S03 | 3 | To carry out accident and incident investigation by June 2026 | Accident cause determined | No.of accident | Railway Transport and Logistics services Improved | No.of accident | Railway Transport and Logistics services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics services Improved | E05S04 | 4 | To develop and implement Railway Operations Maintenance Rulebooks, Manuals and Standard Operational Procedures by june 2026. | Operation and maintenance documents developed | Report | Railway Transport and Logistics services Improved | Report | Railway Transport and Logistics services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics services Improved | E05S05 | 5 | To cordinate and participate in international safety week by June 2026. | International safety week attended | Report | Railway Transport and Logistics services Improved | Report | Railway Transport and Logistics services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics services Improved | E03S01 | 01 | To conduct four monitoring of safety compliance in accordance with Regulatory Act by june 2026. | 4 Safety compliance activites conducted | Report | Railway Transport and Logistics services Improved | Report | Railway Transport and Logistics services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics services Improved | E03S02 | 02 | To conduct quartely occupational health and safety awareness seminars and programs by June, 2026 | 4 occupational health and safety awareness seminars and programs conducted | Report | Railway Transport and Logistics services Improved | Report | Railway Transport and Logistics services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics services Improved | E07S01 | 1 | To develop, Implement and Upadate Corporate Emergency Preparedness and Response Plan by June, 2026 | Corporate emergency preparedness and response plan developed and implemented | Corporate emergency plan | Railway Transport and Logistics services Improved | Corporate emergency plan | Railway Transport and Logistics services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics services Improved | E07S02 | 2 | To Monitor quarterly implementation of the Safety Management System by June 2026 | safety management system monitored | Report | Railway Transport and Logistics services Improved | Report | Railway Transport and Logistics services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced | F10S01 | 01 | To provide conducive working enviroment to 144 RSSU staff by June, 2026 | 144 staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Capacity of the corporation to discharge its mandates enhanced | % of satisfaction of conducive working envoronment | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced | F10S02 | 02 | To facilitate RSSU Staff to attend professional Training, Meetings, and Seminars by June 2026. | 5 staffs trained | No.of staffs trained | Capacity of the corporation to discharge its mandates enhanced | No.of staffs trained | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced |  |  | SUB VOTE NAME:RISK MANAGEMENT AND QUALITY ASSUARANCE UNIT |  |  | Capacity of the corporation to discharge its mandates enhanced |  | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Capacity of the corporation to discharge its mandates enhanced | Indicator | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Railway transport, safety systems and logistics services improved | E07S01 | 1 | To review and update of corporate's risk register and monitoring of implementation of risk action plan by june 2026 | Corporate risk register reviewed and updated; Risk action plan implemented | Documents reviwed and implemented | Railway transport, safety systems and logistics services improved | Documents reviwed and implemented | Railway transport, safety systems and logistics services improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway transport, safety systems and logistics services improved | E07S02 | 2 | To develop and implement institutional Fraud Risk Management by june 2026. | institutional Fraud Risk Management develped and implemented | Document developed | Railway transport, safety systems and logistics services improved | Document developed | Railway transport, safety systems and logistics services improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway transport, safety systems and logistics services improved | E07S03 | 03 | To conduct risk control awareness services to staff and management by June 2026 | Risk control awareness conducted | No. of awareness conducted | Railway transport, safety systems and logistics services improved | No. of awareness conducted | Railway transport, safety systems and logistics services improved | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced | F10S01 | 01 | To provide conducive working enviroment to staff by June, 2026 | xxx staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Capacity of the corporation to discharge its mandates enhanced | % of satisfaction of conducive working envoronment | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced | F10S02 | 02 | To facilitate RSSU Staff to attend professional Training, Meetings, and Seminars by June 2026. | XX staffs trained | No.of staffs trained | Capacity of the corporation to discharge its mandates enhanced | No.of staffs trained | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced |  |  | SUB-VOTE NAME: DIRECTORATE OF CIVIL ENGINEERING AND INFRASTRUCTURE |  |  | Capacity of the corporation to discharge its mandates enhanced |  | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Capacity of the corporation to discharge its mandates enhanced | Indicator | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S01 | 01 | To provide conducive working Environment to 55 staff by June, 2026 | 1200 staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S02 | 02 | To facilitate 16 railway projects preparation by June, 2026 | 16 railway projects prepared | No .of projects prepared | Corporation Operational Efficiency Enhanced | No .of projects prepared | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S03 | 03 | To facilitate 55 staff to attend national and International professional meetings and workshops by June, 2026 | 74 staffs attended profesional meetngs | No.of staffs attended | Corporation Operational Efficiency Enhanced | No.of staffs attended | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S04 | 04 | To participate in regional and international meetings and conferences related to Railways by June 2026 | 4 regional and international meetings attended | No. of meetings attended | Corporation Operational Efficiency Enhanced | No. of meetings attended | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S05 | 05 | To conduct daily and monthly inspection and Maintenance for the SGR and MGR railway network by June, 2026 | Daily and monthly railway inspection conducted | No. of inspection conducted | Corporation Operational Efficiency Enhanced | No. of inspection conducted | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S06 | 06 | To conduct routine maintainance of civil structures and Operation buildings of SGR and MGR by June, 2026 | XX civil structure and operation building maintained | No. of civil structure and operation buildings maintained | Corporation Operational Efficiency Enhanced | No. of civil structure and operation buildings maintained | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  | SUB VOTE NAME: DIRECTORATE OF SIGNALLING AND TELECOMMUNICATION |  |  | Corporation Operational Efficiency Enhanced |  | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Corporation Operational Efficiency Enhanced | Indicator | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | C03S01 | 01 | To conduct routine inspection and maintenance of Signaling and Telecommunication Infrastructure (Facilities, System and Sub-system) for SGR and MGR line by June, 2026 | Signalling and Telecommunication infrastructure maintained | Report | OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | Report | OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | To be assigned | Admin records / reports | 151 | 151 | 151
OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | C03S02 | 02 | To maintain service availability of Signaling and Telecommunication services for MGR and SGR by June, 2026 | 100 percentaeg availability of Signalling and Telecommunication services | Report | OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | Report | OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | To be assigned | Admin records / reports | 151 | 151 | 151
OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | C03S03 | 03 | To facilitate monitoring, evaluation and supervision of the project by June, 2026 | Signalling and Telecommunication projects monitored | Report | OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | Report | OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S01 | 01 | To provide conducive working environment for 500 Staffs by June, 202 | 500 staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S02 | 02 | To participate in professional, national and international meeting related to Signaling and Telecommunication by June 2026 | 4 National and 4 international meetings attended | No. of meetings attended | Corporation Operational Efficiency Enhanced | No. of meetings attended | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S03 | 03 | To conduct short course training related to Signaling and Telecommunication by June 2026 | 165 staffs trained | No. of staff trained | Corporation Operational Efficiency Enhanced | No. of staff trained | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  | SUB VOTE NAME: DIRECTORATE OF ELECTRIFICATION |  |  | Corporation Operational Efficiency Enhanced |  | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Corporation Operational Efficiency Enhanced | Indicator | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | C03S01 | 01 | To conduct routine inspection and maintenance of Power Supply, Catenary and Energy Infrastructure (Facilities, System and Sub-system) for SGR and MGR line by June, 2026 | Power supply, catenary and energy infrastructure maintained | Report | OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | Report | OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | To be assigned | Admin records / reports | 151 | 151 | 151
OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | C03S02 | 02 | To maintain service availability of Electrification services for MGR and SGR by June, 2026 | 100 percentage of availability of electrification services | Report | OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | Report | OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | To be assigned | Admin records / reports | 151 | 151 | 151
OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | C03S03 | 03 | To facilitate monitoring, evaluation and supervision of the project by June, 2026 | Electrification projects monitored | Report | OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | Report | OBJECTIVE DESCRIPTION: Railway Infrastructure, Rolling Stock and Safety System Improved. | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S01 | 01 | To provide conducive working environment for 186 Staffs by June, 202 | 186 staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S02 | 02 | To participate in professional, national and international meeting related to Electrification by June 2026 | 4 National and 4 international meetings attended | No. of meetings attended | Corporation Operational Efficiency Enhanced | No. of meetings attended | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S03 | 03 | To conduct short course training related to Electrification by June 2026 | 186 staffs trained | No. of staff trained | Corporation Operational Efficiency Enhanced | No. of staff trained | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  | SUB VOTE NAME: DIRECTORATE OF ROLLING STOCK |  |  | Corporation Operational Efficiency Enhanced |  | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Corporation Operational Efficiency Enhanced | Indicator | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Infrastructure, Rolling Stock and Safety System improved. | C06S01 | 01 | To conduct routine maintenance of 68 MGR locomotives, 19 SGR Electric Locomotives and 10 EMUs by June, 2026 | 97 Locomotives maintained | No. of Locomotives | Railway Infrastructure, Rolling Stock and Safety System improved. | No. of Locomotives | Railway Infrastructure, Rolling Stock and Safety System improved. | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Infrastructure, Rolling Stock and Safety System improved. | C06S02 | 02 | To conduct routine maintenance of 897 MGR and 1014 SGR Freight wagons by June 2026 | 1911 wagons maintaned | No. of wagons | Railway Infrastructure, Rolling Stock and Safety System improved. | No. of wagons | Railway Infrastructure, Rolling Stock and Safety System improved. | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Infrastructure, Rolling Stock and Safety System improved. | C06S03 | 03 | To conduct routine maintenance of 124 MGR and 89 SGR Coaches by June 2026 | 213 coaches maintained | No. of Coaches | Railway Infrastructure, Rolling Stock and Safety System improved. | No. of Coaches | Railway Infrastructure, Rolling Stock and Safety System improved. | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Infrastructure, Rolling Stock and Safety System improved. | C06S04 | 04 | To conduct routine maintenance of 125 Machinery and Equipment for both MGR and SGR by June, 2026 | 125 Machinery and Equipment maintained | No. of Machinery and Equipment | Railway Infrastructure, Rolling Stock and Safety System improved. | No. of Machinery and Equipment | Railway Infrastructure, Rolling Stock and Safety System improved. | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Infrastructure, Rolling Stock and Safety System improved. | C06S05 | 05 | To ensure availability of consumables for not less than 10,000 MGR and SGR trains by June,2026 | 100% of train consumable available | % of availability | Railway Infrastructure, Rolling Stock and Safety System improved. | % of availability | Railway Infrastructure, Rolling Stock and Safety System improved. | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Infrastructure, Rolling Stock and Safety System improved. | C06S06 | 06 | To facilitate trains crews on monitoring of trains and conducting routine handling, Inspections of rolling stocks, machines and equipment by June, 2026 | xxx inspections conducted | No. of inspection conducted | Railway Infrastructure, Rolling Stock and Safety System improved. | No. of inspection conducted | Railway Infrastructure, Rolling Stock and Safety System improved. | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency enhanced | F10S01 | 01 | To provide 730 Rolling Stock Directorate Staff with basic requirements by June, 2026 | 730 staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency enhanced | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency enhanced | F10S02 | 02 | To participate in (2) local and (1) international workshops, (2)Trainings (including refresher courses), (4) professional meetings and conferences by June, 2026 | 9 local and international trainings attended | No. of staff trained | Corporation Operational Efficiency enhanced | No. of staff trained | Corporation Operational Efficiency enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency enhanced |  |  | SUB VOTE NAME: ENVIRONMENTAL AND SOCIAL UNITY |  |  | Corporation Operational Efficiency enhanced |  | Corporation Operational Efficiency enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Corporation Operational Efficiency enhanced | Indicator | Corporation Operational Efficiency enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  | 01 | To provide conducive working environment to 56 E&S staffs by June, 2026 | 56 staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  | 02 | To participate in Regional and International meetings by June 2026 | xx Regional and xx international meetings attended | No. of meetings attended | Corporation Operational Efficiency Enhanced | No. of meetings attended | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  | 03 | To provide Internal E&S capacity building to the teams in operations | 56 staff trained | No. of staff trained | Corporation Operational Efficiency Enhanced | No. of staff trained | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced |  |  | SUB VOTE NAME: DIRECTORATE OF BUSINESS DEVELOPMENT |  |  | Corporation Operational Efficiency Enhanced |  | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Corporation Operational Efficiency Enhanced | Indicator | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D01S01 | 1 | To facilitate formation of 581 block trains for MGR and 625 block trains for SGR annually by June 2026. | 1206 block trains facilitated | No. of block trains | Railway Transport and Logistics Services Improved | No. of block trains | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D01S02 | 2 | To maintain existing customers and develop new customers' segment for MGR and SGR by June, 2026. | xxx existings customers maintained and xxx new customers developed | No. of customers | Railway Transport and Logistics Services Improved | No. of customers | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D01S03 | 3 | To conduct Joint Technical Committee meetings on improving multimodal operations that includes rail, port and marine for MGR and SGR by June, 2026. | xxx joint technical committee meetings conducted | No. of meetings | % change in cargo transported | No. of meetings | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D02S01 | 01 | To facilitate transportation of 6,665,198 passengers for MGR and for SGR by June, 2026. | 6,665,198 passengers transprted | No. of passengers transported | Changes in the number of SGR passangers transported | Changes in the number of SGR passangers transported from X (value) July, 2024/25 to Y(value) June, 2025/26 | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D02S02 | 2 | To conduct quarterly ticket inspection to passenger for MGR and SGR transportation services for MGR and SGR by June, 2026. | 4 ticket inspection conducted | No. of inspection | Railway Transport and Logistics Services Improved | No. of inspection | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D02S03 | 3 | To conduct quarterly Customer Claims Committee meetings for MGR and SGR by June 2026. | 4 customers claims committee meetings conducted | No. of meetings | Railway Transport and Logistics Services Improved | No. of meetings | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D02S04 | 4 | To coordinate and participate in the Customer Services Week exhibition by June, 2026 | Customers service week conducted | Report | Railway Transport and Logistics Services Improved | Report | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D02S05 | 5 | To facilitate and maintain TRC Call Center by June, 2026 | TRC call center facilitated and maintained | Report | Railway Transport and Logistics Services Improved | Report | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D02S06 | 6 | To conduct quarterly customer services awareness by June, 2026 | 4 customers services awareness conducted | No. of awareness | Railway Transport and Logistics Services Improved | No. of awareness | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D02S07 | 7 | To develop, review and publish TRC Customer Service Policy by June, 2026 | Customers services policy developed | Customer document inplace | Railway Transport and Logistics Services Improved | Customer document inplace | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D02S08 | 8 | To review, update and publishing TRC client service chartter by June, 2026 | Client service chartter reviwed, updated and published | Client service chartter inplace | Railway Transport and Logistics Services Improved | Client service chartter inplace | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D04S01 | 1 | To conduct quarterly stakeholders meeting for sharing current business opportunities for MGR and SGR by June 2026. | 4 stakeholders meeting conducted | No. of meetings | Railway Transport and Logistics Services Improved | No. of meetings | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D04S02 | 2 | To facilitate review of tariff book and other pricing manuals for MGR and SGR by June, 2026. | Tarriff and price manual reviewed | Tarriff and price manual inplace | Railway Transport and Logistics Services Improved | Tarriff and price manual inplace | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D04S05 | 3 | To conduct quarterly promotional activities for TRC business for MGR and SGR by June,2026. | 4 promotion activities conducted | No. of promotion | Railway Transport and Logistics Services Improved | No. of promotion | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D05S01 | 1 | To facilitate implementation and evaluation of the business plan 2022/23 - 2024/25 by June, 2026 | Business plan reviewed and implemented | Business plan document in place | Railway Transport and Logistics Services Improved | Business plan document in place | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D05S02 | 2 | To develop a new business plan (for 2025/26–2027/28) by June 2026. | Business plan developed | Business plan document in place | Railway Transport and Logistics Services Improved | Business plan document in place | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced | F11S01 | 1 | To provide conduncive working environment to 188 staff by June 2026. | 188 staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Capacity of the corporation to discharge its mandates enhanced | % of satisfaction of conducive working envoronment | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced | F11S02 | 2 | To facilitate training for Business Development staff for MGR and SGR by June, 2026. | 188 staff facilitate to attend proffessional training | No. of staff trained | Capacity of the corporation to discharge its mandates enhanced | No. of staff trained | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced |  |  | SUB VOTE NAME: ESTATE MANAGEMENT UNIT |  |  | Capacity of the corporation to discharge its mandates enhanced |  | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Capacity of the corporation to discharge its mandates enhanced | Indicator | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D07S01 | 1 | To pay statutory land fees for TRC buildings by June 2026. | Statutory land fees paid | Payment report | Railway Transport and Logistics Services Improved | Payment report | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D07S02 | 2 | To conduct quarterly physical inspection and verification of assets and properties for MGR and SGR by June, 2026. | 4 physical inspection and verification of asset and properties conducted | Report | Railway Transport and Logistics Services Improved | Report | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D07S03 | 03 | To oversee and verify tenants compliance to leasing contracts for MGR and SGR by June, 2026. | XX leasing contracts verified | No.of contracts | Railway Transport and Logistics Services Improved | No.of contracts | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D07S04 | 4 | To facilitate new potential corporate tenants for leasing and investment opportunities by June, 2026. | xx corporate tenants facilitated | No.of tenants | Railway Transport and Logistics Services Improved | No.of tenants | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D07S05 | 5 | To manage the SGR Phase 1 Lot 1 Property and facilities(DSM, Pugu, Soga, Ruvu, Ngerengere & Morogoro stations) by June, 2026 | XX properties and facilities managed | No .of facilities and properties managed | Railway Transport and Logistics Services Improved | No .of facilities and properties managed | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D07S06 | 6 | To Manage the SGR Phase 1 Lot 2 property and facilities (Dodoma, Kilosa, Mkata, Kidete, Gulwe, Igandu, Bahi, and Makutupora stations) by June 2026. | XX properties and facilities managed | No .of facilities and properties managed | Railway Transport and Logistics Services Improved | No .of facilities and properties managed | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D07S07 | 7 | To Conduct feasibility studies for Real Estate investment opportunities and evaluate their potential risks and returns by June 2026. | xxx Feasibility studies for real estate investment conducted | No. of feasibility studies | Railway Transport and Logistics Services Improved | No. of feasibility studies | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | D07S08 | 8 | To Prepare and Implement Estate Management Policies by June 2026. | xxx Estate management policies prepared | No.of Policies prepared | Railway Transport and Logistics Services Improved | No.of Policies prepared | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced | F11S01 | 01 | To provide conducive working environment to 45 staff by June 2026. | 45 staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Capacity of the corporation to discharge its mandates enhanced | % of satisfaction of conducive working envoronment | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced | F11S02 | 2 | To facilitate training for Estate Management Unit staff for MGR and SGR by June, 2026. | 45 staff trained | No.of staffs trained | Capacity of the corporation to discharge its mandates enhanced | No.of staffs trained | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced | F11S03 | 3 | To facilitate 45 staff to attend Professional Bodies and Annual General Meetings for MGR and SGR by June, 2026. | 45 staff attended profesional meetings | No.of staffs trained | Capacity of the corporation to discharge its mandates enhanced | No.of staffs trained | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced |  |  | SUB VOTE NAME: DIRECTORATE OF OPERATIONS |  |  | Capacity of the corporation to discharge its mandates enhanced |  | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Capacity of the corporation to discharge its mandates enhanced | Target code | MTEF Activity Code | MTEF Activity | Output (Lower level Result) | Indicator | Capacity of the corporation to discharge its mandates enhanced | Indicator | Capacity of the corporation to discharge its mandates enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | E01S01 | 01 | To facilitate daily Freight trains operation activities by June,2026 | Daily logistic of freight efficiency improved | No.of freight train operated | Railway Transport and Logistics Services Improved | No.of freight train operated | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | E01S02 | 02 | To review and develop traffic Operating Manuals by June, 2026 | Traffic Operating Manuals developed and reviewed | No. of Traffic Operating Manuals developed and reviewed | Railway Transport and Logistics Services Improved | No. of Traffic Operating Manuals developed and reviewed | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | E01S03 | 03 | To facilitate clearence of Accidents and incidents by June, 2026 | Minimazation of accidents | No. of accidents and incidents | Railway Transport and Logistics Services Improved | No. of accidents and incidents | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | E01S04 | 04 | To facilitate and monitoring operations of electronic cargo management system and update wagon database by June, 2026 | Electronic cargo management system and wagon databese enhanced and updated | System in place | Railway Transport and Logistics Services Improved | System in place | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | E01S05 | 05 | To facilitate maintenace and verification of weight scale by June,2026 | Accurate measurement reading ensured | No. of loads measured | Railway Transport and Logistics Services Improved | No. of loads measured | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | E02S01 | 01 | To facilitate daily Passenger trains operation activities by June,2026 | Daily logistic of passangers efficiency improved | No. of passangers transported | Railway Transport and Logistics Services Improved | No. of passangers transported | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | E02S02 | 02 | To Carry out traffic inspection and daily monitoring of trains, stations and customers experience by June, 2026 | Daily trains and stations inspection conducted | No of inspections conducted | Railway Transport and Logistics Services Improved | No of inspections conducted | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved | E02S03 | 03 | To conduct staff Familiarization and sensitization for train operations involving MGR and SGR critical staff by June, 2026 | Staff awareness on train operations improved | No of staffs engaged in train operation | Railway Transport and Logistics Services Improved | No of staffs engaged in train operation | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Railway Transport and Logistics Services Improved |  | 01 | To provide working and protection tools for daily trains movement by June, 2026 | Safety of employee in work place enhanced | No of staffs with working and protection tools | Railway Transport and Logistics Services Improved | No of staffs with working and protection tools | Railway Transport and Logistics Services Improved | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S01 | 01 | To provide conducive working environment to operation staff by June, 2026 | xxx staff satisfied with 100% conducive working environment | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | % of satisfaction of conducive working envoronment | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151
Corporation Operational Efficiency Enhanced | F10S02 | 02 | To facilitate operation staff to attend local and international training/workshop by June, 2026 | xxx staff participated in local and international proffessional attended | No. of staff trained | Corporation Operational Efficiency Enhanced | No. of staff trained | Corporation Operational Efficiency Enhanced | To be assigned | Admin records / reports | 151 | 151 | 151

## 04 Evaluation Workplan
Evaluation Workplan
Appendix 3 revised into a proper evaluation work plan with key questions, timeline, lead users and products
Eval ID | Evaluation Study | Type | Background / Rationale | Purpose | Key Evaluation Questions | Methods | Start Date | End Date | Lead Unit | Primary Users | Main Product | Status | Decision Use | Comments / Gaps
EV-01 | Evaluation of the Standard Gauge Railway (SGR): One Year of Operations | Mid-term Evaluation | The Tanzania Railway Corporation (TRC) made a bold step towards modernizing the country’s transport system by introducing the Standard Gauge Railway (SGR), replacing the older Meter Gauge Railway (MGR). This transformation supports Tanzania’s long-term vision for economic growth, improved infrastructure, and enhanced service delivery in the transport sector. The first phase of the SGR, connecting Dar es Salaam to Dodoma, began operations in August 2024. This route has brought about notable improvements, including: •Reduction in travel time from 8 hours to 5 hours for the Dodoma Route and from 4 hours to 1 and Half hour for the route of Dar es Salaam to Morogoro; •Improved safety, comfort, and convenience for passengers; and •Increased interest and high uptake by the public. However, this success has also come with challenges. High passenger demand, especially on weekends, has led to ticket shortages and pressure on operational planning. Now, after one full year of operations, it is important to evaluate the performance and impact of the SGR system to assess what has worked, what needs improvement, and what strategies are needed to ensure long-term sustainability. | The purpose of this evaluation is to: •Quantify and measure achievements after one year of SGR operations •Identify operational and financial challenges •Understand the social and economic impact of the SGR on communities and passengers •Provide evidence-based recommendations for improvement •Inform future expansion and sustainability plans | 1. To what extent has SGR improved service efficiency, safety and customer experience? 2. What operational and financial constraints affect sustainability? 3. What improvements are required for expansion and long-term performance? | •Desk Review of TRC reports, contracts, financial records, and past evaluations (If any) •Passenger Surveys across different classes and routes to assess satisfaction and suggestions •Key Informant Interviews (KIIs) with TRC management, station masters, and staff work direct to SGR •Focus Group Discussions (FGDs) with workers of TRC and cleaners working at SGR •Site Observations at stations to assess infrastructure usage and condition •Stakeholder Engagement Lab: A facilitated stakeholder meeting or workshop to gather feedback from all key actors (TRC, regulators, vendors, civil society, etc.) on expectations vs. reality •Cost Center Analysis: Review of financial allocations and performance of key operational areas | 2025-07-01 | August, 2025 | M&E Unit | TRC Management; M&E Unit; Directorate Heads | Evaluation report, management brief and action matrix | Planned | Management decision / learning / next-cycle planning | 151
EV-02 | End Term Evalution of TRC Strategic Plan (2020/21 - 2024/25) | End Term Evaluation | The primary goal of this evaluation was to examine the implementation and efficacy of the Tanzania Railways Corporation (TRC) Strategic Plan for the years 2020/21 to 2024/25. The review sought to establish how well the strategic objectives were met, identify areas of success and failure, and make recommendations for future strategic planning. The evaluation used a mixed-approaches approach, which included both qualitative and quantitative data collection methods. Key informant interviews, focus group talks, and surveys with technical and support personnel, customers, and passengers were carried out. In addition, document evaluations and Key Performance Indicator (KPI) analysis were conducted to provide a full understanding of the strategic plan's implementation. The study indicated that TRC achieved great progress in various areas, particularly in growing its passenger market share following the implementation of the Standard Gauge Railway (SGR). However, problems such as antiquated infrastructure, insufficient locomotives, and delays in procurement procedures hampered the full realisation of strategic objectives. Most technical workers assessed the efficiency of safety protocols as fair to bad, and the training provided was regarded insufficient to meet the demands of changing railway operations. Customers and passengers expressed a desire for greater customer service, infrastructure, and time management. The study found various problems throughout the strategic plan's implementation, including insufficient money, out-of-date infrastructure, lengthy procurement processes, and external influences such as the COVID-19 pandemic and natural disasters like flooding. These challenges have an impact on the timely fulfilment of strategic objectives as well as the overall efficiency of TRC operations. Key takeaways include the importance of matching KPIs with realistic and attainable targets, the requirement for proper budget and resources, and the importance of ongoing training and skill development for TRC staff. Furthermore, input from passengers and customers underlined the need for TRC to take a more customer-centric approach, as well as increase communication and interaction with stakeholders. The study indicated that, while TRC has made success in some areas, considerable changes are required to fully realise the strategic plan's objectives. Addressing the identified difficulties and using the lessons learnt will be critical to TRC's future success. The recommendations will serve as a guide for TRC's next phase of strategic planning, ensuring that it remains competitive and responsive to the demands of its clients and stakeholders. | To examine the impact of the corporation in the course for five years To ensure how the Corporation can design the new cycle of Strategic Plan | 1. To what extent were strategic objectives and KPIs achieved? 2. What factors enabled or constrained delivery? 3. What should be carried forward into the next planning cycle? | •Desk Review of TRC reports, contracts, financial records, and past evaluations (If any) •Passenger Surveys across different classes and routes to assess satisfaction and suggestions •Key Informant Interviews (KIIs) with TRC management, station masters, and staff work direct to SGR •Focus Group Discussions (FGDs) with workers of TRC and cleaners working at SGR •Site Observations at stations to assess infrastructure usage and condition •Stakeholder Engagement Lab: A facilitated stakeholder meeting or workshop to gather feedback from all key actors (TRC, regulators, vendors, civil society, etc.) on expectations vs. reality •Cost Center Analysis: Review of financial allocations and performance of key operational areas | August, 2025 | October, 2025 | M&E Unit | TRC Management; M&E Unit; Directorate Heads | Evaluation report, management brief and action matrix | Planned | Management decision / learning / next-cycle planning | 151
EV-03 | End Term evaluation of the Business Plan 2022/23 - 2024/25 | End Term Evaluation |  |  | 1. Were planned outputs and outcomes achieved? 2. What implementation lessons should inform future planning? 3. What management actions are recommended? |  |  |  | M&E Unit | TRC Management; M&E Unit; Directorate Heads | Evaluation report, management brief and action matrix | Planned | Management decision / learning / next-cycle planning | 151

## 05 Version Control
Official Workbook Governance
Official version for FY2025/26 monitoring and evaluation use
Field | Value | Owner | Review Date | Comment | Action
Official Version ID | FY2025-26 v1.0 (Cleaned & Structured) | M&E Unit | 2026-03-25 | Use this workbook as the official planning and monitoring file. | Controlled updates only
Source File | MONITORING PLAN-2025-26 (2).xlsx | M&E Unit | 151 | Legacy workbook retained as source only. | Do not use source workbook for live reporting
Workbook Scope | Dashboard, corporate matrix, activity/input register, evaluation workplan | M&E Unit | 151 |  | Confirmed
Revision Rule | Update actuals monthly; revise targets only by management approval | Director of Planning / M&E | 151 | One official live version to be maintained. | Confirmed
Data Quality Rule | Every indicator must have source, owner, frequency and verification method | All directorates | 151 | Blank metadata is a data-quality gap. | Action required

## 06 Lookups
Reference Lists / Lookups
Used for drop-downs and workbook governance
List Name | Value 1 | Value 2 | Value 3 | Value 4 | Value 5
Status | On Track | Off Track | Not Reported | Complete | Data Gap
Risk Level | High | Medium | Low | 151 | 151
Frequency | Monthly | Quarterly | Semi-Annual | Annual | Ad hoc
Verification | Report | MIS/Dashboard | Inspection | Survey/FGD | Admin Records
Lead Unit | M&E Unit | Finance | Operations | Engineering | Procurement

## 07 Jan2026 Import Log
January 2026 Tracking Import Log
Matrix Row | Indicator | Imported Actual (Source) | Stored in Actual Jan | Comment
5 | No. of km speed restriction reduced | 15.5km | 15.5 | Imported from January 2026 tracking file
6 | % of curves/gradient realigned/relocated | 0.6km | 0.6 | Imported from January 2026 tracking file
7 | No. of rail km joined | 1.6km | 1.6 | Imported from January 2026 tracking file
8 | No of km relayed | 1.7km | 1.7 | Imported from January 2026 tracking file
9 | No. of km ballasted | 0km | 0 | Imported from January 2026 tracking file
10 | No. of sidings established | The work completed |  | Imported from January 2026 tracking file
11 | No. of Km of railway line rehabilitated | 0km | 0 | Imported from January 2026 tracking file
12 | % of works completed | 0.1 | 0.1 | Imported from January 2026 tracking file
13 | No. of km of speed restriction | 98.0km | 98 | Imported from January 2026 tracking file
14 | No. of Locomotives available for operations | 18 | 18 | Imported from January 2026 tracking file
15 | Mean Kilometers Before Failure | 6960 | 6960 | Imported from January 2026 tracking file
16 | No. of coaches available | 97 | 97 | Imported from January 2026 tracking file
17 | % of wagons available | 870 | 870 | Imported from January 2026 tracking file
18 | No. of wagons roll out for operation | 0 | 0 | Imported from January 2026 tracking file
19 | No. of wagons delivered | 50 | 50 | Imported from January 2026 tracking file
20 | No. of Locomotive | 2 | 2 | Imported from January 2026 tracking file
21 | Unqualified opinion | The audit for the finacial year 2024/25 completed and report submitted to the office of controller and Auditor General for review. | 2024 | Imported from January 2026 tracking file
22 | Advisory Audit consultant in place | Tax Audit consultant is in place |  | Imported from January 2026 tracking file
23 | Financial Management Report | Second quarter finanacial management report were prepared |  | Imported from January 2026 tracking file
24 | Financial Management Report | Financial statement for the Financial year 2024/25 prepared and submitted to the office of Controller and Auditor General | 2024 | Imported from January 2026 tracking file
25 | Tshs. Collected | NIL | 0 | Imported from January 2026 tracking file
26 | Tshs. Settled | None |  | Imported from January 2026 tracking file
27 | Tshs. Collected | 11131111301.09 | 11131111301.09 | Imported from January 2026 tracking file
28 | Report | The audit engagment was not performed. Instead the Audit team perfomed Revenue collections Audit on MGR - Freight and the audit work is at 100% | 100 | Imported from January 2026 tracking file
29 | No. Metric tons transported | 15451 | 15451 | Imported from January 2026 tracking file
30 | Ton-km | 2517291 | 2517291 | Imported from January 2026 tracking file
31 | No. Metric tons transported | 8625 | 8625 | Imported from January 2026 tracking file
32 | Ton-km | 991875 | 991875 | Imported from January 2026 tracking file
33 | No. of passengers transported | 18341 | 18341 | Imported from January 2026 tracking file
34 | Pax-km | 8542160 | 8542160 | Imported from January 2026 tracking file
35 | No. of passengers transported | 271642 | 271642 | Imported from January 2026 tracking file
36 | Pax-km | 82935299 | 82935299 | Imported from January 2026 tracking file
37 | No. of passengers transported | 110759 | 110759 | Imported from January 2026 tracking file
38 | No. of plots demarcated | Demarcation was not done |  | Imported from January 2026 tracking file
39 | Tshs. Collected | 288822345 | 288822345 | Imported from January 2026 tracking file
40 | % commercial space leased at DSM station | 0.84 | 0.84 | Imported from January 2026 tracking file
41 | % commercial space leased at Morogoro station | 0.95 | 0.95 | Imported from January 2026 tracking file
42 | % commercial space leased at Kilosa station | 0 | 0 | Imported from January 2026 tracking file
43 | % commercial space leased at Dodoma station | 0.67 | 0.67 | Imported from January 2026 tracking file
44 | No. of feasibility studies conducted | Procurement of a consultant to carry out feasibility study for six land parcel/plots is ongoing |  | Imported from January 2026 tracking file
45 | Amount paid | 182435000 | 182435000 | Imported from January 2026 tracking file
46 | No. of incidence/ faults recorded | A total of 12 Signal failures, 3 point-machine failures and 1 derailer were detected with zero false occupation and wheel detector | 12 | Imported from January 2026 tracking file
47 | Incidence Recovery time | The average failure time were 1: 49 | 1 | Imported from January 2026 tracking file
48 | No. of incidence recorded (MGR) | 12 | 12 | Imported from January 2026 tracking file
49 | No. of accident recorded(MGR) | 4 | 4 | Imported from January 2026 tracking file
50 | No. of trainings provided (MGR) | 0 | 0 | Imported from January 2026 tracking file
51 | No. of incidence recorded(SGR) | 16 | 16 | Imported from January 2026 tracking file
52 | No. of accident recorded (SGR) | 4 | 4 | Imported from January 2026 tracking file
53 | No. of trainings provided (SGR) | 1 | 1 | Imported from January 2026 tracking file
54 | Working timetable | Working timetable was nof fully adhered |  | Imported from January 2026 tracking file
55 | Wagon turnround time | 0 | 0 | Imported from January 2026 tracking file
56 | No. of block trains run | 7 | 7 | Imported from January 2026 tracking file
57 | No. of block trains run | 14 | 14 | Imported from January 2026 tracking file
58 | No. of cases finalized | 0 | 0 | Imported from January 2026 tracking file
59 | No. of days | 21 | 21 | Imported from January 2026 tracking file
60 | No. of days | 7 | 7 | Imported from January 2026 tracking file
61 | No. of agreements/ Contracts/MoU reviewed | 136 - employment contracts; 5 - MoUs vetted. | 136 | Imported from January 2026 tracking file
62 | No of meetings | 0 | 0 | Imported from January 2026 tracking file
63 | Tsh. collected | 153.34bil | 153.34 | Imported from January 2026 tracking file
64 | Report | One media coverage was done, and 30 social media content were prepared. | 30 | Imported from January 2026 tracking file
65 | No. of student enrolled | 689 | 689 | Imported from January 2026 tracking file
66 | No of trainings | None |  | Imported from January 2026 tracking file
67 | No. of PPP F.S prepared | 1. Review of the feasibility study for Dar es salaam Commutter Railway through PPP is underway 2. Feasibility Study for Railway line linking the SGR with Airports is underway | 1 | Imported from January 2026 tracking file
68 | No. of document reviewed | Terms of Reference for engagement of the consultant to prepare the policies were reviewed. |  | Imported from January 2026 tracking file
69 | Strategic plan Document | The tender to procure consultant for preparation of Corporate Strategic Plan was opened on 27th November, 2026. The evaluation is ongoing | 27 | Imported from January 2026 tracking file
70 | Railway master plan Document | The preparation of the Terms of Reference (ToR) was finalised and it is in the final stages of tendering. |  | Imported from January 2026 tracking file
71 | Business transformation strategy Document | Review of draft business transformation strategy report completed, the inputs were incorporated and submitted to the Consultant.Currently awaiting for consultant presentation of the report. |  | Imported from January 2026 tracking file
72 | No. of staff recruited | Recruitment approval has been sought from the Permanent Secretary (Establishment ), Follow-ups are being made, however the recruitment permit has not been granted. |  | Imported from January 2026 tracking file
73 | No. of staff oriented | Orientation was conducted to 65 cabin crew | 65 | Imported from January 2026 tracking file
74 | No. of staff vetted | Vetting was conducted to 65 Cabin Crew | 65 | Imported from January 2026 tracking file
75 | 5 Documents prepared (TNA, Training program, Training Policy, Training Evaluation & Training Reports) | Draft Training Policy has been prepared and submitted to the management for their input.and Procurement of Consultant for Training need assesmnet is ongoing under World Bank procedures. |  | Imported from January 2026 tracking file
76 | No. of staff trained | Training on Environmental, Social and Good Governamce ESG for 45 staffs were coducted. | 45 | Imported from January 2026 tracking file
77 | No. of policy document prepared | During the period, draft of staff training policy and internship guidelines was presented to Management meeting for approval before submission to the Board. |  | Imported from January 2026 tracking file
78 | No. of running rooms furnished | Running staff are now staying at the leased Hotel/Lodge. |  | Imported from January 2026 tracking file
79 | Cargo system | Upgrade of the system is ongoing and has reached 80%. The work is expected to be completed at the end of February, 2026 | 80 | Imported from January 2026 tracking file
80 | e-ticketing- Reporting | User requirement have been collected, The implementation is planned to starts from February |  | Imported from January 2026 tracking file
81 | Upgrade ERP system | Terms of reference for engaging consultant was prepared. |  | Imported from January 2026 tracking file
82 | Land and Property Management System | The system requirements were reviewed and preparation of the first draft Software Requirements Specification (SRS) were done |  | Imported from January 2026 tracking file
83 | Maintainance system | Maintenance System has been planned to be moduled in ERP |  | Imported from January 2026 tracking file
84 | Help desk system | Completed |  | Imported from January 2026 tracking file
85 | Overtime system | Gathering of system requirement completed and submitted to Ega for incorporation in the ERMS |  | Imported from January 2026 tracking file
86 | Report | Implementation of procurement Plan is ongoing |  | Imported from January 2026 tracking file
87 | No. of contract awarded | Five(5) procurement contracts were signed | 5 | Imported from January 2026 tracking file
88 | 120 days International competitive tendering | Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time |  | Imported from January 2026 tracking file
89 | 90 days national competitive tendering | Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time |  | Imported from January 2026 tracking file
90 | 90 days Restricted national competitive tendering | Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time |  | Imported from January 2026 tracking file
91 | 60 days international shopping | Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time |  | Imported from January 2026 tracking file
92 | 45 days national shopping | Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time |  | Imported from January 2026 tracking file
93 | 45 days minor value procurement | Most of the works and consultancy tenders were opened beyond the time frame while goods tenders were within the time |  | Imported from January 2026 tracking file
94 | User departments (US) and Tender Board members | No training conducted |  | Imported from January 2026 tracking file
95 | PMU staff | No training conducted |  | Imported from January 2026 tracking file
Unmatched / needs review

## 08 KPI Rationalization
KPI Rationalization Aligned to the Main Monitoring Plan | KPI Rationalization Aligned to the Main Monitoring Plan | KPI Rationalization Aligned to the Main Monitoring Plan | KPI Rationalization Aligned to the Main Monitoring Plan | KPI Rationalization Aligned to the Main Monitoring Plan | KPI Rationalization Aligned to the Main Monitoring Plan | KPI Rationalization Aligned to the Main Monitoring Plan | KPI Rationalization Aligned to the Main Monitoring Plan | KPI Rationalization Aligned to the Main Monitoring Plan | KPI Rationalization Aligned to the Main Monitoring Plan | KPI Rationalization Aligned to the Main Monitoring Plan | KPI Rationalization Aligned to the Main Monitoring Plan
This sheet mirrors the KPI prioritization inserted into the Corporate M&E Matrix and supports dashboard/report structuring. | This sheet mirrors the KPI prioritization inserted into the Corporate M&E Matrix and supports dashboard/report structuring. | This sheet mirrors the KPI prioritization inserted into the Corporate M&E Matrix and supports dashboard/report structuring. | This sheet mirrors the KPI prioritization inserted into the Corporate M&E Matrix and supports dashboard/report structuring. | This sheet mirrors the KPI prioritization inserted into the Corporate M&E Matrix and supports dashboard/report structuring. | This sheet mirrors the KPI prioritization inserted into the Corporate M&E Matrix and supports dashboard/report structuring. | This sheet mirrors the KPI prioritization inserted into the Corporate M&E Matrix and supports dashboard/report structuring. | This sheet mirrors the KPI prioritization inserted into the Corporate M&E Matrix and supports dashboard/report structuring. | This sheet mirrors the KPI prioritization inserted into the Corporate M&E Matrix and supports dashboard/report structuring. | This sheet mirrors the KPI prioritization inserted into the Corporate M&E Matrix and supports dashboard/report structuring. | This sheet mirrors the KPI prioritization inserted into the Corporate M&E Matrix and supports dashboard/report structuring. | This sheet mirrors the KPI prioritization inserted into the Corporate M&E Matrix and supports dashboard/report structuring.
KPI ID | Source Matrix Row | Objective | Target Description | Output / Lower-Level Result | Indicator | FY Target | Unit | KPI Tier | Dashboard Inclusion | Reporting Placement | Tier Rationale
KPI-001 | 5 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | Speed restrictions reduced from 63 km to 10km ( DSM-DOM, DOM-TBR, RUVU JNCT-TANGA PORT) by June, 2026 | Increase operation efficiency | No. of km speed restriction reduced | 15 | Km | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-002 | 6 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 50% of speed along MGR alignment upgraded by June, 2026 | Increase operation efficiency | % of curves/gradient realigned/relocated | 0.1 | Percent | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-003 | 7 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 50% of speed along MGR alignment upgraded by June, 2026 | Increase operation efficiency | No. of rail km joined |  | Km | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-004 | 8 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 50% of speed along MGR alignment upgraded by June, 2026 | Increase operation efficiency | No of km relayed |  | Km | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-005 | 9 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 80 km of railway line ballasted ( Kidomole-Tanga port, Godegode section, Gulwe diversion) by June, 2026 | Increase operation efficiency | No. of km ballasted | 24 | Km | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-006 | 10 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | Establishment of llala-SGR siding by June, 2026 | Increase operation efficiency | No. of sidings established | Ilala siding completed | Count | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-007 | 11 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 100 km of railway line (Kaliua-Mpanda , Godegode section & Tanga port) rehabilitated by June, 2026 | Increase operation efficiency | No. of Km of railway line rehabilitated | 10 | Km | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-008 | 12 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 100% of 25 operational buildings rehabilitated by June, 2026 | Increase operation efficiency | % of works completed | 1 | Percent | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-009 | 13 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 722km of SGR railway line maintained by June, 2026 | Increase operation efficiency | No. of km of speed restriction | 722 | Km | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-010 | 14 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 80% of 45 locomotives available by June, 2026 | Increase operation efficiency | No. of Locomotives available for operations | 36 | Count | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-011 | 15 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 95% of locomotive realibility ensured by June, 2026 | Increase operation efficiency | Mean Kilometers Before Failure | 19000 | Units / To confirm | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-012 | 16 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 80% of 83 MGR coaches available by June, 2026 | Increase operation efficiency | No. of coaches available | 83 | Count | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-013 | 17 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 80% of 883 MGR wagons available by June, 2026 | Increase operation efficiency | % of wagons available | 1046 | Percent | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-014 | 18 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 180 MGR wagons rehabilitated and roll out for operation by June, 2026 | Increase operation efficiency | No. of wagons roll out for operation | 20 | Count | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-015 | 19 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 50 MGR wagons to be delivered by June, 2026 | Increase operation efficiency | No. of wagons delivered | 50 | Count | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-016 | 20 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | 8 new MGR locomotives to be delivered by June, 2026 | Increase operation efficiency | No. of Locomotive | 4 | Count | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-017 | 21 | FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | 2024/25 Corporation unqualified opinion secured by June, 2026 | Increase operation efficiency | Unqualified opinion | Report | Units / To confirm | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-018 | 22 | FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | 2024/25 Corporation unqualified opinion secured by June, 2026 | Increase operation efficiency | Advisory Audit consultant in place |  | Units / To confirm | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-019 | 23 | FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | Quarterly financial management report prepared by June, 2026 | Increase cost management efficiency | Financial Management Report | 1 | Units / To confirm | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-020 | 24 | FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | Audited Financial report prepared and published annually by June, 2026 | Increase cost management efficiency | Financial Management Report |  | Units / To confirm | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-021 | 25 | FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | 70% of Tshs.8,455,960,658.12 debt collected by June, 2026 | Increase revenue collection | Tshs. Collected | 493264371.72 | TZS | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-022 | 26 | FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | 50% of Tshs.19,414,385,689 service provider outstanding debt settled by June, 2026 | Increase operation efficiency | Tshs. Settled | 808932737.04 | TZS | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-023 | 27 | FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | Tshs. 265,372,951,248 of internal revenue collected by June, 2026 | 304601604627.7 | Tshs. Collected | 24068445412.9703 | TZS | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-024 | 28 | FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | Monthly Corporation audited report prepared by June, 2026 | Increase operation efficiency | Report | IT Systems Audit (MGR & SGR) | Units / To confirm | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-025 | 29 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 810,000 metric tons (MGR) to be transported by June, 2026 | 810,000 metric tons transported | No. Metric tons transported | 79766.9671 | Count | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-026 | 30 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 710,889,286 ton-km (MGR) to be covered by June, 2026 | Increase operational efficiency | Ton-km | 76499308.5802 | Km | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-027 | 31 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 500,000 metric tons (SGR) to be transported by June, 2026 | 500,000 metrics tons transported | No. Metric tons transported | 41666.6667 | Count | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-028 | 32 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 224,500,000 ton-km (SGR) to be covered by June, 2026 | Increase operational efficiency | Ton-km | 224500000 | Km | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-029 | 33 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 552,038 Mainline Passengers (MGR) to be transported by June, 2026. | 552,038 mainline passengers transported | No. of passengers transported | 63473.7068 | Count | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-030 | 34 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 406,873,140 pax-km (MGR) to be covered by June, 20226 | Increase operational efficiency | Pax-km | 45856211.1756 | Km | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-031 | 35 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 3,046,320 Mainline Passengers (SGR) to be transported by June, 2026. | 3,046,320 SGR passengers transported | No. of passengers transported | 281559.7776 | Count | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-032 | 36 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 940,380,365 pax-km (SGR) to be covered by June, 20226 | Increase operational efficiency | Pax-km | 87518313.9797 | Km | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-033 | 37 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 3,067,200 commuter passengers to be transported by June, 2026. | 3,067,200 commuter passengers transported | No. of passengers transported | 306684.1031 | Count | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-034 | 38 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 58 Surveyed plots demarcated by June, 2026 | Increase operational efficiency | No. of plots demarcated | 16 | Count | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-035 | 39 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Tshs. 3,607,911,882 revenue to be collected from leased tenants by June, 2026 | Increase revenue collection | Tshs. Collected | 386.34 | TZS | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-036 | 40 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 95% commercial area to be leased for SGR stations by June, 2026 | Increase revenue collection | % commercial space leased at DSM station | 0.89 | Percent | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-037 | 41 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 95% commercial area to be leased for SGR stations by June, 2026 | Increase revenue collection | % commercial space leased at Morogoro station | 0.9 | Percent | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-038 | 42 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 95% commercial area to be leased for SGR stations by June, 2026 | Increase revenue collection | % commercial space leased at Kilosa station | 0.63 | Percent | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-039 | 43 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 95% commercial area to be leased for SGR stations by June, 2026 | Increase revenue collection | % commercial space leased at Dodoma station | 0.87 | Percent | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-040 | 44 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | 4 feasibility studies for Real Estate investment opportunities conducted and evaluate their potential risks and returns by June 2026. | Increase revenue collection | No. of feasibility studies conducted | 4 | Count | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-041 | 45 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | To collect 1,898,000,000 parking revenue from parking fee by June, 2026 | Parking fee collected | Amount paid | 158166667 | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-042 | 46 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Availability of Electrification, signaling and telecommunication services ensured by June, 2026 | Increase operational efficiency | No. of incidence/ faults recorded | 0 | Count | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-043 | 47 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Availability of Electrification, signaling and telecommunication services ensured by June, 2026 | Increase operational efficiency | Incidence Recovery time | 2 | Units / To confirm | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-044 | 48 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Safety and security of railway infrastructure and operation ensured by June, 2026 | Increase operational efficiency | No. of incidence recorded (MGR) | 0 | Count | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-045 | 49 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Safety and security of railway infrastructure and operation ensured by June, 2026 | Increase operational efficiency | No. of accident recorded(MGR) | 0 | Count | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-046 | 50 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Safety and security of railway infrastructure and operation ensured by June, 2026 | Increase operational efficiency | No. of trainings provided (MGR) | 1 | Count | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-047 | 51 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Safety and security of railway infrastructure and operation ensured by June, 2026 | Increase operational efficiency | No. of incidence recorded(SGR) | 0 | Count | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-048 | 52 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Safety and security of railway infrastructure and operation ensured by June, 2026 | Increase operational efficiency | No. of accident recorded (SGR) | 0 | Count | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-049 | 53 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Safety and security of railway infrastructure and operation ensured by June, 2026 | Increase operational efficiency | No. of trainings provided (SGR) | 1 | Count | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-050 | 54 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Punctuality on trains operation ensured by June, 2026 | Increase operational efficiency | Working timetable | Adhered | Units / To confirm | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-051 | 55 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Punctuality on trains operation ensured by June, 2026 | Increase operational efficiency | Wagon turnround time | 14 | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-052 | 56 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Transportation of 810,000 metric tons (MGR) ensured by June, 2026 | Revenue realized and increase operational efficiency | No. of block trains run | 79766.9671 | Count | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-053 | 57 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Transportation of 500,000 metric tons (SGR) ensured by June, 2026 | Revenue realized and increase operational efficiency | No. of block trains run | 41666.6667 | Count | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-054 | 58 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 16 cases finalized by June, 2026 | Increase operational efficiency | No. of cases finalized | 4 | Count | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-055 | 59 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Contract worth above TZS One Billion to be vetted within 21 days | Increase operational efficiency | No. of days | 21 | Count | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-056 | 60 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Agreements and/or Contract worth below TZS One Billion to be vetted within 7 days | Increase operational efficiency | No. of days | 7 | Count | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-057 | 61 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Agreements, Contract and MoU reviewed monthly by June, 2026 | Increase operational efficiency | No. of agreements/ Contracts/MoU reviewed | 7 | Count | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-058 | 62 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | To coordinate quarterly Board Meeting by June, 2026 | Increase operational efficiency | No of meetings | 4 | Count | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-059 | 63 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Tshs. 1.857,082,670,000 mobilized for development projects by June 2026 | Increase operational efficiency | Tsh. collected | 180.7 | Units / To confirm | Critical | Yes | Executive Dashboard | Directly drives executive decisions on safety, service delivery, revenue, or strategic assurance.
KPI-060 | 64 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | To brand corporation image by June, 2026 | Increase operational efficiency | Report | Brand visibility and identinty, brand communication, brand experience and activation and Internal branding | Units / To confirm | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-061 | 65 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 700 students enrolled by June, 2026 | Increase TIRTEC efficiency | No. of student enrolled | 700 | Count | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-062 | 66 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Refreshers course training provided to staff by June, 2026 | Increase staff efficiency | No of trainings | 50 | Count | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-063 | 67 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 2 PPP feasibility study prepared by June, 2026 | Increase operational efficiency | No. of PPP F.S prepared | Mtwara and DSM commuter investor secured | Count | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-064 | 68 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Two policies (Investment plan and Policy) reviewed by June, 2026 | Increase operational efficiency | No. of document reviewed | Review of policies (Investment Plan and policies) completed | Count | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-065 | 69 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Corporate Strategic Plan prepared by June, 2026 | Increase operational efficiency | Strategic plan Document | Strategic plan Document in place | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-066 | 70 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Railway master plan prepared by June, 2026 | Increase operational efficiency | Railway master plan Document | Ongoing | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-067 | 71 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Business transformation strategy prepared and approved by June, 2026 | Increase operational efficiency | Business transformation strategy Document | Business Transformation Report in Place | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-068 | 72 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 279 staffs recruited by June, 2026 | Increase staff capacity and efficiency | No. of staff recruited | 279 | Count | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-069 | 73 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 279 staff oriented and 432 staff vetted by June, 2026 | Increase staff efficiency | No. of staff oriented | 279 | Count | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-070 | 74 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 279 staff oriented and 432 staff vetted by June, 2026 | Increase staff efficiency | No. of staff vetted | 432 | Count | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-071 | 75 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 1,000 Staff trained by June, 2026 | Increase operational efficiency | 5 Documents prepared (TNA, Training program, Training Policy, Training Evaluation & Training Reports) | 2 | Units / To confirm | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-072 | 76 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 1,000 Staff trained by June, 2026 | Increase operational efficiency | No. of staff trained | 250 | Count | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-073 | 77 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 5 HR policies (Staff Regulations, Incentive scheme, Salary Structure,schemes of services & Training Policy) prepared by June, 2026 | Increase operational efficiency | No. of policy document prepared | 2 | Count | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-074 | 78 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | 10 Running rooms furnished by June, 2026 | Increase operational efficiency | No. of running rooms furnished | 10 | Count | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-075 | 79 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Four(4) existing systems enhanced and upgraded by June, 2026 | Increase operational efficiency | Cargo system | e-ticketing- Reporting implemented | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-076 | 80 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Four(4) existing systems enhanced and upgraded by June, 2026 | Increase operational efficiency | e-ticketing- Reporting |  | Units / To confirm | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-077 | 81 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Four(4) existing systems enhanced and upgraded by June, 2026 | Increase operational efficiency | Upgrade ERP system |  | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-078 | 82 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Four(4) existing systems enhanced and upgraded by June, 2026 | Increase operational efficiency | Land and Property Management System |  | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-079 | 83 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Three (3) new systems developed by June, 2026 | Increase operational efficiency | Maintainance system | System in place(Maintainance and overtime) | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-080 | 84 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Three (3) new systems developed by June, 2026 | Increase operational efficiency | Help desk system |  | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-081 | 85 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Three (3) new systems developed by June, 2026 | Increase operational efficiency | Overtime system |  | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-082 | 86 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Satisfactory procurement audit opinion attained by June, 2026 | Increase operational efficiency | Report |  | Units / To confirm | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-083 | 87 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Annual procurement plan implemented by June, 2026 | Increase operational efficiency | No. of contract awarded | 20 | Count | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-084 | 88 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Ensure Procurement process is completed as per timeframe standard by June, 2026 | Increase operational efficiency | 120 days International competitive tendering | Adhered | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-085 | 89 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Ensure Procurement process is completed as per timeframe standard by June, 2026 | Increase operational efficiency | 90 days national competitive tendering |  | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-086 | 90 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Ensure Procurement process is completed as per timeframe standard by June, 2026 | Increase operational efficiency | 90 days Restricted national competitive tendering |  | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-087 | 91 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Ensure Procurement process is completed as per timeframe standard by June, 2026 | Increase operational efficiency | 60 days international shopping |  | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-088 | 92 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Ensure Procurement process is completed as per timeframe standard by June, 2026 | Increase operational efficiency | 45 days national shopping |  | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-089 | 93 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Ensure Procurement process is completed as per timeframe standard by June, 2026 | Increase operational efficiency | 45 days minor value procurement |  | Units / To confirm | Core Operational | No | Main Monthly Report Body | Important for operational control and explains movement in headline performance indicators.
KPI-090 | 94 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Capacity and staff competence ensured by June, 2026 | Increase operational efficiency | User departments (US) and Tender Board members | 1 | Units / To confirm | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.
KPI-091 | 95 | CORPORATION OPERATIONAL EFFICIENCY ENHANCED | Capacity and staff competence ensured by June, 2026 | Increase operational efficiency | PMU staff | 1 | Units / To confirm | Supporting | No | Annex / Departmental Tracker | Useful for departmental follow-up, process control, or explanatory analysis rather than headline reporting.

## 09 Master KPI Register
TRC Master KPI Register
KPI ID | Strategic Objective / Result Area | KPI Title | KPI Tier | Functional Area | Definition | Unit | Baseline | FY 2025/26 Target | Reporting Frequency | Responsible Unit | Primary Data Source | Recommended Reporting Location | Management Note | Data Quality Note
KPI-001 | Railway Transport and Logistics Services Improved | MGR Freight Volume Transported | Critical | Operations | Metric tons of MGR freight transported during the reporting period. | Metric Tons |  | 414319 | Monthly | Operations / Commercial | Operating records and freight returns | Executive Dashboard | Core service and revenue indicator.
KPI-002 | Railway Transport and Logistics Services Improved | SGR Freight Volume Transported | Critical | Operations | Metric tons of SGR freight transported during the reporting period. | Metric Tons |  | 250000 | Monthly | Operations / Commercial | Operating records and freight returns | Executive Dashboard | Shows cargo uptake on SGR.
KPI-003 | Railway Transport and Logistics Services Improved | MGR Commuter Passengers Transported | Critical | Operations | Number of commuter passengers transported on MGR services. | Passengers |  | 1534406 | Monthly | Operations | Passenger manifests and ticketing records | Executive Dashboard | Headline public service indicator.
KPI-004 | Railway Transport and Logistics Services Improved | MGR Mainline Passengers Transported | Critical | Operations | Number of mainline passengers transported on MGR services. | Passengers |  | 310457 | Monthly | Operations | Passenger manifests and ticketing records | Executive Dashboard | Tracks long-distance MGR service demand.
KPI-005 | Railway Transport and Logistics Services Improved | SGR Passengers Transported | Critical | Operations | Number of passengers transported on SGR services. | Passengers |  | 1517716 | Monthly | Operations | Passenger ticketing and train records | Executive Dashboard | High-visibility corporate service indicator.
KPI-006 | Railway Infrastructure, Rolling Stock and Safety System Improved | Average Locomotives Available Per Day | Critical | Rolling Stock | Average number of locomotives available daily for service. | Number |  | 36 | Monthly | DRS / Operations | Rolling stock availability register | Executive Dashboard | Key capacity constraint indicator.
KPI-007 | Railway Infrastructure, Rolling Stock and Safety System Improved | Wagons Available for Operations | Critical | Rolling Stock | Total wagons available for operations during the reporting period. | Number |  | 772 | Monthly | DRS | Rolling stock availability register | Executive Dashboard | Supports freight delivery capacity.
KPI-008 | Railway Infrastructure, Rolling Stock and Safety System Improved | Coaches Available for Operations | Critical | Rolling Stock | Total passenger coaches available for service. | Number |  | 86 | Monthly | DRS | Rolling stock availability register | Executive Dashboard | Supports passenger service continuity.
KPI-009 | Railway Infrastructure, Rolling Stock and Safety System Improved | Mean Kilometres Before Failure | Critical | Rolling Stock | Average kilometres run before a locomotive failure occurs. | Kilometres |  |  | Monthly | DRS / Engineering | Maintenance and failure records | Executive Dashboard | Reliability indicator; baseline/target to be confirmed. | Baseline and annual target should be confirmed.
KPI-010 | Railway Infrastructure, Rolling Stock and Safety System Improved | Major Accidents Recorded - MGR | Critical | Safety | Number of major accidents recorded on MGR operations. | Number |  |  | Monthly | Safety / Operations | Safety incident register | Executive Dashboard | Should trend downward. | Target should be set as reduction target.
KPI-011 | Railway Infrastructure, Rolling Stock and Safety System Improved | Major Accidents Recorded - SGR | Critical | Safety | Number of major accidents recorded on SGR operations. | Number |  |  | Monthly | Safety / Operations | Safety incident register | Executive Dashboard | Should trend downward. | Target should be set as reduction target.
KPI-012 | Railway Infrastructure, Rolling Stock and Safety System Improved | Minor Incidents Recorded | Core Operational | Safety | Number of minor operational or safety incidents recorded. | Number |  |  | Monthly | Safety / Operations | Safety incident register | Main Report Body | Useful for trend and root-cause analysis. | Reduction target recommended.
KPI-013 | Financial Management and Marketing Strengthened | Internal Revenue Collected | Critical | Finance | Total operational and non-operational revenue collected during the reporting ... | TZS |  | 134.33 bn | Monthly | Finance | Financial reports and revenue ledgers | Executive Dashboard | Corporate financial sustainability indicator.
KPI-014 | Financial Management and Marketing Strengthened | Operating Expenditure | Core Operational | Finance | Total operating expenditure incurred during the reporting period. | TZS |  |  | Monthly | Finance | Financial reports and expenditure ledgers | Main Report Body | Should be reviewed alongside revenue. | Annual and monthly target should be confirmed.
KPI-015 | Financial Management and Marketing Strengthened | Unqualified Audit Opinion Achieved | Critical | Governance | Whether the corporation attains an unqualified audit opinion. | Status |  | Yes | Annual | Finance / Internal Audit | Audit reports | Executive Dashboard | Strategic governance indicator.
KPI-016 | Financial Management and Marketing Strengthened | Debt / Arrears Settled | Core Operational | Finance | Value or share of arrears settled during the reporting period. | TZS / % |  |  | Quarterly | Finance | Debt schedules and finance reports | Main Report Body | Supports cash and financial discipline. | Define exact unit and target.
KPI-017 | Railway Infrastructure, Rolling Stock and Safety System Improved | Line Sections Under Speed Restriction | Core Operational | Infrastructure | Length or count of sections operating under severe speed restriction. | Km / Sections |  |  | Monthly | Engineering | Track condition reports | Main Report Body | Directly affects service speed and reliability. | Baseline and target should be defined.
KPI-018 | Railway Infrastructure, Rolling Stock and Safety System Improved | Wagon Turnaround Time | Core Operational | Operations | Average number of days taken for wagon turnaround. | Days |  | 14 | Monthly | Operations | Operations and logistics records | Main Report Body | Critical explanatory operational metric.
KPI-019 | Railway Infrastructure, Rolling Stock and Safety System Improved | Track Rehabilitation Progress | Core Operational | Infrastructure | Kilometres or work packages completed under track rehabilitation programmes. | Km / % |  |  | Monthly | Engineering | Project progress reports | Main Report Body | Tracks restoration of asset condition. | Define project-specific annual targets.
KPI-020 | Railway Infrastructure, Rolling Stock and Safety System Improved | Locomotives Delivered or Rehabilitated | Core Operational | Rolling Stock | Number of locomotives delivered, rehabilitated, or remanufactured into service. | Number |  |  | Monthly | DRS / Engineering | Project and workshop reports | Main Report Body | Supports recovery plan for fleet capacity.
KPI-021 | Corporation Operational Efficiency Enhanced | Annual Procurement Plan Implementation Rate | Critical | Procurement | Share or number of planned tenders progressed to signed implementation stage. | Number / % |  | 99 planned | Monthly | DPMU | Procurement plan tracker | Executive Dashboard | Corporate delivery bottleneck indicator. | Use both count and percentage.
KPI-022 | Corporation Operational Efficiency Enhanced | Tenders Initiated | Core Operational | Procurement | Number of annual procurement plan tenders initiated. | Number |  |  | Monthly | DPMU | APP tracker | Main Report Body | Progress measure for procurement pipeline.
KPI-023 | Corporation Operational Efficiency Enhanced | Contracts Signed and Under Implementation | Core Operational | Procurement | Number of signed contracts that have moved into active implementation. | Number |  |  | Monthly | DPMU | APP tracker and contract register | Main Report Body | Practical delivery indicator.
KPI-024 | Corporation Operational Efficiency Enhanced | Development Budget Received | Critical | Development Finance | Funds received against planned development budget. | TZS |  | 976.10 bn | Monthly | DCPI / Finance | Budget disbursement records | Executive Dashboard | Major driver of project implementation pace.
KPI-025 | Corporation Operational Efficiency Enhanced | Development Budget Utilization | Core Operational | Development Finance | Level of utilization of received development budget. | TZS / % |  |  | Monthly | DCPI / Finance | Project financial reports | Main Report Body | Should be read with disbursement and physical progress. | Define exact target.
KPI-026 | Corporation Operational Efficiency Enhanced | Monthly Development Progress Reports Submitted | Supporting | Reporting | Number of required monthly development progress reports prepared and submitte... | Number |  | 12 | Monthly | M&E Unit | Submission records | Annex / Tracker | Useful for compliance and process discipline.
KPI-027 | Corporation Operational Efficiency Enhanced | Performance Contract Reports Submitted | Supporting | Reporting | Number of required performance contract reports prepared and submitted to ove... | Number |  |  | Quarterly | M&E Unit | Submission records | Annex / Tracker | Important institutional accountability process indicator.
KPI-028 | Corporation Operational Efficiency Enhanced | M&E Core Documents Completed | Supporting | Institutional M&E | Number of required M&E core documents prepared and finalized. | Number |  | 5 | Quarterly | M&E Unit | Approved M&E documents | Annex / Tracker | Tracks institutionalization of the M&E system.
KPI-029 | Corporation Operational Efficiency Enhanced | M&E Champions Trained / Coached | Supporting | Capacity Building | Number of staff or champions trained/coached in M&E practice. | Number |  |  | Quarterly | M&E Unit / HR | Training records | Annex / Tracker | Supports reporting quality and institutional learning.
KPI-030 | Corporation Operational Efficiency Enhanced | Evaluation Workplan Implementation | Supporting | Evaluation | Progress in implementing planned evaluations, reviews, or learning exercises. | Status / % |  |  | Quarterly | M&E Unit | Evaluation workplan tracker | Annex / Tracker | Ensures evaluation function is active.
KPI-031 | Corporation Operational Efficiency Enhanced | SGR Mini Lab Preparatory Actions Completed | Supporting | Strategic Coordination | Completion status of agreed preparatory actions for the SGR Mini Lab process. | Status |  |  | Quarterly | M&E Unit / Coordination Team | Meeting notes and planning records | Annex / Tracker | Supports strategic coordination and problem-solving.

## 10 KPI Register Summary
TRC KPI Register Summary
Overview of the KPI register for use in the monitoring plan and monthly reporting.
Tier | Definition | Count | Default Reporting Use | Suggested Review Frequency | Comment
Critical | Headline indicators affecting safety, service delivery, finance, or strategic delivery. | 12 | Executive Dashboard | Monthly | Keep these visible to management every month.
Core Operational | Important performance and delivery indicators that explain the movement of critical KPIs. | 13 | Main Monthly Report Body | Monthly / Quarterly | Use these to explain operational strengths and weaknesses.
Supporting | Process, compliance, capacity-building, and institutional indicators for detailed follow-up. | 9 | Annex / Tracker | Quarterly | Retain these for completeness and internal control.
Immediate Advice to TRC M&E Unit
1 | Adopt this as the cleaned master KPI reference list before updating the monitoring plan.
2 | Confirm missing baselines and targets for indicators marked with data-quality notes.
3 | Use KPI Tier to control what appears on the dashboard versus in the main report body.
4 | Assign one named data owner for every KPI and enforce the agreed reporting frequency.
5 | Review this register quarterly to add, merge, or retire indicators that are no longer useful.

## 11 KPI Register Guide
How to Use the Cleaned Master KPI Register
This sheet explains how the register should be used within the monitoring plan and reporting system.
1 | Use this register as the official cleaned reference for KPI naming, categorization, and ownership.
2 | Critical KPIs should feed the executive dashboard and management summary.
3 | Core Operational KPIs should appear in the main monthly report body.
4 | Supporting KPIs should be kept in annexes, trackers, and internal control sheets.
5 | Where baseline or target is blank, the M&E Unit should validate and complete the field before routine reporting.
6 | This register should remain aligned to the corporate monitoring plan, evaluation workplan, and data validation process.

## 12 Quarterly Report Extractor
Quarterly Report Extractor | Quarterly Report Extractor | Quarterly Report Extractor | Quarterly Report Extractor | Quarterly Report Extractor | Quarterly Report Extractor | Quarterly Report Extractor | Quarterly Report Extractor | Quarterly Report Extractor | Quarterly Report Extractor | Quarterly Report Extractor
This sheet rolls up three monthly periods from the Corporate M&E Matrix into one quarterly view for reporting, review, and committee use. | This sheet rolls up three monthly periods from the Corporate M&E Matrix into one quarterly view for reporting, review, and committee use. | This sheet rolls up three monthly periods from the Corporate M&E Matrix into one quarterly view for reporting, review, and committee use. | This sheet rolls up three monthly periods from the Corporate M&E Matrix into one quarterly view for reporting, review, and committee use. | This sheet rolls up three monthly periods from the Corporate M&E Matrix into one quarterly view for reporting, review, and committee use. | This sheet rolls up three monthly periods from the Corporate M&E Matrix into one quarterly view for reporting, review, and committee use. | This sheet rolls up three monthly periods from the Corporate M&E Matrix into one quarterly view for reporting, review, and committee use. | This sheet rolls up three monthly periods from the Corporate M&E Matrix into one quarterly view for reporting, review, and committee use. | This sheet rolls up three monthly periods from the Corporate M&E Matrix into one quarterly view for reporting, review, and committee use. | This sheet rolls up three monthly periods from the Corporate M&E Matrix into one quarterly view for reporting, review, and committee use. | This sheet rolls up three monthly periods from the Corporate M&E Matrix into one quarterly view for reporting, review, and committee use.
Quarter # | 2 |  | Quarter Name | Q2 (Oct-Dec) |  | How to use | Change B4 only. The extractor will summarize the corresponding three-month period automatically. | Change B4 only. The extractor will summarize the corresponding three-month period automatically. | Change B4 only. The extractor will summarize the corresponding three-month period automatically. | Change B4 only. The extractor will summarize the corresponding three-month period automatically.
Quarterly Summary
Total KPIs | On Track | Off Track | Not Reported | High Risk | Critical KPIs
34 | 0 | 0 | 0 | 0 | 11
KPI ID | Objective / Result Area | KPI Title | KPI Tier | Responsible Unit | Quarter Plan | Quarter Actual | Variance | Quarterly Status | Risk Level | Comments
KPI-001 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | No. of km speed restriction reduced | Core Operational | To be assigned | 0 | 0 | 0 | On Track | Medium | Source note: Speed restriction was reduced within 15.5km ¦ Deviation in source: 5.5km
KPI-002 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | % of curves/gradient realigned/relocated | Core Operational | To be assigned | 0.2 | 0 | -0.2 | Off Track | Low | Source note: 0.5km was realigned/relocated ¦ Deviation in source: -0.94
KPI-003 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | No. of rail km joined | Core Operational | To be assigned | 0 | 0 | 0 | On Track | 151 | Source note: 1.6 km joined ¦ Deviation in source: -8.4
KPI-004 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | No of km relayed | Core Operational | To be assigned | 0 | 0 | 0 | On Track | 151 | Source note: 1.7 km relayed ¦ Deviation in source: -8.3
KPI-005 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | No. of km ballasted | Core Operational | To be assigned | 0 | 0 | 0 | On Track | 151 | Source note: 0
KPI-006 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | No. of sidings established | Core Operational | To be assigned | 0 | 0 | 0 | On Track | 151 | Jan actual narrative: The work completed ¦ Source note: The work completed
KPI-007 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | No. of Km of railway line rehabilitated | Core Operational | To be assigned | 0 | 0 | 0 | On Track | 151 | Source note: None ¦ Deviation in source: -10
KPI-008 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | % of works completed | Core Operational | To be assigned | 0.4 | 0 | -0.4 | Off Track | 151 | Source note: 0.1 ¦ Deviation in source: =F12-E12
KPI-009 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | No. of km of speed restriction | Core Operational | To be assigned | 0 | 0 | 0 | On Track | 151 | Source note: 98.0km of SGR were maintained ¦ Deviation in source: (624.0km)
KPI-010 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | No. of Locomotives available for operations | Critical | To be assigned | 108 | 0 | -108 | Off Track | 151 | Source note: A total of 18 locomotives were available equals to 50% of target ¦ Deviation in source: -18
KPI-011 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | Mean Kilometers Before Failure | Critical | To be assigned | 41000 | 0 | -41000 | Off Track | 151 | Source note: Locomotives were travelled 6,960 km before failure compared to the target of 17,000km/failure (40.94%) ¦ Deviation in source: -5040
KPI-012 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | No. of coaches available | Critical | To be assigned | 213 | 0 | -213 | Off Track | 151 | Source note: A total of 97 coaches were available agaist a target of 87 coaches.The target was attained by 111.49 percent ¦ Deviation in source: 10
KPI-013 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | % of wagons available | Critical | To be assigned | 2378 | 0 | -2378 | Off Track | 151 | Source note: A total of 870 wagons wa available against a target of 846 coaches.The target was attained by 102.83 percent ¦ Deviation in source: 46
KPI-014 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | No. of wagons roll out for operation | Core Operational | To be assigned | 60 | 0 | -60 | Off Track | 151 | Source note: wagons were not rehabilited ¦ Deviation in source: 0
KPI-015 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | No. of wagons delivered | Core Operational | To be assigned | 0 | 0 | 0 | On Track | 151 | Source note: MGR wagons delivered, now under operations ¦ Deviation in source: 0
KPI-016 | RAILWAY INFRASTRUCTURE, ROLLING STOCK AND SAFETY SYSTEM IMPROVED | No. of Locomotive | Core Operational | To be assigned | 8 | 0 | -8 | Off Track | 151 | Source note: MGR locomotives have been delivered and are under Operations. ¦ Deviation in source: 0
KPI-017 | FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | Unqualified opinion | Critical | To be assigned | 0 | 0 | 0 | On Track | Medium | Source note: The audit for the finacial year 2024/25 completed and report submitted to the office of controller and Auditor General for review.
KPI-018 | FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | Advisory Audit consultant in place | Supporting | To be assigned | 0 | 0 | 0 | On Track | 151 | Jan actual narrative: Tax Audit consultant is in place ¦ Source note: Tax Audit consultant is in place
KPI-019 | FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | Financial Management Report | Supporting | To be assigned | 1 | 0 | -1 | Off Track | Medium | Jan actual narrative: Second quarter finanacial management report were prepared ¦ Source note: Preparation of second quarter finanacial management report is ongoing
KPI-020 | FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | Financial Management Report | Supporting | To be assigned | 0 | 0 | 0 | On Track | 151 | Source note: Financial statement for the Financial year 2024/25 prepared and submitted to the office of Controller and Auditor General
KPI-021 | FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | Tshs. Collected | Critical | To be assigned | 1479793115.16 | 0 | -1479793115.16 | Off Track | 151 | 151
KPI-022 | FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | Tshs. Settled | Core Operational | To be assigned | 2426798211.12 | 0 | -2426798211.12 | Off Track | 151 | 151
KPI-023 | FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | Tshs. Collected | Critical | To be assigned | 67929654680.9191 | 0 | -67929654680.9191 | Off Track | 151 | Source note: A total of 11,131,111,301.09 was collected equals to 47.83 percent of the target.
KPI-024 | FINANCIAL MANAGEMENT AND MARKETING STRENGTHENED | Report | Supporting | To be assigned | 0 | 0 | 0 | On Track | Medium | Source note: The Draft Audit Report has been prepared and submitted to auditee for Management Response
KPI-025 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | No. Metric tons transported | Critical | To be assigned | 217738.4282 | 0 | -217738.4282 | Off Track | 151 | Source note: 15,451 tonnes for MGR were hauled equals to 19.37 percent of the planned target ¦ Deviation in source: =F33-E33
KPI-026 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Ton-km | Core Operational | To be assigned | 204550428.0672 | 0 | -204550428.0672 | Off Track | 151 | Source note: 2,517,291 ton per km was attained ¦ Deviation in source: =F34-E34
KPI-027 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | No. Metric tons transported | Critical | To be assigned | 125000 | 0 | -125000 | Off Track | 151 | Source note: 8,625 tonnes for SGR were hauled equals to 20.70 percent of the planned target ¦ Deviation in source: =F35-E35
KPI-028 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Ton-km | Core Operational | To be assigned | 56125000 | 0 | -56125000 | Off Track | 151 | Source note: 991,875 ton per km was attained ¦ Deviation in source: =F36-E36
KPI-029 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | No. of passengers transported | Critical | To be assigned | 140458.4373 | 0 | -140458.4373 | Off Track | 151 | Source note: 18,341 Mainline Passengers for MGR were transported equals to 47.23 percent of the planned target. ¦ Deviation in source: =F37-E37
KPI-030 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Pax-km | Core Operational | To be assigned | 102176234.8525 | 0 | -102176234.8525 | Off Track | 151 | Source note: 8,542,160 passenger per km were attained ¦ Deviation in source: =F38-E38
KPI-031 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | No. of passengers transported | Critical | To be assigned | 768805.8729 | 0 | -768805.8729 | Off Track | 151 | Source note: 271,642 Mainline Passengers for SGR were transported equals to 112.35 percent of the planned target. ¦ Deviation in source: =F39-E39
KPI-032 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | Pax-km | Core Operational | To be assigned | 238152947.0552 | 0 | -238152947.0552 | Off Track | 151 | Source note: 82,935,299 passenger per km were attained ¦ Deviation in source: =F40-E40
KPI-033 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | No. of passengers transported | Critical | To be assigned | 732682.3737 | 0 | -732682.3737 | Off Track | 151 | Source note: 110,759 Commuter Passengers were transported equals to 40.36 percent of the planned target. ¦ Deviation in source: =F41-E41
KPI-034 | RAILWAY TRANSPORT AND LOGISTICS SERVICES IMPROVED | No. of plots demarcated | Core Operational | To be assigned | 14 | 0 | -14 | Off Track | Medium | Jan actual narrative: Demarcation was not done ¦ Source note: Demarcation was not done